## Sheet1
Activity ID* | Activity Name* | BL Project Total Cost | Actual Total Cost | Remaining Total Cost | At Completion Total Cost | Variance BL Project - Total Cost | Performance % Complete | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Duration | Actual Duration | Planned Total Cost | Activity % Complete
M-L.MCN.108681 | Awaiting Gate D - Kidbrooke Park Road SE3 9PX | 296935 | 62380 | 0 | 62380 | 242231 | 100% | 01-Jul-22 09:00 AM | 31-Oct-24 04:00 PM | 01-Jul-22 09:00 AM |  | 584.9d | 310.9d | 44812
A5310 | Early Support AOT |  | 7676 | 0 | 7676 |  | 100% | 03-Apr-23 08:00 AM | 03-Apr-23 09:00 AM | 20-Mar-23 09:00 AM | 02-May-23 08:00 AM | 0.1d | 27.9d | 14812 | 100%
1 | Project Summary | 0 | 0 | 0 | 0 | 0 | 0% | 13-Oct-22 08:00 AM | 31-Oct-24 04:00 PM | 13-Oct-22 08:00 AM |  | 513.0d | 146.5d | 0
6 | Project Governance Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-23 08:00 AM | 31-Oct-24 04:00 PM | 13-Oct-22 04:00 PM |  | 420.0d | 133.0d | 0
Gate1000 | Gate A Award | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 08:00 AM | 01-Mar-23 08:00 AM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
Gate1010 | Gate B Award | 0 | 0 | 0 | 0 | 0 | 100% | 05-May-23 04:00 PM | 05-May-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
Gate1020 | Gate C Award | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1050 | Gate D Award | 0 | 0 | 0 | 0 | 0 | 0% | 31-Oct-24 04:00 PM | 31-Oct-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
Gate1040 | Hong Kong Board Review | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1030 | Executive Management Team Review | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
9 | Construction Delivery Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 25-Jan-23 09:00 AM | 31-Oct-24 04:00 PM | 13-Oct-22 04:00 PM | 02-May-23 04:00 PM | 444.9d | 134.0d | 0
DEL1050 | Start on Site | 0 | 0 | 0 | 0 | 0 | 100% | 25-May-23 04:00 PM | 25-May-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1080 | Hot Commissioning Commencement | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1130 | Customer (MC or APP) Energisation available | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1090 | Li Intervention | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1060 | Hi Intervention | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1140 | Site Demobilisation Complete | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1100 | Switchgear Energised | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1110 | Tx1 Energised | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1120 | Cct 1 Energised | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1070 | Practical Completion | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1010 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 04-May-23 04:00 PM | 04-May-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1000 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 25-Jan-23 09:00 AM | 25-Jan-23 09:00 AM | 25-Jan-23 09:00 AM | 25-Jan-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1030 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building/Route/Earthing/Component) | 0 | 0 | 0 | 0 | 0 | 100% | 02-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1040 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1020 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1150 | Customer Required By energisation date | 0 | 0 | 0 | 0 | 0 | 100% | 31-Oct-24 04:00 PM | 31-Oct-24 04:00 PM | 02-May-23 04:00 PM | 02-May-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
10 | Alliance Engagement Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 08-Dec-22 04:00 PM | 19-May-23 08:00 AM | 08-Dec-22 04:00 PM | 02-May-23 08:00 AM | 105.0d | 93.0d | 0
AL1000 | Project Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 08-Dec-22 04:00 PM | 08-Dec-22 04:00 PM | 08-Dec-22 04:00 PM | 08-Dec-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
AL1090 | Alliance Delivery Proposal Received (ADP) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL2000 | ADP Approved by AMT | 0 | 0 | 0 | 0 | 0 | 100% | 12-May-23 08:00 AM | 12-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL2010 | Award WPO Contract | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL1040 | Acceptance of AIP by Delivery Member | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL1050 | Award PSC Contract - Developed Design | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL1010 | Award PSC Contract - Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 27-Jan-23 04:00 PM | 27-Jan-23 04:00 PM | 27-Jan-23 04:00 PM | 27-Jan-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
8 | Asset Registration/Update Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-23 09:00 AM | 19-May-23 08:00 AM | 01-Mar-23 09:00 AM | 02-May-23 08:00 AM | 52.9d | 40.9d | 0
ASS1030 | Asset Data - Updated (SAP -Switchgear) | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
ASS1040 | Asset Data - Updated (Netmap - Cable records) | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
ASS1010 | Asset Data - Registration (SAP) - Transformer n/a | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
ASS1000 | Asset Data - Registration (Netmap) | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
ASS1020 | Asset Data - Registration (SAP) - Switchgear n/a | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
ASS1050 | Asset Data - Updated (SAP - Transformer) | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
7 | Project Closeout Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 02-May-23 08:00 AM | 01-Jun-23 09:00 AM | 02-May-23 08:00 AM | 02-May-23 09:00 AM | 20.1d | 0.1d | 0
CLO1000 | Project Completion | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-23 09:00 AM | 01-Jun-23 09:00 AM | 02-May-23 09:00 AM | 02-May-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
CLO1020 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-23 09:00 AM | 01-Jun-23 09:00 AM | 02-May-23 09:00 AM | 02-May-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
CLO1030 | Financial Close | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-23 09:00 AM | 01-Jun-23 09:00 AM | 02-May-23 09:00 AM | 02-May-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
CLO1050 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CLO1010 | Completion Certificate Signed off | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CLO1060 | Completion of the Health and Safety File | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
1 | Project Specific Milestones - Inc. Contract Data | 0 | 0 | 0 | 0 | 0 | 0% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0
ProjKM1000 | Consent Conveyacing Pack Submission | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM1020 | Project Consents Executed | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
TASK DESIGN DELIVERY MILESTONES | TASK DESIGN DELIVERY MILESTONES (DO NOT DELETE or CHANGE ACTIVITY ID) | 0 | 0 | 0 | 0 | 0 | 0% | 13-Oct-22 08:00 AM | 01-Jun-23 09:00 AM | 13-Oct-22 08:00 AM | 19-May-23 12:00 PM | 154.1d | 146.5d | 0
DES-DM1 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 24-Jan-23 09:00 AM | 25-Jan-23 09:00 AM | 24-Jan-23 09:00 AM | 25-Jan-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
DES-DM2 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 13-Oct-22 08:00 AM | 13-Oct-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM3 | Risk & Value Intevention A-B | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-22 08:00 AM | 13-Oct-22 04:00 PM | 13-Oct-22 08:00 AM | 13-Oct-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM4 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-22 08:00 AM | 13-Oct-22 04:00 PM | 13-Oct-22 08:00 AM | 13-Oct-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM5 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DES-DM6 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DES-DM7 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building / Route / Earthing / Component) | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
DES-DM8 | Risk & Value Intevention B-C | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DES-DM9 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DES-DM10-1 | Asset Data - Registration (SAP) - Transformer | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
DES-DM10-2 | Asset Data - Registration (SAP) - Switchgear | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
DES-DM11 | Pre-Construction Information - PCI Documentation (CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
DES-DM12 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
DES-DM13 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 12:00 PM | 19-May-23 12:00 PM | 02-May-23 08:00 AM | 19-May-23 12:00 PM | 0.0d | 12.5d | 0 | 100%
DES-DM14 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-23 09:00 AM | 01-Jun-23 09:00 AM | 02-May-23 09:00 AM | 02-May-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
2 | Pre Gate B | 0 | 20025 | 0 | 20025 | (20,025) | 0% | 01-Jul-22 09:00 AM | 15-Sep-23 04:00 PM | 01-Jul-22 09:00 AM | 03-Feb-23 04:00 PM | 301.9d | 147.9d | 5000
1 | Project Management | 0 | 20025 | 0 | 20025 | (20,025) | 0% | 01-Mar-23 08:00 AM | 15-Sep-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 137.0d | 0.0d | 5000
1 | Project Manager | 0 | 4522 | 0 | 4522 | (4,522) | 0% | 01-Mar-23 08:00 AM | 15-Sep-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 137.0d | 0.0d | 2000
PMA-B0010 | Indirect Project Management Pre-Gate B Cost Bar | 0 | 4522 | 0 | 4522 | (4,522) | 100% | 01-Mar-23 08:00 AM | 15-Sep-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 137.0d | 0.0d | 2000 | 100%
2 | Quantity Surveyor | 0 | 13230 | 0 | 13230 | (13,230) | 0% | 01-Mar-23 08:00 AM | 15-Sep-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 137.0d | 0.0d | 1000
PMA-B0020 | QS Pre-Gate B Cost Bar | 0 | 13230 | 0 | 13230 | (13,230) | 100% | 01-Mar-23 08:00 AM | 15-Sep-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 137.0d | 0.0d | 1000 | 100%
3 | P6 Planner | 0 | 2273 | 0 | 2273 | (2,273) | 0% | 01-Mar-23 08:00 AM | 15-Sep-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 137.0d | 0.0d | 2000
PMA-B0030 | Project Planner Pre-Gate B Cost Bar | 0 | 2273 | 0 | 2273 | (2,273) | 100% | 01-Mar-23 08:00 AM | 15-Sep-23 04:00 PM | 13-Oct-22 04:00 PM | 13-Oct-22 04:00 PM | 137.0d | 0.0d | 2000 | 100%
2 | PM Activities | 0 | 0 | 0 | 0 | 0 | 0% | 14-Nov-22 09:00 AM | 06-Feb-23 04:00 PM | 13-Oct-22 04:00 PM | 03-Feb-23 04:00 PM | 54.9d | 75.0d | 0
Al0010 | Start 1st Draft PEP & AIP | 0 | 0 | 0 | 0 | 0 | 100% | 13-Jan-23 04:00 PM | 13-Jan-23 04:00 PM | 13-Jan-23 04:00 PM | 13-Jan-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
FEED-A-B-M-0003 | Works Information & contract Scope Complete & Agreed (PSC) | 0 | 0 | 0 | 0 | 0 | 100% | 20-Jan-23 04:00 PM | 20-Jan-23 04:00 PM | 20-Jan-23 04:00 PM | 20-Jan-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
FEED-0040 | Build Gate B-C Detailed Programme containing High level Gate C-D | 0 | 0 | 0 | 0 | 0 | 100% | 06-Feb-23 08:00 AM | 06-Feb-23 04:00 PM | 13-Oct-22 04:00 PM | 14-Oct-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
A2640 | Work Order Number Raised | 0 | 0 | 0 | 0 | 0 | 100% | 14-Nov-22 09:00 AM | 14-Nov-22 09:00 AM | 14-Nov-22 09:00 AM | 14-Nov-22 09:00 AM | 0.0d | 0.0d | 0 | 100%
A2920 | Mobilise | 0 | 0 | 0 | 0 | 0 | 100% | 30-Jan-23 08:00 AM | 03-Feb-23 04:00 PM | 30-Jan-23 08:00 AM | 03-Feb-23 04:00 PM | 5.0d | 5.0d | 0 | 100%
A3010 | Early Engagement in place for Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 12-Dec-22 09:00 AM | 12-Dec-22 09:00 AM | 12-Dec-22 09:00 AM | 12-Dec-22 09:00 AM | 0.0d | 0.0d | 0 | 100%
3 | OP&C Wayleave/Planng Permission/Consents | 0 | 0 | 0 | 0 | 0 | 0% | 11-Apr-23 08:00 AM | 09-May-23 04:00 PM | 03-Oct-22 08:00 AM | 13-Oct-22 03:00 PM | 19.0d | 8.9d | 0
OP&C2000 | Wayleave Permissions/Planning Consents | 0 | 0 | 0 | 0 | 0 | 100% | 11-Apr-23 08:00 AM | 09-May-23 04:00 PM | 03-Oct-22 08:00 AM | 13-Oct-22 03:00 PM | 19.0d | 8.9d | 0 | 100%
5 | Enabling / Preparation Works | 0 | 0 | 0 | 0 | 0 | 0% | 11-Apr-23 08:00 AM | 24-Apr-23 04:00 PM | 03-Oct-22 08:00 AM | 13-Oct-22 03:00 PM | 10.0d | 8.9d | 0
EN-A-B-0010 | Enabling Works | 0 | 0 | 0 | 0 | 0 | 100% | 11-Apr-23 08:00 AM | 24-Apr-23 04:00 PM | 03-Oct-22 08:00 AM | 13-Oct-22 03:00 PM | 10.0d | 8.9d | 0 | 100%
9 | Concept Design | 0 | 0 | 0 | 0 | 0 | 0% | 01-Jul-22 09:00 AM | 31-Jan-23 09:00 AM | 01-Jul-22 09:00 AM | 26-Aug-22 09:00 AM | 144.0d | 40.0d | 0
FEED-A-B-M-0006 | Concept Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 17-Jan-23 09:00 AM | 31-Jan-23 09:00 AM | 11-Jul-22 09:00 AM | 22-Jul-22 04:00 PM | 10.0d | 9.9d | 0 | 100%
A4530 | Site Visit | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jul-22 09:00 AM | 04-Jul-22 09:00 AM | 01-Jul-22 09:00 AM | 04-Jul-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A4540 | Site information review/ Protection Phylosophy/ Preliminary Layouts | 0 | 0 | 0 | 0 | 0 | 100% | 04-Jul-22 09:00 AM | 15-Jul-22 09:00 AM | 04-Jul-22 09:00 AM | 15-Jul-22 09:00 AM | 9.0d | 9.0d | 0 | 100%
A4550 | Trial Holes / Surveys | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jul-22 09:00 AM | 09-Aug-22 09:00 AM | 01-Jul-22 09:00 AM | 09-Aug-22 09:00 AM | 27.0d | 27.0d | 0 | 100%
A4560 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 10-Aug-22 09:00 AM | 10-Aug-22 09:00 AM | 10-Aug-22 09:00 AM | 10-Aug-22 09:00 AM | 0.0d | 0.0d | 0 | 100%
A4580 | Risk & Value Intevention | 0 | 0 | 0 | 0 | 0 | 100% | 11-Aug-22 09:00 AM | 12-Aug-22 09:00 AM | 11-Aug-22 09:00 AM | 12-Aug-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A4590 | Layouts ready for estimating | 0 | 0 | 0 | 0 | 0 | 100% | 15-Aug-22 09:00 AM | 22-Aug-22 09:00 AM | 15-Aug-22 09:00 AM | 22-Aug-22 09:00 AM | 5.0d | 5.0d | 0 | 100%
A4600 | Concept Design Review | 0 | 0 | 0 | 0 | 0 | 100% | 22-Aug-22 09:00 AM | 23-Aug-22 09:00 AM | 22-Aug-22 09:00 AM | 23-Aug-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A4740 | Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 10-Aug-22 09:00 AM | 11-Aug-22 09:00 AM | 10-Aug-22 09:00 AM | 11-Aug-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A4750 | Publish Concept Design Documents & Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 25-Aug-22 09:00 AM | 26-Aug-22 09:00 AM | 25-Aug-22 09:00 AM | 26-Aug-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A4760 | Prepare Design cost estimate for Developed & Technical stage (CAP15/16) | 0 | 0 | 0 | 0 | 0 | 100% | 24-Aug-22 09:00 AM | 25-Aug-22 09:00 AM | 24-Aug-22 09:00 AM | 25-Aug-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A4910 | Environmental Survey | 0 | 0 | 0 | 0 | 0 | 100% | 15-Jul-22 09:00 AM | 18-Jul-22 09:00 AM | 15-Jul-22 09:00 AM | 18-Jul-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A4920 | Risk & Value Intevention A-B | 0 | 0 | 0 | 0 | 0 | 100% | 15-Aug-22 09:00 AM | 15-Aug-22 09:00 AM | 15-Aug-22 09:00 AM | 15-Aug-22 09:00 AM | 0.0d | 0.0d | 0 | 100%
7 | Gate B Governance | 0 | 0 | 0 | 0 | 0 | 0% | 24-Aug-22 09:00 AM | 05-May-23 04:00 PM | 24-Aug-22 09:00 AM | 20-Sep-22 04:00 PM | 171.9d | 17.9d | 0
FEED-A-B-M-0010 | Issue AIP | 0 | 0 | 0 | 0 | 0 | 100% | 08-Sep-22 09:00 AM | 08-Sep-22 09:00 AM | 08-Sep-22 09:00 AM | 08-Sep-22 09:00 AM | 0.0d | 0.0d | 0 | 100%
Gate2030 | Submit Gate B Paper to RPfB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 100% | 20-Sep-22 08:00 AM | 20-Sep-22 08:00 AM | 20-Sep-22 08:00 AM | 20-Sep-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
FEED-2350 | Update PEP | 0 | 0 | 0 | 0 | 0 | 100% | 24-Aug-22 09:00 AM | 26-Aug-22 09:00 AM | 24-Aug-22 09:00 AM | 26-Aug-22 09:00 AM | 2.0d | 2.0d | 0 | 100%
Gate2000 | Prepare Gate B Paper | 0 | 0 | 0 | 0 | 0 | 100% | 01-Sep-22 09:00 AM | 08-Sep-22 09:00 AM | 01-Sep-22 09:00 AM | 08-Sep-22 09:00 AM | 5.0d | 5.0d | 0 | 100%
A2720 | Risk & Value workshop | 0 | 0 | 0 | 0 | 0 | 100% | 02-Sep-22 08:00 AM | 02-Sep-22 04:00 PM | 02-Sep-22 08:00 AM | 02-Sep-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
A2770 | GATE B Presentation at AMT | 0 | 0 | 0 | 0 | 0 | 100% | 05-May-23 08:00 AM | 05-May-23 04:00 PM | 20-Sep-22 08:00 AM | 20-Sep-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
A2880 | Network Design Review (NDR) | 0 | 0 | 0 | 0 | 0 | 100% | 08-Sep-22 09:00 AM | 09-Sep-22 09:00 AM | 08-Sep-22 09:00 AM | 09-Sep-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A2890 | Risk Advisory Board (RAB) Revirew | 0 | 0 | 0 | 0 | 0 | 100% | 13-Sep-22 09:00 AM | 14-Sep-22 09:00 AM | 13-Sep-22 09:00 AM | 14-Sep-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
A2900 | Update P6 programme & Cost phasing | 0 | 0 | 0 | 0 | 0 | 100% | 24-Aug-22 09:00 AM | 01-Sep-22 09:00 AM | 24-Aug-22 09:00 AM | 01-Sep-22 09:00 AM | 5.0d | 5.0d | 0 | 100%
A2910 | Gate B CU Design | 0 | 0 | 0 | 0 | 0 | 100% | 24-Aug-22 09:00 AM | 01-Sep-22 09:00 AM | 24-Aug-22 09:00 AM | 01-Sep-22 09:00 AM | 5.0d | 5.0d | 0 | 100%
A2795 | ADM Review and acceptance of AIP | 0 | 0 | 0 | 0 | 0 | 100% | 08-Sep-22 09:00 AM | 13-Sep-22 09:00 AM | 08-Sep-22 09:00 AM | 13-Sep-22 09:00 AM | 3.0d | 3.0d | 0 | 100%
A5130 | Gate B QRA Workshop | 0 | 0 | 0 | 0 | 0 | 100% | 14-Sep-22 09:00 AM | 15-Sep-22 09:00 AM | 14-Sep-22 09:00 AM | 15-Sep-22 09:00 AM | 1.0d | 1.0d | 0 | 100%
3 | Gate B-C | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-23 09:00 AM | 19-May-23 08:00 AM | 13-Oct-22 04:00 PM | 19-May-23 08:00 AM | 52.9d | 145.0d | 0
A2780 | B to C Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A2790 | Update PEP, Formalise AIP & Appendix B, Set Target Budget | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A2800 | Review of Target Budget and sign off | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A3046 | Mobilise | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A3030 | Prepare PSC | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A3040 | PSC Review period | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A3035 | Finalise PSC | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
1 | Project Management | 0 | 0 | 0 | 0 | 0 | 0% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0
1 | Project Manager | 0 | 0 | 0 | 0 | 0 | 0% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0
PMB-C2120 | Indirect Project Manager B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0 | 100%
2 | Quantity Surveyor | 0 | 0 | 0 | 0 | 0 | 0% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0
PMB-C2140 | QS B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0 | 100%
3 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 0% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0
PMB-C2130 | Project Planner B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0 | 100%
2 | Design / Surveys / OP&C | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-23 09:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 44.9d | 133.0d | 0
OP&C2010 | Wayleaves/Consents Approval | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
PMB-C2020 | Principal Design Co-ordinator/SHES - Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0 | 100%
DESIGNB-C-0001 | Design B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-23 08:00 AM | 09-May-23 08:00 AM | 13-Oct-22 04:00 PM | 02-May-23 08:00 AM | 0.0d | 133.0d | 0 | 100%
A2360 | SAP/Commissioning Engineer/Project Engineer Early Engagement | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4620 | Developed Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4630 | Prepare Developed design PSC | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4640 | Order Placed/Request Supplier Preliminary Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
A4660 | Compile Documents Layout for Construction - Civils/Electrical/Route/M&E) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4670 | Detailed Third Party Review (Asset Management / Networ Ops) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4680 | Developed Design Review | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4770 | Specification and layouts for Tendering | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4780 | Developed Design 3rd Party | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4790 | Developed Design - UKPN Internal | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4800 | Publish Developed Design Documents & Drawings/Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4810 | Surveys | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4930 | Risk & Value Intevention (AST 00 008) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4940 | Risk & Value Intevention B-C | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4950 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A5000 | Supplier Preliminary Drawings Preparation/Review | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
A5020 | Completion of Developed Design | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
4 | Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0
PRC B-C-1000 | B-C Long Lead Procurement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
5 | Gate C Governance | 0 | 0 | 0 | 0 | 0 | 0% | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 12.0d | 12.0d | 0
A2754 | Review of ADP by PM and Project Team | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1031 | Prepare Gate C Paper | 0 | 0 | 0 | 0 | 0 | 100% | 10-May-23 08:00 AM | 10-May-23 08:00 AM | 02-May-23 08:00 AM | 10-May-23 08:00 AM | 0.0d | 5.0d | 0 | 100%
Gate1041 | Submit Gate C Paper to RPfB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 100% | 16-May-23 04:00 PM | 16-May-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1035 | ADP Presentation at AMT | 0 | 0 | 0 | 0 | 0 | 100% | 12-May-23 08:00 AM | 12-May-23 08:00 AM | 02-May-23 08:00 AM | 12-May-23 08:00 AM | 0.0d | 7.0d | 0 | 100%
A2753 | Risk Advisory Board (RAB) Revirew | 0 | 0 | 0 | 0 | 0 | 100% | 12-May-23 08:00 AM | 12-May-23 08:00 AM | 02-May-23 08:00 AM | 12-May-23 08:00 AM | 0.0d | 1.0d | 0 | 100%
A2752 | Prepare Alliance Delivery Proposal (ADP) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
Q3056 | Prepare WPO | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A4510 | Network Design Review (NDR) | 0 | 0 | 0 | 0 | 0 | 100% | 16-May-23 08:00 AM | 16-May-23 08:00 AM | 02-May-23 08:00 AM | 16-May-23 08:00 AM | 0.0d | 2.0d | 0 | 100%
A5140 | Gate C QRA Workshop | 0 | 0 | 0 | 0 | 0 | 100% | 12-May-23 08:00 AM | 12-May-23 08:00 AM | 02-May-23 08:00 AM | 12-May-23 08:00 AM | 0.0d | 1.0d | 0 | 100%
4 | Gate C-D | 296935 | 34680 | 0 | 34680 | 262256 | 100% | 01-Mar-23 09:00 AM | 20-Sep-24 04:00 PM | 01-Mar-23 09:00 AM |  | 390.9d | 145.9d | 25000
CONT100 | Contract Data - Start Date | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CONT110 | Contract Data - Access Date (Date to be set as per contract info) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CONT130 | Contract Data - Key Date (Add as required)?? | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CONT140 | Contract Data - Completion Date for the Whole of the Works | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
1 | Project Management | 14643 | 4671 | 0 | 4671 | 9972 | 100% | 02-May-23 08:00 AM | 14-Jun-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 30.0d | 1.0d | 0
411 | Project Manager | 8634 | 4671 | 0 | 4671 | 3963 | 100% | 02-May-23 08:00 AM | 14-Jun-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 30.0d | 1.0d | 0
PMC-D0001 | Indirect Project Mnagement C-D Cost Bar | 8634 | 4671 | 0 | 4671 | 3963 | 100% | 02-May-23 08:00 AM | 14-Jun-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 30.0d | 1.0d | 0 | 100%
412 | Quantity Surveyor | 3460 | 0 | 0 | 0 | 3460 | 100% | 02-May-23 08:00 AM | 14-Jun-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 30.0d | 1.0d | 0
PMC-D0004 | QS C-D Cost Bar | 3460 | 0 | 0 | 0 | 3460 | 100% | 02-May-23 08:00 AM | 14-Jun-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 30.0d | 1.0d | 0 | 100%
413 | P6 Planner | 2549 | 0 | 0 | 0 | 2549 | 100% | 02-May-23 08:00 AM | 14-Jun-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 30.0d | 1.0d | 0
PMC-D0002 | Project Planner C-D Cost Bar | 2549 | 0 | 0 | 0 | 2549 | 100% | 02-May-23 08:00 AM | 14-Jun-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 30.0d | 1.0d | 0 | 100%
3 | Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-23 09:00 AM | 19-May-23 08:00 AM | 01-Mar-23 09:00 AM | 19-May-23 08:00 AM | 52.9d | 52.9d | 0
A5010 | Manufacture of Long Lead items | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
434 | Cable & Materials Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-23 09:00 AM | 19-May-23 08:00 AM | 01-Mar-23 09:00 AM | 19-May-23 08:00 AM | 52.9d | 52.9d | 0
PRC1190 | 11&33kV Cable & Materials manufacture | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
PRC1170 | 132kV Cable Accessories & Jointing manufacture | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 01-Mar-23 09:00 AM | 02-Mar-23 09:00 AM | 1.0d | 1.0d | 0 | 100%
436 | Relay Panels Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0
PRC1000 | Relay panels manufacture | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
2 | Design / Surveys / OP&C Gate C-D | 14475 | 3581 | 0 | 3581 | 10894 | 100% | 02-May-23 08:00 AM | 15-Jun-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 12:00 PM | 30.0d | 12.5d | 0
PMC-D1960 | Design C-D Cost Bar | 14475 | 3581 | 0 | 3581 | 10894 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A4700 | Technical Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A4730 | As-Build Drawings review | 0 | 0 | 0 | 0 | 0 | 100% | 15-Jun-23 08:00 AM | 15-Jun-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 0.0d | 1.0d | 0 | 100%
A4820 | Design Support to Construction team (TQs and Troubleshooting) | 0 | 0 | 0 | 0 | 0 | 100% | 22-May-23 08:00 AM | 22-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 04:00 PM | 0.0d | 1.0d | 0 | 100%
A4830 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 12:00 PM | 19-May-23 12:00 PM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4840 | Update post construction drawing (Internal Design) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4850 | As built drawing received from Supplier | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4860 | Technical Design Complete | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4870 | As built drawing received from Site | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4880 | As built drawing received from Commissioning team | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4960 | Pre-Construction Information - PCI Documentation ((CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4970 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A5050 | Request protection settings | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 12:00 PM | 19-May-23 12:00 PM | 02-May-23 08:00 AM | 19-May-23 12:00 PM | 0.0d | 12.5d | 0 | 100%
A5060 | Protection Settings | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 12:00 PM | 19-May-23 12:00 PM | 02-May-23 08:00 AM | 19-May-23 12:00 PM | 0.0d | 12.5d | 0 | 100%
4 | Construction | 267817 | 26428 | 0 | 26428 | 241390 | 100% | 19-May-23 08:00 AM | 01-Jun-23 09:00 AM | 02-May-23 08:00 AM | 29-Sep-23 08:00 AM | 8.1d | 105.0d | 25000
A4490 | Site Engineer | 27357 | 1428 | 0 | 1428 | 25929 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5150 | Panel Refub material | 100000 | 0 | 0 | 0 | 100000 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5160 | DLO Fitters for fixing panel | 20000 | 0 | 0 | 0 | 20000 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5170 | Steel work support and cleats | 10000 | 0 | 0 | 0 | 10000 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5180 | Fire proofing and duct sealing | 5000 | 0 | 0 | 0 | 5000 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5190 | Scaffolding | 10000 | 0 | 0 | 0 | 10000 | 100% | 01-Jun-23 09:00 AM | 01-Jun-23 09:00 AM | 02-May-23 09:00 AM | 02-May-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
A5200 | Authorised Person | 2611 | 0 | 0 | 0 | 2611 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5210 | HSE Advisor | 2315 | 0 | 0 | 0 | 2315 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5220 | Commissioning Engineer | 6194 | 0 | 0 | 0 | 6194 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5230 | SAP | 6246 | 0 | 0 | 0 | 6246 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5240 | Developing Safe System of work | 20000 | 25000 | 0 | 25000 | (5,000) | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 25-Sep-23 08:00 AM | 29-Sep-23 08:00 AM | 0.0d | 4.0d | 25000 | 100%
A5250 | New Earth Gear for new CB Truck | 5000 | 0 | 0 | 0 | 5000 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5260 | Site Est - Fixed Charge | 15350 | 0 | 0 | 0 | 15350 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5270 | Site Est - Variable Charge upto 750,000 | 13150 | 0 | 0 | 0 | 13150 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5280 | 11kV 300 Triplex to 300 Triplex St Jnt | 2895 | 0 | 0 | 0 | 2895 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5290 | ELR 10kV 300 Cu Triplx CWAY 1/2 | 21700 | 0 | 0 | 0 | 21700 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
441 | Site Pre Start (Enabling Works) | 0 | 0 | 0 | 0 | 0 | 0% | 19-May-23 08:00 AM | 25-May-23 04:00 PM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 5.0d | 12.0d | 0
A1980 | Prepare Construction Phase Plan | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A1990 | Prepare Issue F10 | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A2000 | Setup Health & safety File | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
PS4480 | Site Access | 0 | 0 | 0 | 0 | 0 | 100% | 25-May-23 04:00 PM | 25-May-23 04:00 PM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
442 | Mobilisation | 0 | 0 | 0 | 0 | 0 | 0% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0
T2650 | Mobilisation of Principle Contractor | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
443 | Outages | 0 | 0 | 0 | 0 | 0 | 0% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0
OUT1920 | Outage 1 | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
448 | Cable Install | 0 | 0 | 0 | 0 | 0 | 0% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0
CONS-5720 | Cable Installation Planned Start | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CONS-14150 | Cable Installation Planned Completion | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CONS-14160 | Cable Installation Contract Completion Date | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
T13940 | Install 11kV Cabling | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
T13950 | Joint & Terminate Cables | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
T13960 | Cable Sheath Tests | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
T13970 | 11kV Pressure Tests | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A5300 | Install/Modify Relay panel | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
449 | Test & Commissioning | 0 | 0 | 0 | 0 | 0 | 0% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0
TC4890 | SAP Updated | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
TC4900 | Netmap Updated | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
CLO130 | Demobilise from site | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A2940 | Hot Commissioning of Substation | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A2950 | Energisation | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A3060 | Protection Settings uploaded | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4450 | Substation Under Rules | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
6 | Closure | 0 | 0 | 0 | 0 | 0 | 0% | 02-May-23 08:00 AM | 20-Sep-24 04:00 PM | 02-May-23 08:00 AM |  | 350.0d | 12.0d | 0
CLO3100 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
CLO120 | Review and Approve H&S File | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
CLO14150 | Financial Closure | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-23 09:00 AM | 01-Jun-23 09:00 AM | 02-May-23 09:00 AM | 02-May-23 09:00 AM | 0.0d | 0.0d | 0 | 100%
CLO15940 | Familiarisation Training | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-23 08:00 AM | 19-May-23 08:00 AM | 02-May-23 08:00 AM | 19-May-23 08:00 AM | 0.0d | 12.0d | 0 | 100%
A4460 | Deadline for submission of defined costs (65 days from contract completion) | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 02-May-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 03-Jun-24 08:00 AM | 20-Sep-24 04:00 PM |  |  | 79.0d | 0.0d | 0
Gate1070 | Prepare Gate D Paper | 0 | 0 | 0 | 0 | 0 | 0% | 03-Jun-24 08:00 AM | 20-Sep-24 04:00 PM |  |  | 79.0d | 0.0d | 0 | 0%
Gate1080 | Submit Gate D Paper to RPrB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 0% | 20-Sep-24 04:00 PM | 20-Sep-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%