## Sheet1
Activity ID* | Activity Name* | BL Project Total Cost | Actual Total Cost | Remaining Total Cost | At Completion Total Cost | Variance BL Project - Total Cost | Performance % Complete | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Duration | Actual Duration | Planned Total Cost | Activity % Complete
M-E.MCN.109987 | EJHo Boscombe Road LU5 4LT | 303598 | 39316 | 264282 | 303598 | 264282 | 12.95% | 02-Jan-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 303598
1 | Project Summary | 303598 | 39316 | 264282 | 303598 | 264282 | 12.95% | 02-Jan-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 303598
6 | Project Governance Milestones | 0 | 0 | 0 | 0 | 0 | 12.95% | 02-Jan-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0
Gate1010 | Gate B Award | 0 | 0 | 0 | 0 | 0 | 100% | 02-Jan-26 08:00 AM | 02-Jan-26 08:00 AM | 02-Apr-26 08:00 AM | 02-Apr-26 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1020 | Gate C Award | 0 | 0 | 0 | 0 | 0 | 0% | 26-Jun-26 04:00 PM | 26-Jun-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
Gate1030 | Gate D Award | 0 | 0 | 0 | 0 | 0 | 0% | 11-Jun-27 04:00 PM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0 | 0%
9 | Construction Delivery Milestones | 0 | 0 | 0 | 0 | 0 | 21.66% | 02-Jan-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0
AL1000 | Project Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 02-Jan-26 08:00 AM | 02-Jan-26 08:00 AM | 01-Feb-26 08:00 AM | 01-Feb-26 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL2010 | Award WPO Contract | 0 | 0 | 0 | 0 | 0 | 0% | 17-Jul-26 04:00 PM | 17-Jul-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1130 | Customer (MC or APP) Energisation available | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1140 | Site Demobilisation Complete | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1070 | Practical Completion | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1010 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 0% | 27-Mar-26 04:00 PM | 27-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1000 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 07-Jan-26 04:00 PM | 07-Jan-26 04:00 PM | 06-Feb-26 04:00 PM | 06-Feb-26 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1040 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 0% | 19-Jun-26 04:00 PM | 19-Jun-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1020 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 0% | 15-Apr-26 04:00 PM | 15-Apr-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A5160 | Start on Site - Main Works | 0 | 0 | 0 | 0 | 0 | 0% | 28-Aug-26 04:00 PM | 28-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A5170 | Start on Site - Work Package | 0 | 0 | 0 | 0 | 0 | 0% | 28-Aug-26 04:00 PM | 28-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
10 | Alliance / Contractor Engagement Milestones | 303598 | 39316 | 264282 | 303598 | 264282 | 12.95% | 02-Jan-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 303598
PMB-C2120 | Indirect Project Manager Cost Bar | 32528 | 4212 | 28316 | 32528 | 28316 | 12.95% | 02-Jan-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 360.0d |  | 32528 | 13%
A4480 | Direct Costs 2025 | 0 | 0 | 0 | 0 | 0 | 0% | 29-Jun-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 98.0d |  | 0 | 0%
A5250 | Direct Costs Contractor | 271070 | 0 | 271070 | 271070 | 271070 | 0% | 29-Jun-26 08:00 AM | 09-Jul-26 04:00 PM |  |  | 9.0d |  | 271070 | 0%
A5260 | Direct Costs Labour | 0 | 0 | 0 | 0 | 0 | 21.25% | 02-Jan-26 08:00 AM | 18-Nov-26 04:00 PM |  |  | 224.0d |  | 0 | 21%
A5270 | Direct Costs Material | 0 | 0 | 0 | 0 | 0 | 0% | 29-Jun-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 129.0d |  | 0 | 0%
8 | Asset Registration/Update Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 28-Sep-26 04:00 PM | 04-Nov-26 04:00 PM |  |  | 0.0d |  | 0
ASS1030 | Asset Data - Updated (SAP -Switchgear) | 0 | 0 | 0 | 0 | 0 | 0% | 04-Nov-26 04:00 PM | 04-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1040 | Asset Data - Updated (Netmap - Cable records) | 0 | 0 | 0 | 0 | 0 | 0% | 04-Nov-26 04:00 PM | 04-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1000 | Asset Data - Registration (Netmap) | 0 | 0 | 0 | 0 | 0 | 0% | 28-Sep-26 04:00 PM | 28-Sep-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1020 | Asset Data - Registration (SAP) - Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 28-Sep-26 04:00 PM | 28-Sep-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
7 | Project Closeout Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 26-Nov-26 04:00 PM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0
CLO1000 | Project Completion | 0 | 0 | 0 | 0 | 0 | 0% | 11-Jun-27 04:00 PM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1020 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 27-Nov-26 04:00 PM | 27-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1030 | Financial Close | 0 | 0 | 0 | 0 | 0 | 0% | 13-May-27 04:00 PM | 13-May-27 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1050 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 26-Nov-26 04:00 PM | 26-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1010 | Completion Certificate Signed off | 0 | 0 | 0 | 0 | 0 | 0% | 10-Dec-26 04:00 PM | 10-Dec-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1060 | Completion of the Health and Safety File | 0 | 0 | 0 | 0 | 0 | 0% | 26-Nov-26 04:00 PM | 26-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
1 | Project Specific Milestones - Inc. Contract Data | 0 | 0 | 0 | 0 | 0 | 76.83% | 07-Jan-26 04:00 PM | 30-Mar-26 04:00 PM |  |  | 0.0d |  | 0
ProjKM1000 | Consent Conveyacing Pack Submission | 0 | 0 | 0 | 0 | 0 | 100% | 07-Jan-26 04:00 PM | 07-Jan-26 04:00 PM | 07-Apr-26 04:00 PM | 07-Apr-26 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM1020 | Project Consents Executed | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 04:00 PM | 30-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
TASK DESIGN DELIVERY MILESTONES | TASK DESIGN DELIVERY MILESTONES (DO NOT DELETE or CHANGE ACTIVITY ID) | 0 | 0 | 0 | 0 | 0 | 19.5% | 07-Jan-26 08:00 AM | 26-Nov-26 04:00 PM |  |  | 0.0d |  | 0
DES-DM1 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 07-Jan-26 08:00 AM | 07-Jan-26 04:00 PM | 08-Mar-26 08:00 AM | 12-Jan-26 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM2 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 08-Jan-26 08:00 AM | 08-Jan-26 04:00 PM | 07-Feb-26 08:00 AM | 13-Jan-26 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM4 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 0% | 27-Mar-26 08:00 AM | 27-Mar-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM5 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 0% | 15-Apr-26 08:00 AM | 15-Apr-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM6 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 31-Mar-26 08:00 AM | 31-Mar-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM7 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building / Route / Earthing / Component) | 0 | 0 | 0 | 0 | 0 | 0% | 16-Apr-26 08:00 AM | 16-Apr-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM9 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 0% | 19-Jun-26 08:00 AM | 19-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM10-2 | Asset Data - Registration (SAP) - Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 12-Aug-26 08:00 AM | 12-Aug-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM11 | Pre-Construction Information - PCI Documentation (CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 0% | 24-Jun-26 08:00 AM | 24-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM12 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 0% | 25-Jun-26 08:00 AM | 25-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM13 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 0% | 26-Jun-26 08:00 AM | 26-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM14 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 26-Nov-26 08:00 AM | 26-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
3 | Gate B-C | 0 | 0 | 0 | 0 | 0 | 35.98% | 02-Jan-26 08:00 AM | 10-Jul-26 04:00 PM |  |  | 0.0d |  | 0
2 | Design / Surveys / OP&C | 0 | 0 | 0 | 0 | 0 | 39.77% | 02-Jan-26 08:00 AM | 22-Jun-26 04:00 PM |  |  | 0.0d |  | 0
9 | Concept Design | 0 | 0 | 0 | 0 | 0 | 78.16% | 02-Jan-26 08:00 AM | 30-Mar-26 04:00 PM |  |  | 0.0d |  | 0
FEED-A-B-M-0006 | Concept Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 02-Jan-26 08:00 AM | 07-Jan-26 04:00 PM | 01-Feb-26 08:00 AM | 10-Jan-26 04:00 PM | 4.0d | 0.0d | 0 | 100%
A4590 | Layouts ready for estimating | 0 | 0 | 0 | 0 | 0 | 70.37% | 20-Feb-26 08:00 AM | 19-Mar-26 04:00 PM |  |  | 20.0d |  | 0 | 70%
A4600 | Concept Design Review | 0 | 0 | 0 | 0 | 0 | 0% | 20-Mar-26 08:00 AM | 26-Mar-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4740 | Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 09-Jan-26 08:00 AM | 19-Feb-26 04:00 PM | 08-Feb-26 08:00 AM |  | 30.0d |  | 0 | 100%
A4750 | Publish Concept Design Documents & Drawings | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 08:00 AM | 30-Mar-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A4760 | Prepare Design cost estimate for Developed & Technical stage (CAP15/16) | 0 | 0 | 0 | 0 | 0 | 0% | 27-Mar-26 08:00 AM | 27-Mar-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
3 | Detailed Design | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 08:00 AM | 22-Jun-26 04:00 PM |  |  | 0.0d |  | 0
A2790 | Update PEP, Formalise AIP & Appendix B | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 08:00 AM | 07-Apr-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4620 | Developed Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 0% | 08-Apr-26 08:00 AM | 14-Apr-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4660 | Compile Documents Layout for Construction - Civils/Electrical/Route/M&E) | 0 | 0 | 0 | 0 | 0 | 0% | 29-May-26 08:00 AM | 11-Jun-26 04:00 PM |  |  | 10.0d |  | 0 | 0%
A4680 | Developed Design Review | 0 | 0 | 0 | 0 | 0 | 0% | 12-Jun-26 08:00 AM | 18-Jun-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4790 | Developed Design - UKPN Internal | 0 | 0 | 0 | 0 | 0 | 0% | 15-Apr-26 08:00 AM | 28-May-26 04:00 PM |  |  | 30.0d |  | 0 | 0%
A4800 | Publish Developed Design Documents & Drawings/Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 0% | 22-Jun-26 08:00 AM | 22-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
5 | Gate C Governance | 0 | 0 | 0 | 0 | 0 | 0% | 22-Jun-26 08:00 AM | 10-Jul-26 04:00 PM |  |  | 0.0d |  | 0
Gate1031 | Prepare Gate C Paper | 0 | 0 | 0 | 0 | 0 | 0% | 22-Jun-26 08:00 AM | 26-Jun-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
Q3056 | Prepare WPO | 0 | 0 | 0 | 0 | 0 | 0% | 29-Jun-26 08:00 AM | 10-Jul-26 04:00 PM |  |  | 10.0d |  | 0 | 0%
4 | Gate C-D | 0 | 0 | 0 | 0 | 0 | 12.95% | 02-Jan-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0
3 | Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 08:00 AM | 11-Aug-26 04:00 PM |  |  | 0.0d |  | 0
432 | Switchgear Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 08:00 AM | 11-Aug-26 04:00 PM |  |  | 0.0d |  | 0
PRC2030 | Switchgear Manufacture | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 08:00 AM | 10-Aug-26 04:00 PM |  |  | 92.0d |  | 0 | 0%
A5080 | Switchgear Delivery | 0 | 0 | 0 | 0 | 0 | 0% | 11-Aug-26 08:00 AM | 11-Aug-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
434 | Cable & Materials Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 31-Mar-26 08:00 AM | 21-May-26 04:00 PM |  |  | 0.0d |  | 0
PRC1190 | 11,33 & 132kV Cable, Cable Accessories & Jointing manufacture | 0 | 0 | 0 | 0 | 0 | 0% | 31-Mar-26 08:00 AM | 14-May-26 04:00 PM |  |  | 30.0d |  | 0 | 0%
PRC1170 | 11,33 & 132kV Cable, Cable Accessories & Jointing delivery | 0 | 0 | 0 | 0 | 0 | 0% | 15-May-26 08:00 AM | 21-May-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
2 | Design / Surveys / OP&C Gate C-D | 0 | 0 | 0 | 0 | 0 | 0% | 23-Jun-26 08:00 AM | 26-Nov-26 04:00 PM |  |  | 0.0d |  | 0
A4700 | Technical Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 0% | 23-Jun-26 08:00 AM | 23-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A4730 | As-Build Drawings review | 0 | 0 | 0 | 0 | 0 | 0% | 20-Nov-26 08:00 AM | 26-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4830 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 0% | 25-Jun-26 04:00 PM | 25-Jun-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A4860 | Technical Design Complete | 0 | 0 | 0 | 0 | 0 | 0% | 03-Aug-26 04:00 PM | 03-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A4880 | As built drawing received from Commissioning team | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 08:00 AM | 19-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4960 | Pre-Construction Information - PCI Documentation ((CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 0% | 24-Jun-26 04:00 PM | 24-Jun-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A4970 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 0% | 03-Aug-26 04:00 PM | 03-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
4 | Construction | 0 | 0 | 0 | 0 | 0 | 21.66% | 02-Jan-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0
441 | Contract Data Part 1 | 0 | 0 | 0 | 0 | 0 | 21.66% | 02-Jan-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0
PS4480 | Site Access | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jul-26 04:00 PM | 20-Jul-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A5280 | Contractor Planned Completion | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A5290 | Starting date | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jul-26 08:00 AM | 20-Jul-26 08:00 AM |  |  | 0.0d |  | 0 | 0%
A5300 | Key date | 0 | 0 | 0 | 0 | 0 | 100% | 02-Jan-26 08:00 AM | 02-Jan-26 04:00 PM | 02-Apr-26 08:00 AM | 05-Jan-26 04:00 PM | 1.0d | 0.0d | 0 | 100%
A5310 | UKPN Completion date | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
442 | Mobilisation | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jul-26 08:00 AM | 28-Aug-26 04:00 PM |  |  | 0.0d |  | 0
T2650 | Offsite Mobilisation of Principle Contractor | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jul-26 08:00 AM | 14-Aug-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
A5240 | Onsite Mobilisation of Principle Contractor | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 28-Aug-26 04:00 PM |  |  | 10.0d |  | 0 | 0%
446 | Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 01-Sep-26 08:00 AM | 03-Nov-26 04:00 PM |  |  | 0.0d |  | 0
OUT1930 | Outage | 0 | 0 | 0 | 0 | 0 | 0% | 03-Nov-26 08:00 AM | 03-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
CONS-1830 | Install 11kV Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 01-Sep-26 08:00 AM | 28-Sep-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
CONS-3840 | Install Multicores & Terminate | 0 | 0 | 0 | 0 | 0 | 0% | 29-Sep-26 08:00 AM | 05-Oct-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
CONS-13850 | Cold Commission 11/6.6kV Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 06-Oct-26 08:00 AM | 02-Nov-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
A3080 | Hot commissioning of Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 03-Nov-26 08:00 AM | 03-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
448 | Cable Install | 0 | 0 | 0 | 0 | 0 | 0% | 01-Sep-26 08:00 AM | 13-Oct-26 04:00 PM |  |  | 0.0d |  | 0
T13940 | Install 11kV Cabling | 0 | 0 | 0 | 0 | 0 | 0% | 01-Sep-26 08:00 AM | 28-Sep-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
T13950 | Cable Sheath Tests | 0 | 0 | 0 | 0 | 0 | 0% | 29-Sep-26 08:00 AM | 05-Oct-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
T13960 | Joint & Terminate Cables | 0 | 0 | 0 | 0 | 0 | 0% | 06-Oct-26 08:00 AM | 12-Oct-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
T13970 | 11kV Pressure Tests | 0 | 0 | 0 | 0 | 0 | 0% | 13-Oct-26 08:00 AM | 13-Oct-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
449 | Test & Commissioning | 0 | 0 | 0 | 0 | 0 | 0% | 03-Nov-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0
TC4890 | SAP Updated | 0 | 0 | 0 | 0 | 0 | 0% | 04-Nov-26 08:00 AM | 04-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
TC4900 | Netmap Updated | 0 | 0 | 0 | 0 | 0 | 0% | 04-Nov-26 08:00 AM | 04-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
CLO130 | Demobilise from site | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A2940 | Hot Commissioning of Substation | 0 | 0 | 0 | 0 | 0 | 0% | 03-Nov-26 08:00 AM | 03-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A2950 | Energisation | 0 | 0 | 0 | 0 | 0 | 0% | 05-Nov-26 08:00 AM | 11-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A3060 | Protection Settings uploaded | 0 | 0 | 0 | 0 | 0 | 0% | 03-Nov-26 04:00 PM | 03-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A4450 | Substation Under Rules | 0 | 0 | 0 | 0 | 0 | 0% | 04-Nov-26 08:00 AM | 04-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
6 | Closure | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0
CLO3100 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 27-Nov-26 08:00 AM | 27-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
CLO120 | Review and Approve H&S File | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 08:00 AM | 26-Nov-26 04:00 PM |  |  | 10.0d |  | 0 | 0%
CLO14150 | Financial Closure | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 08:00 AM | 13-May-27 04:00 PM |  |  | 120.0d |  | 0 | 0%
CLO15940 | Familiarisation Training | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 08:00 AM | 25-Nov-26 04:00 PM |  |  | 10.0d |  | 0 | 0%
A4460 | Deadline for submission of defined costs (65 days from contract completion) | 0 | 0 | 0 | 0 | 0 | 0% | 10-Dec-26 04:00 PM | 10-Dec-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-27 08:00 AM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0
Gate1080 | Prepare Gate D Paper | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-27 08:00 AM | 11-Jun-27 04:00 PM |  |  | 20.0d |  | 0 | 0%
Gate1090 | Submit Gate D Paper to RPrB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 0% | 11-Jun-27 04:00 PM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 0 | 0%