## Sheet1
Activity ID* | Activity Name* | BL Project Total Cost | Actual Total Cost | Remaining Total Cost | At Completion Total Cost | Variance BL Project - Total Cost | Performance % Complete | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Duration | Actual Duration | Planned Total Cost | Activity % Complete
M-E.MCN.109408 | EZW (ANM) Hulcote Farm, Salford Road, MK17 8BS | 345666 | 300600 | 45066 | 345666 | 45066 | 44.31% | 03-Feb-25 08:00 AM | 28-Jul-27 04:00 PM | 04-May-25 08:00 AM |  | 621.0d |  | 345666
1 | Project Summary | 345666 | 300600 | 45066 | 345666 | 45066 | 48.37% | 03-Feb-25 08:00 AM | 13-May-27 04:00 PM | 05-Mar-25 08:00 AM |  | 568.0d |  | 345666
6 | Project Governance Milestones | 0 | 0 | 0 | 0 | 0 | 57.2% | 03-Feb-25 08:00 AM | 05-Jan-27 04:00 PM | 05-Mar-25 08:00 AM |  | 479.0d |  | 0
Gate1000 | Gate A Award | 3025 | 2655 | 370 | 3025 | 370 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 04-May-25 08:00 AM | 04-May-25 08:00 AM | 0.0d | 0.0d | 3025 | 100%
Gate1010 | Gate B Award | 2893 | 2414 | 479 | 2893 | 479 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 08:00 AM | 30-Sep-25 08:00 AM | 30-Sep-25 08:00 AM | 0.0d | 0.0d | 2893 | 100%
Gate1020 | Gate C Award | 0 | 0 | 0 | 0 | 0 | 100% | 23-Jan-26 04:00 PM | 23-Jan-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
Gate1030 | Gate D Award | 1423 | 1184 | 239 | 1423 | 239 | 0% | 05-Jan-27 04:00 PM | 05-Jan-27 04:00 PM |  |  | 0.0d |  | 1423 | 0%
Gate1040 | Hong Kong Board Review | 0 | 0 | 0 | 0 | 0 | 100% | 27-Feb-26 04:00 PM | 27-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
Gate1050 | Executive Management Team Review | 723 | 615 | 108 | 723 | 108 | 100% | 13-Feb-26 04:00 PM | 13-Feb-26 04:00 PM |  |  | 0.0d |  | 723 | 100%
9 | Construction Delivery Milestones | 0 | 0 | 0 | 0 | 0 | 59.13% | 10-Mar-25 04:00 PM | 19-Nov-26 04:00 PM | 09-Apr-25 04:00 PM |  | 427.0d |  | 0
DEL1080 | Hot Commissioning Commencement | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 20-Oct-26 08:00 AM |  |  | 0.0d |  | 0 | 0%
DEL1130 | Customer (MC or APP) Energisation available | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1090 | Li Intervention | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1060 | Hi Intervention | 3023 | 2749 | 274 | 3023 | 274 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 3023 | 100%
DEL1140 | Site Demobilisation Complete | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1100 | Switchgear Energised | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1110 | Tx1 Energised | 3216 | 2892 | 324 | 3216 | 324 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 3216 | 0%
DEL1120 | Cct 1 Energised | 801 | 725 | 76 | 801 | 76 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 801 | 0%
DEL1070 | Practical Completion | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1010 | Concept Design Signed off - CAP 02-017 | 1923 | 1749 | 174 | 1923 | 174 | 100% | 25-Jun-25 04:00 PM | 25-Jun-25 04:00 PM | 25-Jul-25 04:00 PM | 25-Jul-25 04:00 PM | 0.0d | 0.0d | 1923 | 100%
DEL1000 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 755 | 635 | 120 | 755 | 120 | 100% | 10-Mar-25 04:00 PM | 10-Mar-25 04:00 PM | 09-Apr-25 04:00 PM | 09-Apr-25 04:00 PM | 0.0d | 0.0d | 755 | 100%
DEL1030 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building/Route/Earthing/Component) | 0 | 0 | 0 | 0 | 0 | 100% | 11-Nov-25 04:00 PM | 11-Nov-25 04:00 PM | 09-Feb-26 04:00 PM | 09-Feb-26 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1040 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 12-Dec-25 04:00 PM | 12-Dec-25 04:00 PM | 11-Jan-26 04:00 PM | 11-Jan-26 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1020 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 01-Sep-25 04:00 PM | 01-Sep-25 04:00 PM | 30-Nov-25 04:00 PM | 30-Nov-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1150 | Customer Required By energisation date | 0 | 0 | 0 | 0 | 0 | 0% | 19-Nov-26 04:00 PM | 19-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1050 | Start on Site - Enabling Works | 0 | 0 | 0 | 0 | 0 | 100% | 29-Aug-25 08:00 AM | 29-Aug-25 08:00 AM | 27-Nov-25 08:00 AM | 27-Nov-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
A5160 | Start on Site - Main Works | 2693 | 2275 | 418 | 2693 | 418 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 2693 | 100%
A5170 | Start on Site - Work Package | 2708 | 2247 | 461 | 2708 | 461 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 2708 | 100%
10 | Alliance / Contractor Engagement Milestones | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 06-Feb-26 04:00 PM | 04-May-25 08:00 AM |  | 254.0d |  | 0
AL1000 | Project Kick Off Meeting | 921 | 827 | 94 | 921 | 94 | 100% | 14-Feb-25 04:00 PM | 14-Feb-25 04:00 PM | 16-Mar-25 04:00 PM | 16-Mar-25 04:00 PM | 0.0d | 0.0d | 921 | 100%
AL1090 | Alliance Delivery Proposal Received (ADP) | 0 | 0 | 0 | 0 | 0 | 100% | 22-Dec-25 08:00 AM | 22-Dec-25 08:00 AM | 22-Mar-26 08:00 AM | 22-Mar-26 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL2000 | ADP Approved by AMT | 0 | 0 | 0 | 0 | 0 | 100% | 19-Jan-26 04:00 PM | 19-Jan-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
AL2010 | Award WPO Contract | 0 | 0 | 0 | 0 | 0 | 100% | 06-Feb-26 04:00 PM | 06-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
AL1040 | Acceptance of AIP by Delivery Member | 1893 | 1719 | 174 | 1893 | 174 | 100% | 21-Jul-25 04:00 PM | 21-Jul-25 04:00 PM | 19-Sep-25 04:00 PM | 19-Sep-25 04:00 PM | 0.0d | 0.0d | 1893 | 100%
AL1050 | Award PSC Contract - Developed Design | 0 | 0 | 0 | 0 | 0 | 100% | 20-Aug-25 04:00 PM | 20-Aug-25 04:00 PM | 19-Sep-25 04:00 PM | 19-Sep-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
AL1010 | Award PSC Contract - Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 21-Feb-25 04:00 PM | 21-Feb-25 04:00 PM | 23-Mar-25 04:00 PM | 23-Mar-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
A5180 | Early Engagement PSC | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 05-Mar-25 08:00 AM | 05-Mar-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
A5190 | Pre-design PSC | 2102 | 1809 | 293 | 2102 | 293 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 05-Mar-25 08:00 AM | 05-Mar-25 08:00 AM | 0.0d | 0.0d | 2102 | 100%
A5200 | Concept design PSC | 1304 | 1150 | 154 | 1304 | 154 | 100% | 10-Mar-25 04:00 PM | 10-Mar-25 04:00 PM | 09-Apr-25 04:00 PM | 09-Apr-25 04:00 PM | 0.0d | 0.0d | 1304 | 100%
A5210 | Developed design PSC | 0 | 0 | 0 | 0 | 0 | 100% | 01-Sep-25 04:00 PM | 01-Sep-25 04:00 PM | 30-Nov-25 04:00 PM | 30-Nov-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
A5220 | Design framework consultant PSC | 3007 | 2511 | 496 | 3007 | 496 | 100% | 10-Mar-25 04:00 PM | 10-Mar-25 04:00 PM | 08-Jun-25 04:00 PM | 08-Jun-25 04:00 PM | 0.0d | 0.0d | 3007 | 100%
A5230 | Secondary contractor call off form | 1747 | 1595 | 152 | 1747 | 152 | 100% | 23-Jan-26 04:00 PM | 23-Jan-26 04:00 PM |  |  | 0.0d |  | 1747 | 100%
8 | Asset Registration/Update Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 20-May-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 108.0d |  | 0
ASS1030 | Asset Data - Updated (SAP -Switchgear) | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1040 | Asset Data - Updated (Netmap - Cable records) | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1010 | Asset Data - Registration (SAP) - Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 04:00 PM | 17-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1000 | Asset Data - Registration (Netmap) | 1155 | 1046 | 109 | 1155 | 109 | 0% | 20-May-26 04:00 PM | 20-May-26 04:00 PM |  |  | 0.0d |  | 1155 | 0%
ASS1020 | Asset Data - Registration (SAP) - Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 04:00 PM | 17-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1050 | Asset Data - Updated (SAP - Transformer) | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
7 | Project Closeout Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 02-Nov-26 04:00 PM | 13-May-27 04:00 PM |  |  | 128.0d |  | 0
CLO1000 | Project Completion | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jan-27 04:00 PM | 05-Jan-27 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1020 | Project Handover - to Network Ops | 2073 | 1901 | 172 | 2073 | 172 | 0% | 05-Jan-27 04:00 PM | 05-Jan-27 04:00 PM |  |  | 0.0d |  | 2073 | 0%
CLO1030 | Financial Close | 0 | 0 | 0 | 0 | 0 | 0% | 13-May-27 04:00 PM | 13-May-27 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1050 | As-Built Records Accepted | 2607 | 2349 | 258 | 2607 | 258 | 0% | 04-Jan-27 04:00 PM | 04-Jan-27 04:00 PM |  |  | 0.0d |  | 2607 | 0%
CLO1010 | Completion Certificate Signed off | 1125 | 1021 | 104 | 1125 | 104 | 0% | 11-Dec-26 04:00 PM | 11-Dec-26 04:00 PM |  |  | 0.0d |  | 1125 | 0%
CLO1060 | Completion of the Health and Safety File | 0 | 0 | 0 | 0 | 0 | 0% | 02-Nov-26 04:00 PM | 02-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
1 | Project Specific Milestones - Inc. Contract Data | 0 | 0 | 0 | 0 | 0 | 100% | 04-Apr-25 04:00 PM | 14-Aug-25 04:00 PM | 04-May-25 04:00 PM | 19-Aug-25 04:00 PM | 90.0d | 107.0d | 0
ProjKM1000 | Consent Conveyacing Pack Submission | 1435 | 1180 | 255 | 1435 | 255 | 100% | 04-Apr-25 04:00 PM | 04-Apr-25 04:00 PM | 03-Jul-25 04:00 PM | 03-Jul-25 04:00 PM | 0.0d | 0.0d | 1435 | 100%
ProjKM1020 | Project Consents Executed | 0 | 0 | 0 | 0 | 0 | 100% | 14-Aug-25 04:00 PM | 14-Aug-25 04:00 PM | 13-Sep-25 04:00 PM | 13-Sep-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
TASK DESIGN DELIVERY MILESTONES | TASK DESIGN DELIVERY MILESTONES (DO NOT DELETE or CHANGE ACTIVITY ID) | 0 | 0 | 0 | 0 | 0 | 55.04% | 10-Mar-25 08:00 AM | 04-Jan-27 04:00 PM | 08-Jun-25 08:00 AM |  | 453.0d |  | 0
DES-DM1 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 3351 | 2993 | 358 | 3351 | 358 | 100% | 10-Mar-25 08:00 AM | 10-Mar-25 04:00 PM | 08-Jun-25 08:00 AM | 15-Mar-25 04:00 PM | 1.0d | 0.0d | 3351 | 100%
DES-DM2 | Concept Survey Information Accepted | 2383 | 2032 | 351 | 2383 | 351 | 100% | 08-May-25 08:00 AM | 08-May-25 04:00 PM | 06-Aug-25 08:00 AM | 13-May-25 04:00 PM | 1.0d | 0.0d | 2383 | 100%
DES-DM3 | Risk & Value Intevention A-B | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-25 08:00 AM | 19-May-25 04:00 PM | 17-Aug-25 08:00 AM | 22-May-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM4 | Concept Design Signed off - CAP 02-017 | 1789 | 1633 | 156 | 1789 | 156 | 100% | 25-Jun-25 08:00 AM | 25-Jun-25 04:00 PM | 24-Aug-25 08:00 AM | 30-Jun-25 04:00 PM | 1.0d | 0.0d | 1789 | 100%
DES-DM5 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 01-Sep-25 08:00 AM | 01-Sep-25 04:00 PM | 01-Oct-25 08:00 AM | 03-Sep-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM6 | Developed Survey Information Accepted | 2012 | 1811 | 201 | 2012 | 201 | 100% | 12-Sep-25 08:00 AM | 12-Sep-25 04:00 PM | 11-Nov-25 08:00 AM | 15-Sep-25 04:00 PM | 1.0d | 0.0d | 2012 | 100%
DES-DM7 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building / Route / Earthing / Component) | 900 | 815 | 85 | 900 | 85 | 100% | 11-Nov-25 08:00 AM | 11-Nov-25 04:00 PM | 09-Feb-26 08:00 AM | 16-Nov-25 04:00 PM | 1.0d | 0.0d | 900 | 100%
DES-DM8 | Risk & Value Intevention B-C | 1191 | 1073 | 118 | 1191 | 118 | 100% | 14-Oct-25 08:00 AM | 14-Oct-25 04:00 PM | 13-Dec-25 08:00 AM | 16-Oct-25 04:00 PM | 1.0d | 0.0d | 1191 | 100%
DES-DM9 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 12-Dec-25 08:00 AM | 12-Dec-25 04:00 PM | 11-Jan-26 08:00 AM | 15-Dec-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM10-1 | Asset Data - Registration (SAP) - Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 17-Aug-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM10-2 | Asset Data - Registration (SAP) - Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 17-Aug-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM11 | Pre-Construction Information - PCI Documentation (CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 10-Feb-26 08:00 AM | 10-Feb-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
DES-DM12 | Design issued for Construction - Handover to Construction Team | 1509 | 1277 | 232 | 1509 | 232 | 100% | 11-Feb-26 08:00 AM | 11-Feb-26 04:00 PM |  |  | 1.0d |  | 1509 | 100%
DES-DM13 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 08:00 AM | 30-Mar-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
DES-DM14 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 04-Jan-27 08:00 AM | 04-Jan-27 04:00 PM |  |  | 1.0d |  | 0 | 0%
2 | Pre Gate B | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 05-Mar-25 08:00 AM | 03-Aug-25 04:00 PM | 125.0d | 151.0d | 0
1 | Project Management | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-May-25 08:00 AM | 05-Aug-25 04:00 PM | 125.0d | 93.0d | 0
1 | Project Manager | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 02-Aug-25 04:00 PM | 125.0d | 120.0d | 0
PMA-B0010 | Indirect Project Management Pre-Gate B Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 03-Aug-25 04:00 PM | 125.0d | 121.0d | 0 | 100%
2 | Quantity Surveyor | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 02-Aug-25 04:00 PM | 125.0d | 120.0d | 0
PMA-B0020 | QS Pre-Gate B Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 05-Mar-25 08:00 AM | 05-Aug-25 04:00 PM | 125.0d | 153.0d | 0 | 100%
3 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 05-Mar-25 08:00 AM | 05-Aug-25 04:00 PM | 125.0d | 153.0d | 0
PMA-B0030 | Project Planner Pre-Gate B Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 03-Aug-25 04:00 PM | 125.0d | 121.0d | 0 | 100%
2 | PM Activities | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 07-Mar-25 04:00 PM | 05-Mar-25 08:00 AM | 12-Mar-25 04:00 PM | 25.0d | 7.0d | 0
Al0010 | Start 1st Draft PEP & AIP | 0 | 0 | 0 | 0 | 0 | 100% | 21-Feb-25 04:00 PM | 21-Feb-25 04:00 PM | 23-Mar-25 04:00 PM | 23-Mar-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
FEED-A-B-M-0003 | Works Information & contract Scope Complete & Agreed (PSC) | 2210 | 1986 | 224 | 2210 | 224 | 100% | 21-Feb-25 04:00 PM | 21-Feb-25 04:00 PM | 22-Apr-25 04:00 PM | 22-Apr-25 04:00 PM | 0.0d | 0.0d | 2210 | 100%
FEED-0040 | Build Gate B-C Detailed Programme containing High level Gate C-D | 1206 | 1002 | 204 | 1206 | 204 | 100% | 03-Mar-25 08:00 AM | 07-Mar-25 04:00 PM | 02-Apr-25 08:00 AM | 12-Mar-25 04:00 PM | 5.0d | 0.0d | 1206 | 100%
A2640 | Work Order Number Raised | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 04-Apr-25 08:00 AM | 04-Apr-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
A2920 | Mobilise | 1178 | 1068 | 110 | 1178 | 110 | 100% | 24-Feb-25 08:00 AM | 28-Feb-25 04:00 PM | 25-Apr-25 08:00 AM | 03-Mar-25 04:00 PM | 5.0d | 0.0d | 1178 | 100%
A3010 | Early Engagement in place for Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 04-May-25 08:00 AM | 04-May-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
3 | OP&C Wayleave/Planng Permission/Consents | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 04-Apr-25 04:00 PM | 09-May-25 08:00 AM | 09-Apr-25 04:00 PM | 20.0d | 0.0d | 0
OP&C2000 | Wayleave Permissions/Planning Consents | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 04-Apr-25 04:00 PM | 09-Apr-25 08:00 AM | 09-Apr-25 04:00 PM | 20.0d | 0.0d | 0 | 100%
5 | Enabling / Preparation Works | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 21-Mar-25 04:00 PM | 08-Jun-25 08:00 AM | 24-Mar-25 04:00 PM | 10.0d | 0.0d | 0
EN-A-B-0010 | Enabling Works | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 21-Mar-25 04:00 PM | 09-May-25 08:00 AM | 26-Mar-25 04:00 PM | 10.0d | 0.0d | 0 | 100%
9 | Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 03-Mar-25 08:00 AM | 27-Jun-25 04:00 PM | 01-Jun-25 08:00 AM | 29-Jun-25 04:00 PM | 81.0d | 28.0d | 0
FEED-A-B-M-0006 | Concept Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 03-Mar-25 08:00 AM | 07-Mar-25 04:00 PM | 02-Apr-25 08:00 AM | 10-Mar-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A4530 | Site Visit | 760 | 688 | 72 | 760 | 72 | 100% | 11-Mar-25 08:00 AM | 11-Mar-25 04:00 PM | 10-May-25 08:00 AM | 16-Mar-25 04:00 PM | 1.0d | 0.0d | 760 | 100%
A4540 | Site information review/ Protection Phylosophy/ Preliminary Layouts | 2330 | 1962 | 368 | 2330 | 368 | 100% | 12-Mar-25 08:00 AM | 24-Mar-25 04:00 PM | 11-Apr-25 08:00 AM | 26-Mar-25 04:00 PM | 9.0d | 0.0d | 2330 | 100%
A4550 | Surveys | 1203 | 1084 | 119 | 1203 | 119 | 100% | 10-Mar-25 08:00 AM | 07-May-25 04:00 PM | 08-Jun-25 08:00 AM | 10-May-25 04:00 PM | 40.0d | 0.0d | 1203 | 100%
A4560 | Concept Survey Information Accepted | 3100 | 2683 | 417 | 3100 | 417 | 100% | 08-May-25 04:00 PM | 08-May-25 04:00 PM | 07-Jul-25 04:00 PM | 07-Jul-25 04:00 PM | 0.0d | 0.0d | 3100 | 100%
A4580 | Risk & Value Intevention | 2971 | 2526 | 445 | 2971 | 445 | 100% | 12-May-25 08:00 AM | 16-May-25 04:00 PM | 10-Aug-25 08:00 AM | 21-May-25 04:00 PM | 5.0d | 0.0d | 2971 | 100%
A4590 | Layouts ready for estimating | 759 | 683 | 76 | 759 | 76 | 100% | 20-May-25 08:00 AM | 17-Jun-25 04:00 PM | 18-Aug-25 08:00 AM | 22-Jun-25 04:00 PM | 20.0d | 0.0d | 759 | 100%
A4600 | Concept Design Review | 0 | 0 | 0 | 0 | 0 | 100% | 18-Jun-25 08:00 AM | 24-Jun-25 04:00 PM | 17-Aug-25 08:00 AM | 27-Jun-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A4740 | Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-25 08:00 AM | 09-May-25 04:00 PM | 07-Aug-25 08:00 AM | 14-May-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4750 | Publish Concept Design Documents & Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 27-Jun-25 08:00 AM | 27-Jun-25 04:00 PM | 27-Jul-25 08:00 AM | 29-Jun-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4760 | Prepare Design cost estimate for Developed & Technical stage (CAP15/16) | 1228 | 1035 | 193 | 1228 | 193 | 100% | 26-Jun-25 08:00 AM | 26-Jun-25 04:00 PM | 24-Sep-25 08:00 AM | 29-Jun-25 04:00 PM | 1.0d | 0.0d | 1228 | 100%
A4910 | Environmental Survey | 0 | 0 | 0 | 0 | 0 | 100% | 24-Mar-25 08:00 AM | 24-Mar-25 04:00 PM | 23-Apr-25 08:00 AM | 29-Mar-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4920 | Risk & Value Intevention A-B | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-25 04:00 PM | 19-May-25 04:00 PM | 18-Jun-25 04:00 PM | 18-Jun-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
7 | Gate B Governance | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jun-25 08:00 AM | 29-Jul-25 08:00 AM | 24-Sep-25 08:00 AM | 01-Aug-25 08:00 AM | 23.0d | 0.0d | 0
FEED-A-B-M-0010 | Issue AIP | 0 | 0 | 0 | 0 | 0 | 100% | 16-Jul-25 04:00 PM | 16-Jul-25 04:00 PM | 15-Aug-25 04:00 PM | 15-Aug-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
Gate2030 | Submit Gate B Paper to RPfB (AST 01 004 > £1m) | 2437 | 2003 | 434 | 2437 | 434 | 100% | 29-Jul-25 08:00 AM | 29-Jul-25 08:00 AM | 27-Sep-25 08:00 AM | 27-Sep-25 08:00 AM | 0.0d | 0.0d | 2437 | 100%
FEED-2350 | Update PEP | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jun-25 08:00 AM | 27-Jun-25 04:00 PM | 26-Jul-25 08:00 AM | 02-Jul-25 04:00 PM | 2.0d | 0.0d | 0 | 100%
Gate2000 | Prepare Gate B Paper | 0 | 0 | 0 | 0 | 0 | 100% | 03-Jul-25 08:00 AM | 16-Jul-25 04:00 PM | 02-Aug-25 08:00 AM | 19-Jul-25 04:00 PM | 10.0d | 0.0d | 0 | 100%
A2720 | Risk & Value workshop | 0 | 0 | 0 | 0 | 0 | 100% | 04-Jul-25 08:00 AM | 04-Jul-25 04:00 PM | 03-Aug-25 08:00 AM | 09-Jul-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2770 | GATE B Presentation at AMT | 0 | 0 | 0 | 0 | 0 | 100% | 23-Jul-25 08:00 AM | 23-Jul-25 04:00 PM | 21-Sep-25 08:00 AM | 25-Jul-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2880 | Network Design Review (NDR) | 0 | 0 | 0 | 0 | 0 | 100% | 17-Jul-25 08:00 AM | 17-Jul-25 04:00 PM | 15-Sep-25 08:00 AM | 20-Jul-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2890 | Risk Advisory Board (RAB) Revirew | 0 | 0 | 0 | 0 | 0 | 100% | 22-Jul-25 08:00 AM | 22-Jul-25 04:00 PM | 20-Sep-25 08:00 AM | 27-Jul-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2900 | Update P6 programme & Cost phasing | 1161 | 974 | 187 | 1161 | 187 | 100% | 26-Jun-25 08:00 AM | 02-Jul-25 04:00 PM | 24-Sep-25 08:00 AM | 04-Jul-25 04:00 PM | 5.0d | 0.0d | 1161 | 100%
A2910 | Gate B CU Design | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jun-25 08:00 AM | 02-Jul-25 04:00 PM | 25-Aug-25 08:00 AM | 05-Jul-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A2795 | ADM Review and acceptance of AIP | 0 | 0 | 0 | 0 | 0 | 100% | 17-Jul-25 08:00 AM | 21-Jul-25 04:00 PM | 16-Aug-25 08:00 AM | 23-Jul-25 04:00 PM | 3.0d | 0.0d | 0 | 100%
A5130 | Gate B QRA Workshop | 932 | 794 | 138 | 932 | 138 | 100% | 23-Jul-25 08:00 AM | 23-Jul-25 04:00 PM | 21-Sep-25 08:00 AM | 28-Jul-25 04:00 PM | 1.0d | 0.0d | 932 | 100%
3 | Gate B-C | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 06-Feb-26 04:00 PM | 30-Sep-25 08:00 AM |  | 129.0d |  | 0
A2780 | B to C Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-25 08:00 AM | 04-Aug-25 04:00 PM | 03-Sep-25 08:00 AM | 07-Aug-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2790 | Update PEP, Formalise AIP & Appendix B, Set Target Budget | 0 | 0 | 0 | 0 | 0 | 100% | 05-Aug-25 08:00 AM | 11-Aug-25 04:00 PM | 03-Nov-25 08:00 AM | 16-Aug-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A2800 | Review of Target Budget and sign off | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-25 08:00 AM | 14-Aug-25 04:00 PM | 11-Oct-25 08:00 AM | 16-Aug-25 04:00 PM | 3.0d | 0.0d | 0 | 100%
A3046 | Mobilise | 0 | 0 | 0 | 0 | 0 | 100% | 21-Aug-25 08:00 AM | 28-Aug-25 04:00 PM | 19-Nov-25 08:00 AM | 31-Aug-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A3030 | Prepare PSC | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-25 08:00 AM | 08-Aug-25 04:00 PM | 02-Nov-25 08:00 AM | 13-Aug-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A3040 | PSC Review period | 3184 | 2885 | 299 | 3184 | 299 | 100% | 14-Aug-25 08:00 AM | 20-Aug-25 04:00 PM | 12-Nov-25 08:00 AM | 22-Aug-25 04:00 PM | 5.0d | 0.0d | 3184 | 100%
A3035 | Finalise PSC | 2162 | 1981 | 181 | 2162 | 181 | 100% | 11-Aug-25 08:00 AM | 13-Aug-25 04:00 PM | 10-Sep-25 08:00 AM | 16-Aug-25 04:00 PM | 3.0d | 0.0d | 2162 | 100%
1 | Project Management | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 25-Jan-26 04:00 PM | 119.0d | 87.0d | 0
1 | Project Manager | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 28-Jan-26 04:00 PM | 119.0d | 90.0d | 0
PMB-C2120 | Indirect Project Manager B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 31-Aug-25 08:00 AM | 28-Jan-26 04:00 PM | 119.0d | 150.0d | 0 | 100%
2 | Quantity Surveyor | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 26-Jan-26 04:00 PM | 119.0d | 88.0d | 0
PMB-C2140 | QS B-C Cost Bar | 1886 | 1599 | 287 | 1886 | 287 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 28-Jan-26 04:00 PM | 119.0d | 90.0d | 1886 | 100%
3 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 31-Aug-25 08:00 AM | 25-Jan-26 04:00 PM | 119.0d | 147.0d | 0
PMB-C2130 | Project Planner B-C Cost Bar | 2761 | 2440 | 321 | 2761 | 321 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 31-Aug-25 08:00 AM | 26-Jan-26 04:00 PM | 119.0d | 148.0d | 2761 | 100%
2 | Design / Surveys / OP&C | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Sep-25 08:00 AM | 28-Jan-26 04:00 PM | 119.0d | 120.0d | 0
OP&C2010 | Wayleaves/Consents Approval | 2825 | 2428 | 397 | 2825 | 397 | 100% | 01-Aug-25 08:00 AM | 14-Aug-25 04:00 PM | 30-Sep-25 08:00 AM | 16-Aug-25 04:00 PM | 10.0d | 0.0d | 2825 | 100%
PMB-C2020 | Principal Design Co-ordinator/SHES - Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 08:00 AM | 30-Sep-25 08:00 AM | 30-Sep-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
DESIGNB-C-0001 | Design B-C Cost Bar | 1095 | 1005 | 90 | 1095 | 90 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 25-Jan-26 04:00 PM | 119.0d | 87.0d | 1095 | 100%
A2360 | SAP/Commissioning Engineer/Project Engineer Early Engagement | 0 | 0 | 0 | 0 | 0 | 100% | 15-Sep-25 08:00 AM | 15-Sep-25 04:00 PM | 14-Dec-25 08:00 AM | 20-Sep-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4620 | Developed Design Kick off/ Scope agreement | 833 | 727 | 106 | 833 | 106 | 100% | 29-Aug-25 08:00 AM | 29-Aug-25 04:00 PM | 27-Nov-25 08:00 AM | 03-Sep-25 04:00 PM | 1.0d | 0.0d | 833 | 100%
A4630 | Prepare Developed design PSC | 1769 | 1616 | 153 | 1769 | 153 | 100% | 03-Sep-25 08:00 AM | 03-Sep-25 04:00 PM | 03-Oct-25 08:00 AM | 06-Sep-25 04:00 PM | 1.0d | 0.0d | 1769 | 100%
A4640 | Order Placed/Request Supplier Preliminary Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 15-Sep-25 04:00 PM | 15-Sep-25 04:00 PM | 14-Dec-25 04:00 PM | 14-Dec-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
A4660 | Compile Documents Layout for Construction - Civils/Electrical/Route/M&E) | 1748 | 1453 | 295 | 1748 | 295 | 100% | 13-Nov-25 08:00 AM | 26-Nov-25 04:00 PM | 12-Jan-26 08:00 AM | 28-Nov-25 04:00 PM | 10.0d | 0.0d | 1748 | 100%
A4670 | Detailed Third Party Review (Asset Management / Networ Ops) | 0 | 0 | 0 | 0 | 0 | 100% | 27-Nov-25 08:00 AM | 10-Dec-25 04:00 PM | 27-Dec-25 08:00 AM | 13-Dec-25 04:00 PM | 10.0d | 0.0d | 0 | 100%
A4680 | Developed Design Review | 0 | 0 | 0 | 0 | 0 | 100% | 11-Dec-25 08:00 AM | 11-Dec-25 04:00 PM | 10-Jan-26 08:00 AM | 16-Dec-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4770 | Specification and layouts for Tendering | 0 | 0 | 0 | 0 | 0 | 100% | 02-Sep-25 08:00 AM | 02-Sep-25 04:00 PM | 02-Oct-25 08:00 AM | 04-Sep-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4780 | Developed Design 3rd Party | 0 | 0 | 0 | 0 | 0 | 100% | 15-Sep-25 08:00 AM | 10-Oct-25 04:00 PM | 14-Nov-25 08:00 AM | 13-Oct-25 04:00 PM | 20.0d | 0.0d | 0 | 100%
A4790 | Developed Design - UKPN Internal | 0 | 0 | 0 | 0 | 0 | 100% | 15-Sep-25 08:00 AM | 10-Oct-25 04:00 PM | 14-Nov-25 08:00 AM | 12-Oct-25 04:00 PM | 20.0d | 0.0d | 0 | 100%
A4800 | Publish Developed Design Documents & Drawings/Handover to Construction Team | 1870 | 1714 | 156 | 1870 | 156 | 100% | 15-Dec-25 08:00 AM | 15-Dec-25 04:00 PM | 13-Feb-26 08:00 AM | 20-Dec-25 04:00 PM | 1.0d | 0.0d | 1870 | 100%
A4810 | Surveys | 2605 | 2182 | 423 | 2605 | 423 | 100% | 29-Aug-25 08:00 AM | 11-Sep-25 04:00 PM | 28-Sep-25 08:00 AM | 16-Sep-25 04:00 PM | 10.0d | 0.0d | 2605 | 100%
A4930 | Risk & Value Intevention (AST 00 008) | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-25 08:00 AM | 13-Oct-25 04:00 PM | 12-Nov-25 08:00 AM | 16-Oct-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4940 | Risk & Value Intevention B-C | 2449 | 2243 | 206 | 2449 | 206 | 100% | 14-Oct-25 04:00 PM | 14-Oct-25 04:00 PM | 12-Jan-26 04:00 PM | 12-Jan-26 04:00 PM | 0.0d | 0.0d | 2449 | 100%
A4950 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 12-Sep-25 04:00 PM | 12-Sep-25 04:00 PM | 11-Dec-25 04:00 PM | 11-Dec-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
A5000 | Supplier Preliminary Drawings Preparation/Review | 0 | 0 | 0 | 0 | 0 | 100% | 16-Sep-25 08:00 AM | 10-Nov-25 04:00 PM | 15-Nov-25 08:00 AM | 13-Nov-25 04:00 PM | 40.0d | 0.0d | 0 | 100%
A5020 | Completion of Developed Design post Acceptance of anufacturer's Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 12-Nov-25 08:00 AM | 12-Nov-25 04:00 PM | 12-Dec-25 08:00 AM | 17-Nov-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
4 | Procurement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 04:00 PM | 30-Oct-25 08:00 AM | 03-Aug-25 04:00 PM | 1.0d | 0.0d | 0
PRC B-C-1000 | B-C Long Lead Procurement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 04:00 PM | 30-Sep-25 08:00 AM | 04-Aug-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
5 | Gate C Governance | 0 | 0 | 0 | 0 | 0 | 100% | 15-Dec-25 08:00 AM | 06-Feb-26 04:00 PM | 13-Feb-26 08:00 AM |  | 34.0d |  | 0
A2754 | Review of ADP by PM and Project Team | 0 | 0 | 0 | 0 | 0 | 100% | 22-Dec-25 08:00 AM | 05-Jan-26 04:00 PM | 22-Mar-26 08:00 AM | 10-Jan-26 04:00 PM | 5.0d | 0.0d | 0 | 100%
Gate1031 | Prepare Gate C Paper | 3320 | 2810 | 510 | 3320 | 510 | 100% | 06-Jan-26 08:00 AM | 12-Jan-26 04:00 PM |  |  | 5.0d |  | 3320 | 100%
Gate1041 | Submit Gate C Paper to RPfB (AST 01 004 > £1m) | 837 | 695 | 142 | 837 | 142 | 100% | 23-Jan-26 04:00 PM | 23-Jan-26 04:00 PM |  |  | 0.0d |  | 837 | 100%
Gate1035 | ADP Presentation at AMT | 1690 | 1458 | 232 | 1690 | 232 | 100% | 19-Jan-26 08:00 AM | 19-Jan-26 04:00 PM |  |  | 1.0d |  | 1690 | 100%
A2753 | Risk Advisory Board (RAB) Revirew | 1512 | 1350 | 162 | 1512 | 162 | 100% | 16-Jan-26 08:00 AM | 16-Jan-26 04:00 PM |  |  | 1.0d |  | 1512 | 100%
A2752 | Prepare Alliance Delivery Proposal (ADP) | 2977 | 2533 | 444 | 2977 | 444 | 100% | 15-Dec-25 08:00 AM | 19-Dec-25 04:00 PM | 13-Feb-26 08:00 AM | 22-Dec-25 04:00 PM | 5.0d | 0.0d | 2977 | 100%
Q3056 | Prepare WPO | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 06-Feb-26 04:00 PM |  |  | 10.0d |  | 0 | 100%
A4510 | Network Design Review (NDR) | 1258 | 1107 | 151 | 1258 | 151 | 100% | 13-Jan-26 08:00 AM | 13-Jan-26 04:00 PM |  |  | 1.0d |  | 1258 | 100%
A5140 | Gate C QRA Workshop | 0 | 0 | 0 | 0 | 0 | 100% | 23-Jan-26 08:00 AM | 23-Jan-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
4 | Gate C-D | 0 | 0 | 0 | 0 | 0 | 44.31% | 03-Feb-25 08:00 AM | 28-Jul-27 04:00 PM | 05-Mar-25 08:00 AM |  | 621.0d |  | 0
CONT100 | Contract Data - Start Date | 1094 | 953 | 141 | 1094 | 141 | 100% | 06-Feb-26 04:00 PM | 06-Feb-26 04:00 PM |  |  | 0.0d |  | 1094 | 100%
CONT110 | Contract Data - Access Date (Date to be set as per contract info) | 0 | 0 | 0 | 0 | 0 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
CONT130 | Contract Data - Key Date (Add as required)?? | 0 | 0 | 0 | 0 | 0 | 100% | 06-Mar-26 04:00 PM | 06-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
CONT140 | Contract Data - Completion Date for the Whole of the Works | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
1 | Project Management | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
411 | Project Manager | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
PMC-D0001 | Indirect Project Mnagement C-D Cost Bar | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 236.0d |  | 0 | 13%
412 | Quantity Surveyor | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
PMC-D0004 | QS C-D Cost Bar | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 236.0d |  | 0 | 13%
413 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
PMC-D0002 | Project Planner C-D Cost Bar | 1819 | 1561 | 258 | 1819 | 258 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 236.0d |  | 1819 | 13%
3 | Procurement | 0 | 0 | 0 | 0 | 0 | 43.27% | 12-Nov-25 08:00 AM | 14-Aug-26 04:00 PM | 11-Jan-26 08:00 AM |  | 188.0d |  | 0
A5010 | Manufacture of Long Lead items | 0 | 0 | 0 | 0 | 0 | 79.87% | 12-Nov-25 08:00 AM | 10-Apr-26 04:00 PM | 12-Dec-25 08:00 AM |  | 100.0d |  | 0 | 80%
431 | Transformer Procurement | 0 | 0 | 0 | 0 | 0 | 43.27% | 12-Nov-25 08:00 AM | 14-Aug-26 04:00 PM | 12-Dec-25 08:00 AM |  | 188.0d |  | 0
PRC1210 | Transformers manufacture | 1744 | 1530 | 214 | 1744 | 214 | 79.87% | 12-Nov-25 08:00 AM | 10-Apr-26 04:00 PM | 10-Feb-26 08:00 AM |  | 100.0d |  | 1744 | 80%
A5070 | Transformers Delivery | 0 | 0 | 0 | 0 | 0 | 0% | 14-Aug-26 08:00 AM | 14-Aug-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
432 | Switchgear Procurement | 0 | 0 | 0 | 0 | 0 | 43.27% | 12-Nov-25 08:00 AM | 14-Aug-26 04:00 PM | 10-Feb-26 08:00 AM |  | 188.0d |  | 0
PRC2030 | Switchgear Manufacture | 1342 | 1134 | 208 | 1342 | 208 | 79.87% | 12-Nov-25 08:00 AM | 10-Apr-26 04:00 PM | 10-Feb-26 08:00 AM |  | 100.0d |  | 1342 | 80%
A5080 | Switchgear Delivery | 0 | 0 | 0 | 0 | 0 | 0% | 14-Aug-26 08:00 AM | 14-Aug-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
434 | Cable & Materials Procurement | 0 | 0 | 0 | 0 | 0 | 74.38% | 12-Nov-25 08:00 AM | 21-Apr-26 04:00 PM | 11-Jan-26 08:00 AM |  | 107.0d |  | 0
PRC1190 | 11&33kV Cable & Materials manufacture | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0 | 52%
PRC1170 | 132kV Cable Accessories & Jointing manufacture | 0 | 0 | 0 | 0 | 0 | 100% | 12-Nov-25 08:00 AM | 11-Feb-26 04:00 PM | 10-Feb-26 08:00 AM |  | 60.0d |  | 0 | 100%
436 | Relay Panels Procurement | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0
PRC1000 | Relay panels manufacture | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0 | 52%
437 | Overhead Lines Procurement | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0
PRC1090 | OHL manufacture | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0 | 52%
2 | Design / Surveys / OP&C Gate C-D | 0 | 0 | 0 | 0 | 0 | 12.83% | 26-Jan-26 08:00 AM | 04-Jan-27 04:00 PM |  |  | 234.0d |  | 0
PMC-D1960 | Design C-D Cost Bar | 0 | 0 | 0 | 0 | 0 | 15.12% | 26-Jan-26 08:00 AM | 13-Nov-26 04:00 PM |  |  | 205.0d |  | 0 | 15%
A4700 | Technical Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 09-Feb-26 08:00 AM | 09-Feb-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
A4710 | Technical design using Manufacture drawings (Major plant like Transformer, Switchgear etc) | 0 | 0 | 0 | 0 | 0 | 18.62% | 12-Feb-26 08:00 AM | 07-Jul-26 04:00 PM |  |  | 100.0d |  | 0 | 19%
A4720 | Technical design using equipment Specified/ordered post gate C | 1261 | 1123 | 138 | 1261 | 138 | 18.62% | 12-Feb-26 08:00 AM | 07-Jul-26 04:00 PM |  |  | 100.0d |  | 1261 | 19%
A4730 | As-Build Drawings review | 0 | 0 | 0 | 0 | 0 | 0% | 21-Dec-26 08:00 AM | 04-Jan-27 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4820 | Design Support to Construction team (TQs and Troubleshooting) | 0 | 0 | 0 | 0 | 0 | 17.65% | 12-Feb-26 12:00 PM | 15-Jul-26 12:00 PM |  |  | 105.0d |  | 0 | 18%
A4830 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 11-Feb-26 04:00 PM | 11-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
A4840 | Update post construction drawing (Internal Design) | 3150 | 2582 | 568 | 3150 | 568 | 0% | 23-Nov-26 08:00 AM | 18-Dec-26 04:00 PM |  |  | 20.0d |  | 3150 | 0%
A4850 | As built drawing received from Supplier | 1803 | 1645 | 158 | 1803 | 158 | 0% | 13-Nov-26 08:00 AM | 19-Nov-26 04:00 PM |  |  | 5.0d |  | 1803 | 0%
A4860 | Technical Design Complete | 0 | 0 | 0 | 0 | 0 | 0% | 15-Jul-26 12:00 PM | 15-Jul-26 12:00 PM |  |  | 0.0d |  | 0 | 0%
A4870 | As built drawing received from Site | 0 | 0 | 0 | 0 | 0 | 0% | 16-Nov-26 08:00 AM | 20-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4880 | As built drawing received from Commissioning team | 0 | 0 | 0 | 0 | 0 | 0% | 16-Nov-26 08:00 AM | 20-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4960 | Pre-Construction Information - PCI Documentation ((CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 10-Feb-26 04:00 PM | 10-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
A4970 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 04:00 PM | 30-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A5050 | Request protection settings | 2976 | 2599 | 377 | 2976 | 377 | 100% | 12-Feb-26 08:00 AM | 13-Feb-26 04:00 PM |  |  | 2.0d |  | 2976 | 100%
A5060 | Protection Settings | 0 | 0 | 0 | 0 | 0 | 58.97% | 16-Feb-26 08:00 AM | 27-Mar-26 04:00 PM |  |  | 30.0d |  | 0 | 59%
4 | Construction | 0 | 0 | 0 | 0 | 0 | 44.31% | 03-Feb-25 08:00 AM | 28-Jul-27 04:00 PM | 04-May-25 08:00 AM |  | 621.0d |  | 0
A4480 | Direct Costs 2020 | 2104 | 1876 | 228 | 2104 | 228 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 02-Aug-25 04:00 PM | 125.0d | 120.0d | 2104 | 100%
A4490 | Direct Costs 2021 | 0 | 0 | 0 | 0 | 0 | 60.99% | 01-Aug-25 08:00 AM | 31-Jul-26 04:00 PM | 30-Oct-25 08:00 AM |  | 250.0d |  | 0 | 61%
A4500 | Direct Costs 2022 | 703 | 628 | 75 | 703 | 75 | 0% | 03-Aug-26 08:00 AM | 28-Jul-27 04:00 PM |  |  | 247.0d |  | 703 | 0%
441 | Site Pre Start (Enabling Works) | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 20-Feb-26 04:00 PM |  |  | 20.0d |  | 0
A1980 | Prepare Construction Phase Plan | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 30-Jan-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
A1990 | Prepare Issue F10 | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 30-Jan-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
A2000 | Setup Health & safety File | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 30-Jan-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
PS4480 | Site Access | 0 | 0 | 0 | 0 | 0 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
442 | Mobilisation | 0 | 0 | 0 | 0 | 0 | 100% | 02-Feb-26 08:00 AM | 20-Feb-26 04:00 PM |  |  | 15.0d |  | 0
T2650 | Mobilisation of Principle Contractor | 3363 | 2982 | 381 | 3363 | 381 | 100% | 02-Feb-26 08:00 AM | 20-Feb-26 04:00 PM |  |  | 15.0d |  | 3363 | 100%
443 | Outages | 0 | 0 | 0 | 0 | 0 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 0
OUT1920 | Outage 1 | 0 | 0 | 0 | 0 | 0 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 0 | 100%
OUT1930 | Outage 2 | 2905 | 2487 | 418 | 2905 | 418 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 2905 | 100%
444 | Building Civils & Fit Out Contract | 0 | 0 | 0 | 0 | 0 | 10.92% | 20-Feb-26 04:00 PM | 13-Aug-26 04:00 PM |  |  | 120.0d |  | 0
CONS-14260 | Civils Start Date | 0 | 0 | 0 | 0 | 0 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
A5100 | Building works | 3278 | 2709 | 569 | 3278 | 569 | 9.36% | 23-Feb-26 08:00 AM | 13-Aug-26 04:00 PM |  |  | 120.0d |  | 3278 | 9%
A5110 | Switchroom Water Tight | 3158 | 2798 | 360 | 3158 | 360 | 0% | 13-Aug-26 04:00 PM | 13-Aug-26 04:00 PM |  |  | 0.0d |  | 3158 | 0%
A5120 | Transformer Bay ready for delivery | 0 | 0 | 0 | 0 | 0 | 0% | 13-Aug-26 04:00 PM | 13-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
445 | Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 05-Nov-26 04:00 PM |  |  | 58.0d |  | 0
CONS-13730 | Install Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 14-Sep-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
CONS-3740 | Install TX Transformer Tails | 2940 | 2507 | 433 | 2940 | 433 | 0% | 15-Sep-26 08:00 AM | 17-Sep-26 04:00 PM |  |  | 3.0d |  | 2940 | 0%
CONS-3750 | Install Transformer Protection Panels & AVC | 0 | 0 | 0 | 0 | 0 | 0% | 18-Sep-26 08:00 AM | 24-Sep-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
CONS-3760 | Cold Commission Transformer | 1027 | 874 | 153 | 1027 | 153 | 0% | 25-Sep-26 08:00 AM | 15-Oct-26 04:00 PM |  |  | 15.0d |  | 1027 | 0%
CONS-14170 | Transformer Installation Planned Completion | 0 | 0 | 0 | 0 | 0 | 0% | 19-Oct-26 04:00 PM | 19-Oct-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A3070 | Hot commissioning of Transformer | 1922 | 1739 | 183 | 1922 | 183 | 0% | 16-Oct-26 08:00 AM | 05-Nov-26 04:00 PM |  |  | 15.0d |  | 1922 | 0%
446 | Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 16-Nov-26 04:00 PM |  |  | 65.0d |  | 0
CONS-1830 | Install 11kV Switchgear | 1160 | 1034 | 126 | 1160 | 126 | 0% | 17-Aug-26 08:00 AM | 14-Sep-26 04:00 PM |  |  | 20.0d |  | 1160 | 0%
CONS-3840 | Install Multicores & Terminate | 1685 | 1432 | 253 | 1685 | 253 | 0% | 15-Sep-26 08:00 AM | 21-Sep-26 04:00 PM |  |  | 5.0d |  | 1685 | 0%
CONS-13850 | Cold Commission 11/6.6kV Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 22-Sep-26 08:00 AM | 19-Oct-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
CONS-14200 | 11/6.6kV Switchgear Installation Planned Completion | 725 | 617 | 108 | 725 | 108 | 0% | 19-Oct-26 04:00 PM | 19-Oct-26 04:00 PM |  |  | 0.0d |  | 725 | 0%
CONS-14210 | 11/6.6kV Switchgear Installation Planned Start | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 17-Aug-26 08:00 AM |  |  | 0.0d |  | 0 | 0%
A2570 | Switchgear Install Cost | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 16-Nov-26 04:00 PM |  |  | 65.0d |  | 0 | 0%
A3080 | Hot commissioning of Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 16-Nov-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
447 | Overhead Lines | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-26 08:00 AM | 22-Apr-26 08:00 AM |  |  | 0.0d |  | 0
CONS-14250 | Overhead Lines Installation Planned Start | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-26 08:00 AM | 22-Apr-26 08:00 AM |  |  | 0.0d |  | 0 | 0%
448 | Cable Install | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-26 08:00 AM | 05-Jun-26 04:00 PM |  |  | 31.0d |  | 0
CONS-5720 | Cable Installation Planned Start | 1623 | 1397 | 226 | 1623 | 226 | 0% | 22-Apr-26 08:00 AM | 22-Apr-26 08:00 AM |  |  | 0.0d |  | 1623 | 0%
CONS-14150 | Cable Installation Planned Completion | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jun-26 04:00 PM | 05-Jun-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CONS-14160 | Cable Installation Contract Completion Date | 3324 | 2858 | 466 | 3324 | 466 | 0% | 05-Jun-26 04:00 PM | 05-Jun-26 04:00 PM |  |  | 0.0d |  | 3324 | 0%
T13940 | Install 11kV Cabling | 1304 | 1108 | 196 | 1304 | 196 | 0% | 22-Apr-26 08:00 AM | 20-May-26 04:00 PM |  |  | 20.0d |  | 1304 | 0%
T13950 | Cable Sheath Tests | 0 | 0 | 0 | 0 | 0 | 0% | 21-May-26 08:00 AM | 28-May-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
T13960 | Joint & Terminate Cables | 0 | 0 | 0 | 0 | 0 | 0% | 29-May-26 08:00 AM | 04-Jun-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
T13970 | 11kV Pressure Tests | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jun-26 08:00 AM | 05-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
449 | Test & Commissioning | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 13-Nov-26 04:00 PM |  |  | 19.0d |  | 0
TC4890 | SAP Updated | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 08:00 AM | 21-Oct-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
TC4900 | Netmap Updated | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 08:00 AM | 21-Oct-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
CLO130 | Demobilise from site | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 08:00 AM | 13-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A2940 | Hot Commissioning of Substation | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 20-Oct-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A2950 | Energisation | 0 | 0 | 0 | 0 | 0 | 0% | 06-Nov-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A3060 | Protection Settings uploaded | 2759 | 2297 | 462 | 2759 | 462 | 0% | 20-Oct-26 04:00 PM | 20-Oct-26 04:00 PM |  |  | 0.0d |  | 2759 | 0%
A4450 | Substation Under Rules | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 08:00 AM | 21-Oct-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
6 | Closure | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 158.0d |  | 0
CLO3100 | Project Handover - to Network Ops | 1837 | 1583 | 254 | 1837 | 254 | 0% | 05-Jan-27 08:00 AM | 05-Jan-27 04:00 PM |  |  | 1.0d |  | 1837 | 0%
CLO120 | Review and Approve H&S File | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 02-Nov-26 04:00 PM |  |  | 10.0d |  | 0 | 0%
CLO14150 | Financial Closure | 0 | 0 | 0 | 0 | 0 | 0% | 16-Nov-26 08:00 AM | 13-May-27 04:00 PM |  |  | 120.0d |  | 0 | 0%
CLO15940 | Familiarisation Training | 1747 | 1596 | 151 | 1747 | 151 | 0% | 13-Nov-26 08:00 AM | 26-Nov-26 04:00 PM |  |  | 10.0d |  | 1747 | 0%
A4460 | Deadline for submission of defined costs (65 days from contract completion) | 0 | 0 | 0 | 0 | 0 | 0% | 11-Dec-26 04:00 PM | 11-Dec-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-27 08:00 AM | 11-Jun-27 04:00 PM |  |  | 20.0d |  | 0
Gate1080 | Prepare Gate D Paper | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-27 08:00 AM | 11-Jun-27 04:00 PM |  |  | 20.0d |  | 0 | 0%
Gate1090 | Submit Gate D Paper to RPrB (AST 01 004 > £1m) | 3245 | 2879 | 366 | 3245 | 366 | 0% | 11-Jun-27 04:00 PM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 3245 | 0%
M-E.MCN.109347 | EDL Harlow Science Park, Zone 5 London Road, CM17 9NA | 0 | 0 | 0 | 0 | 0 | 44.31% | 03-Feb-25 08:00 AM | 28-Jul-27 04:00 PM | 04-Apr-25 08:00 AM |  | 621.0d |  | 0
1 | Project Summary | 0 | 0 | 0 | 0 | 0 | 48.37% | 03-Feb-25 08:00 AM | 13-May-27 04:00 PM | 04-Apr-25 08:00 AM |  | 568.0d |  | 0
6 | Project Governance Milestones | 0 | 0 | 0 | 0 | 0 | 57.2% | 03-Feb-25 08:00 AM | 05-Jan-27 04:00 PM | 05-Mar-25 08:00 AM |  | 479.0d |  | 0
Gate1000 | Gate A Award | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 05-Mar-25 08:00 AM | 05-Mar-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1010 | Gate B Award | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 08:00 AM | 30-Oct-25 08:00 AM | 30-Oct-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1020 | Gate C Award | 0 | 0 | 0 | 0 | 0 | 100% | 23-Jan-26 04:00 PM | 23-Jan-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
Gate1050 | Gate D Award | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jan-27 04:00 PM | 05-Jan-27 04:00 PM |  |  | 0.0d |  | 0 | 0%
Gate1040 | Hong Kong Board Review | 0 | 0 | 0 | 0 | 0 | 100% | 27-Feb-26 04:00 PM | 27-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
Gate1030 | Executive Management Team Review | 0 | 0 | 0 | 0 | 0 | 100% | 13-Feb-26 04:00 PM | 13-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
9 | Construction Delivery Milestones | 0 | 0 | 0 | 0 | 0 | 59.13% | 10-Mar-25 04:00 PM | 19-Nov-26 04:00 PM | 09-May-25 04:00 PM |  | 427.0d |  | 0
DEL1050 | Start on Site | 3352 | 3050 | 302 | 3352 | 302 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 3352 | 100%
DEL1080 | Hot Commissioning Commencement | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 20-Oct-26 08:00 AM |  |  | 0.0d |  | 0 | 0%
DEL1130 | Customer (MC or APP) Energisation available | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1090 | Li Intervention | 2119 | 1867 | 252 | 2119 | 252 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 2119 | 0%
DEL1060 | Hi Intervention | 0 | 0 | 0 | 0 | 0 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 0 | 100%
DEL1140 | Site Demobilisation Complete | 2575 | 2188 | 387 | 2575 | 387 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 2575 | 0%
DEL1100 | Switchgear Energised | 995 | 870 | 125 | 995 | 125 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 995 | 0%
DEL1110 | Tx1 Energised | 1393 | 1142 | 251 | 1393 | 251 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 1393 | 0%
DEL1120 | Cct 1 Energised | 0 | 0 | 0 | 0 | 0 | 0% | 12-Nov-26 04:00 PM | 12-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1070 | Practical Completion | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
DEL1010 | Concept Design Signed off - CAP 02-017 | 3277 | 2780 | 497 | 3277 | 497 | 100% | 25-Jun-25 04:00 PM | 25-Jun-25 04:00 PM | 25-Jul-25 04:00 PM | 25-Jul-25 04:00 PM | 0.0d | 0.0d | 3277 | 100%
DEL1000 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 04:00 PM | 10-Mar-25 04:00 PM | 09-Apr-25 04:00 PM | 09-Apr-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1030 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building/Route/Earthing/Component) | 0 | 0 | 0 | 0 | 0 | 100% | 11-Nov-25 04:00 PM | 11-Nov-25 04:00 PM | 11-Dec-25 04:00 PM | 11-Dec-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1040 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 12-Dec-25 04:00 PM | 12-Dec-25 04:00 PM | 11-Jan-26 04:00 PM | 11-Jan-26 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1020 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 01-Sep-25 04:00 PM | 01-Sep-25 04:00 PM | 30-Nov-25 04:00 PM | 30-Nov-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1150 | Customer Required By energisation date | 0 | 0 | 0 | 0 | 0 | 0% | 19-Nov-26 04:00 PM | 19-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
10 | Alliance Engagement Milestones | 0 | 0 | 0 | 0 | 0 | 100% | 14-Feb-25 04:00 PM | 06-Feb-26 04:00 PM | 16-Mar-25 04:00 PM |  | 244.0d |  | 0
AL1000 | Project Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 14-Feb-25 04:00 PM | 14-Feb-25 04:00 PM | 15-May-25 04:00 PM | 15-May-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
AL1090 | Alliance Delivery Proposal Received (ADP) | 0 | 0 | 0 | 0 | 0 | 100% | 22-Dec-25 08:00 AM | 22-Dec-25 08:00 AM | 20-Feb-26 08:00 AM | 20-Feb-26 08:00 AM | 0.0d | 0.0d | 0 | 100%
AL2000 | ADP Approved by AMT | 0 | 0 | 0 | 0 | 0 | 100% | 19-Jan-26 04:00 PM | 19-Jan-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
AL2010 | Award WPO Contract | 0 | 0 | 0 | 0 | 0 | 100% | 06-Feb-26 04:00 PM | 06-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
AL1040 | Acceptance of AIP by Delivery Member | 0 | 0 | 0 | 0 | 0 | 100% | 21-Jul-25 04:00 PM | 21-Jul-25 04:00 PM | 19-Oct-25 04:00 PM | 19-Oct-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
AL1050 | Award PSC Contract - Developed Design | 2185 | 1885 | 300 | 2185 | 300 | 100% | 20-Aug-25 04:00 PM | 20-Aug-25 04:00 PM | 19-Sep-25 04:00 PM | 19-Sep-25 04:00 PM | 0.0d | 0.0d | 2185 | 100%
AL1010 | Award PSC Contract - Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 21-Feb-25 04:00 PM | 21-Feb-25 04:00 PM | 22-Apr-25 04:00 PM | 22-Apr-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
8 | Asset Registration/Update Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 20-May-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 108.0d |  | 0
ASS1030 | Asset Data - Updated (SAP -Switchgear) | 2081 | 1826 | 255 | 2081 | 255 | 0% | 21-Oct-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 0.0d |  | 2081 | 0%
ASS1040 | Asset Data - Updated (Netmap - Cable records) | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1010 | Asset Data - Registration (SAP) - Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 04:00 PM | 17-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
ASS1000 | Asset Data - Registration (Netmap) | 2658 | 2353 | 305 | 2658 | 305 | 0% | 20-May-26 04:00 PM | 20-May-26 04:00 PM |  |  | 0.0d |  | 2658 | 0%
ASS1020 | Asset Data - Registration (SAP) - Switchgear | 721 | 625 | 96 | 721 | 96 | 0% | 17-Aug-26 04:00 PM | 17-Aug-26 04:00 PM |  |  | 0.0d |  | 721 | 0%
ASS1050 | Asset Data - Updated (SAP - Transformer) | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 04:00 PM | 21-Oct-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
7 | Project Closeout Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 02-Nov-26 04:00 PM | 13-May-27 04:00 PM |  |  | 128.0d |  | 0
CLO1000 | Project Completion | 2199 | 1899 | 300 | 2199 | 300 | 0% | 05-Jan-27 04:00 PM | 05-Jan-27 04:00 PM |  |  | 0.0d |  | 2199 | 0%
CLO1020 | Project Handover - to Network Ops | 1971 | 1657 | 314 | 1971 | 314 | 0% | 05-Jan-27 04:00 PM | 05-Jan-27 04:00 PM |  |  | 0.0d |  | 1971 | 0%
CLO1030 | Financial Close | 2952 | 2559 | 393 | 2952 | 393 | 0% | 13-May-27 04:00 PM | 13-May-27 04:00 PM |  |  | 0.0d |  | 2952 | 0%
CLO1050 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 04-Jan-27 04:00 PM | 04-Jan-27 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1010 | Completion Certificate Signed off | 0 | 0 | 0 | 0 | 0 | 0% | 11-Dec-26 04:00 PM | 11-Dec-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1060 | Completion of the Health and Safety File | 0 | 0 | 0 | 0 | 0 | 0% | 02-Nov-26 04:00 PM | 02-Nov-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
1 | Project Specific Milestones - Inc. Contract Data | 0 | 0 | 0 | 0 | 0 | 100% | 04-Apr-25 04:00 PM | 14-Aug-25 04:00 PM | 03-Jun-25 04:00 PM | 17-Aug-25 04:00 PM | 90.0d | 75.0d | 0
ProjKM1000 | Consent Conveyacing Pack Submission | 0 | 0 | 0 | 0 | 0 | 100% | 04-Apr-25 04:00 PM | 04-Apr-25 04:00 PM | 03-Jul-25 04:00 PM | 03-Jul-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM1020 | Project Consents Executed | 0 | 0 | 0 | 0 | 0 | 100% | 14-Aug-25 04:00 PM | 14-Aug-25 04:00 PM | 13-Oct-25 04:00 PM | 13-Oct-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
TASK DESIGN DELIVERY MILESTONES | TASK DESIGN DELIVERY MILESTONES (DO NOT DELETE or CHANGE ACTIVITY ID) | 0 | 0 | 0 | 0 | 0 | 55.04% | 10-Mar-25 08:00 AM | 04-Jan-27 04:00 PM | 08-Jun-25 08:00 AM |  | 453.0d |  | 0
DES-DM1 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 10-Mar-25 04:00 PM | 09-May-25 08:00 AM | 15-Mar-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM2 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 08-May-25 08:00 AM | 08-May-25 04:00 PM | 06-Aug-25 08:00 AM | 10-May-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM3 | Risk & Value Intevention A-B | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-25 08:00 AM | 19-May-25 04:00 PM | 18-Jun-25 08:00 AM | 22-May-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM4 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 25-Jun-25 08:00 AM | 25-Jun-25 04:00 PM | 23-Sep-25 08:00 AM | 27-Jun-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM5 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 1002 | 912 | 90 | 1002 | 90 | 100% | 01-Sep-25 08:00 AM | 01-Sep-25 04:00 PM | 30-Nov-25 08:00 AM | 06-Sep-25 04:00 PM | 1.0d | 0.0d | 1002 | 100%
DES-DM6 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 12-Sep-25 08:00 AM | 12-Sep-25 04:00 PM | 12-Oct-25 08:00 AM | 17-Sep-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM7 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building / Route / Earthing / Component) | 0 | 0 | 0 | 0 | 0 | 100% | 11-Nov-25 08:00 AM | 11-Nov-25 04:00 PM | 09-Feb-26 08:00 AM | 14-Nov-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM8 | Risk & Value Intevention B-C | 3255 | 2927 | 328 | 3255 | 328 | 100% | 14-Oct-25 08:00 AM | 14-Oct-25 04:00 PM | 12-Jan-26 08:00 AM | 19-Oct-25 04:00 PM | 1.0d | 0.0d | 3255 | 100%
DES-DM9 | Develped Design Signed off - CAP 02-017 | 785 | 657 | 128 | 785 | 128 | 100% | 12-Dec-25 08:00 AM | 12-Dec-25 04:00 PM | 10-Feb-26 08:00 AM | 14-Dec-25 04:00 PM | 1.0d | 0.0d | 785 | 100%
DES-DM10-1 | Asset Data - Registration (SAP) - Transformer | 1082 | 896 | 186 | 1082 | 186 | 0% | 17-Aug-26 08:00 AM | 17-Aug-26 04:00 PM |  |  | 1.0d |  | 1082 | 0%
DES-DM10-2 | Asset Data - Registration (SAP) - Switchgear | 2229 | 1942 | 287 | 2229 | 287 | 0% | 17-Aug-26 08:00 AM | 17-Aug-26 04:00 PM |  |  | 1.0d |  | 2229 | 0%
DES-DM11 | Pre-Construction Information - PCI Documentation (CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 10-Feb-26 08:00 AM | 10-Feb-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
DES-DM12 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 11-Feb-26 08:00 AM | 11-Feb-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
DES-DM13 | Protection Settings Issued | 2454 | 2167 | 287 | 2454 | 287 | 0% | 30-Mar-26 08:00 AM | 30-Mar-26 04:00 PM |  |  | 1.0d |  | 2454 | 0%
DES-DM14 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 04-Jan-27 08:00 AM | 04-Jan-27 04:00 PM |  |  | 1.0d |  | 0 | 0%
2 | Pre Gate B | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-May-25 08:00 AM | 05-Aug-25 04:00 PM | 125.0d | 93.0d | 0
1 | Project Management | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 03-Aug-25 04:00 PM | 125.0d | 121.0d | 0
1 | Project Manager | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 05-Mar-25 08:00 AM | 05-Aug-25 04:00 PM | 125.0d | 153.0d | 0
PMA-B0010 | Indirect Project Management Pre-Gate B Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 02-Aug-25 04:00 PM | 125.0d | 120.0d | 0 | 100%
2 | Quantity Surveyor | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 03-Aug-25 04:00 PM | 125.0d | 121.0d | 0
PMA-B0020 | QS Pre-Gate B Cost Bar | 1220 | 1041 | 179 | 1220 | 179 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 05-Mar-25 08:00 AM | 05-Aug-25 04:00 PM | 125.0d | 153.0d | 1220 | 100%
3 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-Apr-25 08:00 AM | 02-Aug-25 04:00 PM | 125.0d | 120.0d | 0
PMA-B0030 | Project Planner Pre-Gate B Cost Bar | 897 | 809 | 88 | 897 | 88 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 05-Mar-25 08:00 AM | 03-Aug-25 04:00 PM | 125.0d | 151.0d | 897 | 100%
2 | PM Activities | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 07-Mar-25 04:00 PM | 04-May-25 08:00 AM | 09-Mar-25 04:00 PM | 25.0d | 0.0d | 0
Al0010 | Start 1st Draft PEP & AIP | 0 | 0 | 0 | 0 | 0 | 100% | 21-Feb-25 04:00 PM | 21-Feb-25 04:00 PM | 22-May-25 04:00 PM | 22-May-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
FEED-A-B-M-0003 | Works Information & contract Scope Complete & Agreed (PSC) | 3057 | 2735 | 322 | 3057 | 322 | 100% | 21-Feb-25 04:00 PM | 21-Feb-25 04:00 PM | 22-Apr-25 04:00 PM | 22-Apr-25 04:00 PM | 0.0d | 0.0d | 3057 | 100%
FEED-0040 | Build Gate B-C Detailed Programme containing High level Gate C-D | 0 | 0 | 0 | 0 | 0 | 100% | 03-Mar-25 08:00 AM | 07-Mar-25 04:00 PM | 01-Jun-25 08:00 AM | 10-Mar-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A2640 | Work Order Number Raised | 1251 | 1110 | 141 | 1251 | 141 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 05-Mar-25 08:00 AM | 05-Mar-25 08:00 AM | 0.0d | 0.0d | 1251 | 100%
A2920 | Mobilise | 0 | 0 | 0 | 0 | 0 | 100% | 24-Feb-25 08:00 AM | 28-Feb-25 04:00 PM | 25-May-25 08:00 AM | 02-Mar-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A3010 | Early Engagement in place for Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-25 08:00 AM | 03-Feb-25 08:00 AM | 05-Mar-25 08:00 AM | 05-Mar-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
3 | OP&C Wayleave/Planng Permission/Consents | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 04-Apr-25 04:00 PM | 08-Jun-25 08:00 AM | 09-Apr-25 04:00 PM | 20.0d | 0.0d | 0
OP&C2000 | Wayleave Permissions/Planning Consents | 2228 | 1876 | 352 | 2228 | 352 | 100% | 10-Mar-25 08:00 AM | 04-Apr-25 04:00 PM | 09-May-25 08:00 AM | 06-Apr-25 04:00 PM | 20.0d | 0.0d | 2228 | 100%
5 | Enabling / Preparation Works | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 21-Mar-25 04:00 PM | 08-Jun-25 08:00 AM | 24-Mar-25 04:00 PM | 10.0d | 0.0d | 0
EN-A-B-0010 | Enabling Works | 0 | 0 | 0 | 0 | 0 | 100% | 10-Mar-25 08:00 AM | 21-Mar-25 04:00 PM | 08-Jun-25 08:00 AM | 23-Mar-25 04:00 PM | 10.0d | 0.0d | 0 | 100%
9 | Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 03-Mar-25 08:00 AM | 27-Jun-25 04:00 PM | 01-Jun-25 08:00 AM | 02-Jul-25 04:00 PM | 81.0d | 31.0d | 0
FEED-A-B-M-0006 | Concept Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 03-Mar-25 08:00 AM | 07-Mar-25 04:00 PM | 02-Apr-25 08:00 AM | 12-Mar-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A4530 | Site Visit | 0 | 0 | 0 | 0 | 0 | 100% | 11-Mar-25 08:00 AM | 11-Mar-25 04:00 PM | 10-Apr-25 08:00 AM | 14-Mar-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4540 | Site information review/ Protection Phylosophy/ Preliminary Layouts | 0 | 0 | 0 | 0 | 0 | 100% | 12-Mar-25 08:00 AM | 24-Mar-25 04:00 PM | 11-May-25 08:00 AM | 29-Mar-25 04:00 PM | 9.0d | 0.0d | 0 | 100%
A4550 | Surveys | 2297 | 1929 | 368 | 2297 | 368 | 100% | 10-Mar-25 08:00 AM | 07-May-25 04:00 PM | 09-Apr-25 08:00 AM | 09-May-25 04:00 PM | 40.0d | 30.0d | 2297 | 100%
A4560 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 08-May-25 04:00 PM | 08-May-25 04:00 PM | 06-Aug-25 04:00 PM | 06-Aug-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
A4580 | Risk & Value Intevention | 0 | 0 | 0 | 0 | 0 | 100% | 12-May-25 08:00 AM | 16-May-25 04:00 PM | 10-Aug-25 08:00 AM | 21-May-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A4590 | Layouts ready for estimating | 1736 | 1427 | 309 | 1736 | 309 | 100% | 20-May-25 08:00 AM | 17-Jun-25 04:00 PM | 19-Jun-25 08:00 AM | 19-Jun-25 04:00 PM | 20.0d | 0.0d | 1736 | 100%
A4600 | Concept Design Review | 2197 | 1855 | 342 | 2197 | 342 | 100% | 18-Jun-25 08:00 AM | 24-Jun-25 04:00 PM | 16-Sep-25 08:00 AM | 27-Jun-25 04:00 PM | 5.0d | 0.0d | 2197 | 100%
A4740 | Concept Design | 2027 | 1757 | 270 | 2027 | 270 | 100% | 09-May-25 08:00 AM | 09-May-25 04:00 PM | 08-Jul-25 08:00 AM | 11-May-25 04:00 PM | 1.0d | 0.0d | 2027 | 100%
A4750 | Publish Concept Design Documents & Drawings | 3182 | 2878 | 304 | 3182 | 304 | 100% | 27-Jun-25 08:00 AM | 27-Jun-25 04:00 PM | 26-Aug-25 08:00 AM | 02-Jul-25 04:00 PM | 1.0d | 0.0d | 3182 | 100%
A4760 | Prepare Design cost estimate for Developed & Technical stage (CAP15/16) | 1134 | 937 | 197 | 1134 | 197 | 100% | 26-Jun-25 08:00 AM | 26-Jun-25 04:00 PM | 26-Jul-25 08:00 AM | 01-Jul-25 04:00 PM | 1.0d | 0.0d | 1134 | 100%
A4910 | Environmental Survey | 0 | 0 | 0 | 0 | 0 | 100% | 24-Mar-25 08:00 AM | 24-Mar-25 04:00 PM | 23-Apr-25 08:00 AM | 27-Mar-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4920 | Risk & Value Intevention A-B | 0 | 0 | 0 | 0 | 0 | 100% | 19-May-25 04:00 PM | 19-May-25 04:00 PM | 18-Jul-25 04:00 PM | 18-Jul-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
7 | Gate B Governance | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jun-25 08:00 AM | 29-Jul-25 08:00 AM | 25-Aug-25 08:00 AM | 31-Jul-25 08:00 AM | 23.0d | 0.0d | 0
FEED-A-B-M-0010 | Issue AIP | 0 | 0 | 0 | 0 | 0 | 100% | 16-Jul-25 04:00 PM | 16-Jul-25 04:00 PM | 15-Aug-25 04:00 PM | 15-Aug-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
Gate2030 | Submit Gate B Paper to RPfB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 100% | 29-Jul-25 08:00 AM | 29-Jul-25 08:00 AM | 28-Aug-25 08:00 AM | 28-Aug-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
FEED-2350 | Update PEP | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jun-25 08:00 AM | 27-Jun-25 04:00 PM | 26-Jul-25 08:00 AM | 29-Jun-25 04:00 PM | 2.0d | 0.0d | 0 | 100%
Gate2000 | Prepare Gate B Paper | 2569 | 2212 | 357 | 2569 | 357 | 100% | 03-Jul-25 08:00 AM | 16-Jul-25 04:00 PM | 01-Oct-25 08:00 AM | 19-Jul-25 04:00 PM | 10.0d | 0.0d | 2569 | 100%
A2720 | Risk & Value workshop | 1230 | 1086 | 144 | 1230 | 144 | 100% | 04-Jul-25 08:00 AM | 04-Jul-25 04:00 PM | 03-Aug-25 08:00 AM | 06-Jul-25 04:00 PM | 1.0d | 0.0d | 1230 | 100%
A2770 | GATE B Presentation at AMT | 0 | 0 | 0 | 0 | 0 | 100% | 23-Jul-25 08:00 AM | 23-Jul-25 04:00 PM | 22-Aug-25 08:00 AM | 28-Jul-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2880 | Network Design Review (NDR) | 1671 | 1402 | 269 | 1671 | 269 | 100% | 17-Jul-25 08:00 AM | 17-Jul-25 04:00 PM | 15-Oct-25 08:00 AM | 22-Jul-25 04:00 PM | 1.0d | 0.0d | 1671 | 100%
A2890 | Risk Advisory Board (RAB) Revirew | 0 | 0 | 0 | 0 | 0 | 100% | 22-Jul-25 08:00 AM | 22-Jul-25 04:00 PM | 20-Sep-25 08:00 AM | 25-Jul-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2900 | Update P6 programme & Cost phasing | 2444 | 2173 | 271 | 2444 | 271 | 100% | 26-Jun-25 08:00 AM | 02-Jul-25 04:00 PM | 26-Jul-25 08:00 AM | 07-Jul-25 04:00 PM | 5.0d | 0.0d | 2444 | 100%
A2910 | Gate B CU Design | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jun-25 08:00 AM | 02-Jul-25 04:00 PM | 24-Sep-25 08:00 AM | 04-Jul-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A2795 | ADM Review and acceptance of AIP | 0 | 0 | 0 | 0 | 0 | 100% | 17-Jul-25 08:00 AM | 21-Jul-25 04:00 PM | 16-Aug-25 08:00 AM | 24-Jul-25 04:00 PM | 3.0d | 0.0d | 0 | 100%
A5130 | Gate B QRA Workshop | 1402 | 1218 | 184 | 1402 | 184 | 100% | 23-Jul-25 08:00 AM | 23-Jul-25 04:00 PM | 22-Aug-25 08:00 AM | 28-Jul-25 04:00 PM | 1.0d | 0.0d | 1402 | 100%
3 | Gate B-C | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 06-Feb-26 04:00 PM | 30-Oct-25 08:00 AM |  | 129.0d |  | 0
A2780 | B to C Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-25 08:00 AM | 04-Aug-25 04:00 PM | 03-Oct-25 08:00 AM | 07-Aug-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A2790 | Update PEP, Formalise AIP & Appendix B, Set Target Budget | 0 | 0 | 0 | 0 | 0 | 100% | 05-Aug-25 08:00 AM | 11-Aug-25 04:00 PM | 03-Nov-25 08:00 AM | 13-Aug-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A2800 | Review of Target Budget and sign off | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-25 08:00 AM | 14-Aug-25 04:00 PM | 11-Sep-25 08:00 AM | 19-Aug-25 04:00 PM | 3.0d | 0.0d | 0 | 100%
A3046 | Mobilise | 0 | 0 | 0 | 0 | 0 | 100% | 21-Aug-25 08:00 AM | 28-Aug-25 04:00 PM | 20-Oct-25 08:00 AM | 02-Sep-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A3030 | Prepare PSC | 1447 | 1222 | 225 | 1447 | 225 | 100% | 04-Aug-25 08:00 AM | 08-Aug-25 04:00 PM | 02-Nov-25 08:00 AM | 11-Aug-25 04:00 PM | 5.0d | 0.0d | 1447 | 100%
A3040 | PSC Review period | 0 | 0 | 0 | 0 | 0 | 100% | 14-Aug-25 08:00 AM | 20-Aug-25 04:00 PM | 12-Nov-25 08:00 AM | 25-Aug-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
A3035 | Finalise PSC | 0 | 0 | 0 | 0 | 0 | 100% | 11-Aug-25 08:00 AM | 13-Aug-25 04:00 PM | 10-Oct-25 08:00 AM | 15-Aug-25 04:00 PM | 3.0d | 0.0d | 0 | 100%
1 | Project Management | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 31-Aug-25 08:00 AM | 26-Jan-26 04:00 PM | 119.0d | 148.0d | 0
1 | Project Manager | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 28-Jan-26 04:00 PM | 119.0d | 90.0d | 0
PMB-C2120 | Indirect Project Manager B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 25-Jan-26 04:00 PM | 119.0d | 87.0d | 0 | 100%
2 | Quantity Surveyor | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 26-Jan-26 04:00 PM | 119.0d | 88.0d | 0
PMB-C2140 | QS B-C Cost Bar | 2669 | 2363 | 306 | 2669 | 306 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 31-Aug-25 08:00 AM | 25-Jan-26 04:00 PM | 119.0d | 147.0d | 2669 | 100%
3 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Oct-25 08:00 AM | 28-Jan-26 04:00 PM | 119.0d | 90.0d | 0
PMB-C2130 | Project Planner B-C Cost Bar | 764 | 627 | 137 | 764 | 137 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Sep-25 08:00 AM | 28-Jan-26 04:00 PM | 119.0d | 120.0d | 764 | 100%
2 | Design / Surveys / OP&C | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Sep-25 08:00 AM | 26-Jan-26 04:00 PM | 119.0d | 118.0d | 0
OP&C2010 | Wayleaves/Consents Approval | 1846 | 1651 | 195 | 1846 | 195 | 100% | 01-Aug-25 08:00 AM | 14-Aug-25 04:00 PM | 30-Oct-25 08:00 AM | 19-Aug-25 04:00 PM | 10.0d | 0.0d | 1846 | 100%
PMB-C2020 | Principal Design Co-ordinator/SHES - Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 08:00 AM | 30-Oct-25 08:00 AM | 30-Oct-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
DESIGNB-C-0001 | Design B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 23-Jan-26 04:00 PM | 30-Sep-25 08:00 AM | 26-Jan-26 04:00 PM | 119.0d | 118.0d | 0 | 100%
A2360 | SAP/Commissioning Engineer/Project Engineer Early Engagement | 3360 | 3013 | 347 | 3360 | 347 | 100% | 15-Sep-25 08:00 AM | 15-Sep-25 04:00 PM | 14-Nov-25 08:00 AM | 20-Sep-25 04:00 PM | 1.0d | 0.0d | 3360 | 100%
A4620 | Developed Design Kick off/ Scope agreement | 3354 | 2785 | 569 | 3354 | 569 | 100% | 29-Aug-25 08:00 AM | 29-Aug-25 04:00 PM | 27-Nov-25 08:00 AM | 31-Aug-25 04:00 PM | 1.0d | 0.0d | 3354 | 100%
A4630 | Prepare Developed design PSC | 766 | 661 | 105 | 766 | 105 | 100% | 03-Sep-25 08:00 AM | 03-Sep-25 04:00 PM | 02-Nov-25 08:00 AM | 06-Sep-25 04:00 PM | 1.0d | 0.0d | 766 | 100%
A4640 | Order Placed/Request Supplier Preliminary Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 15-Sep-25 04:00 PM | 15-Sep-25 04:00 PM | 15-Oct-25 04:00 PM | 15-Oct-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
A4660 | Compile Documents Layout for Construction - Civils/Electrical/Route/M&E) | 0 | 0 | 0 | 0 | 0 | 100% | 13-Nov-25 08:00 AM | 26-Nov-25 04:00 PM | 13-Dec-25 08:00 AM | 01-Dec-25 04:00 PM | 10.0d | 0.0d | 0 | 100%
A4670 | Detailed Third Party Review (Asset Management / Networ Ops) | 1158 | 970 | 188 | 1158 | 188 | 100% | 27-Nov-25 08:00 AM | 10-Dec-25 04:00 PM | 27-Dec-25 08:00 AM | 15-Dec-25 04:00 PM | 10.0d | 0.0d | 1158 | 100%
A4680 | Developed Design Review | 1304 | 1194 | 110 | 1304 | 110 | 100% | 11-Dec-25 08:00 AM | 11-Dec-25 04:00 PM | 10-Jan-26 08:00 AM | 14-Dec-25 04:00 PM | 1.0d | 0.0d | 1304 | 100%
A4770 | Specification and layouts for Tendering | 0 | 0 | 0 | 0 | 0 | 100% | 02-Sep-25 08:00 AM | 02-Sep-25 04:00 PM | 01-Nov-25 08:00 AM | 07-Sep-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4780 | Developed Design 3rd Party | 3178 | 2769 | 409 | 3178 | 409 | 100% | 15-Sep-25 08:00 AM | 10-Oct-25 04:00 PM | 15-Oct-25 08:00 AM | 12-Oct-25 04:00 PM | 20.0d | 0.0d | 3178 | 100%
A4790 | Developed Design - UKPN Internal | 0 | 0 | 0 | 0 | 0 | 100% | 15-Sep-25 08:00 AM | 10-Oct-25 04:00 PM | 14-Dec-25 08:00 AM | 13-Oct-25 04:00 PM | 20.0d | 0.0d | 0 | 100%
A4800 | Publish Developed Design Documents & Drawings/Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 15-Dec-25 08:00 AM | 15-Dec-25 04:00 PM | 15-Mar-26 08:00 AM | 20-Dec-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4810 | Surveys | 0 | 0 | 0 | 0 | 0 | 100% | 29-Aug-25 08:00 AM | 11-Sep-25 04:00 PM | 28-Sep-25 08:00 AM | 13-Sep-25 04:00 PM | 10.0d | 0.0d | 0 | 100%
A4930 | Risk & Value Intevention (AST 00 008) | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-25 08:00 AM | 13-Oct-25 04:00 PM | 11-Jan-26 08:00 AM | 16-Oct-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
A4940 | Risk & Value Intevention B-C | 3031 | 2499 | 532 | 3031 | 532 | 100% | 14-Oct-25 04:00 PM | 14-Oct-25 04:00 PM | 13-Nov-25 04:00 PM | 13-Nov-25 04:00 PM | 0.0d | 0.0d | 3031 | 100%
A4950 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 12-Sep-25 04:00 PM | 12-Sep-25 04:00 PM | 12-Oct-25 04:00 PM | 12-Oct-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
A5000 | Supplier Preliminary Drawings Preparation/Review | 0 | 0 | 0 | 0 | 0 | 100% | 16-Sep-25 08:00 AM | 10-Nov-25 04:00 PM | 16-Oct-25 08:00 AM | 15-Nov-25 04:00 PM | 40.0d | 30.0d | 0 | 100%
A5020 | Completion of Developed Design post Acceptance of anufacturer's Drawings | 3026 | 2556 | 470 | 3026 | 470 | 100% | 12-Nov-25 08:00 AM | 12-Nov-25 04:00 PM | 10-Feb-26 08:00 AM | 15-Nov-25 04:00 PM | 1.0d | 0.0d | 3026 | 100%
4 | Procurement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 04:00 PM | 30-Oct-25 08:00 AM | 06-Aug-25 04:00 PM | 1.0d | 0.0d | 0
PRC B-C-1000 | B-C Long Lead Procurement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 08:00 AM | 01-Aug-25 04:00 PM | 31-Aug-25 08:00 AM | 03-Aug-25 04:00 PM | 1.0d | 0.0d | 0 | 100%
5 | Gate C Governance | 0 | 0 | 0 | 0 | 0 | 100% | 15-Dec-25 08:00 AM | 06-Feb-26 04:00 PM | 14-Jan-26 08:00 AM |  | 34.0d |  | 0
A2754 | Review of ADP by PM and Project Team | 0 | 0 | 0 | 0 | 0 | 100% | 22-Dec-25 08:00 AM | 05-Jan-26 04:00 PM | 21-Jan-26 08:00 AM | 10-Jan-26 04:00 PM | 5.0d | 0.0d | 0 | 100%
Gate1031 | Prepare Gate C Paper | 1597 | 1444 | 153 | 1597 | 153 | 100% | 06-Jan-26 08:00 AM | 12-Jan-26 04:00 PM |  |  | 5.0d |  | 1597 | 100%
Gate1041 | Submit Gate C Paper to RPfB (AST 01 004 > £1m) | 1003 | 868 | 135 | 1003 | 135 | 100% | 23-Jan-26 04:00 PM | 23-Jan-26 04:00 PM |  |  | 0.0d |  | 1003 | 100%
Gate1035 | ADP Presentation at AMT | 0 | 0 | 0 | 0 | 0 | 100% | 19-Jan-26 08:00 AM | 19-Jan-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
A2753 | Risk Advisory Board (RAB) Revirew | 0 | 0 | 0 | 0 | 0 | 100% | 16-Jan-26 08:00 AM | 16-Jan-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
A2752 | Prepare Alliance Delivery Proposal (ADP) | 0 | 0 | 0 | 0 | 0 | 100% | 15-Dec-25 08:00 AM | 19-Dec-25 04:00 PM | 14-Jan-26 08:00 AM | 24-Dec-25 04:00 PM | 5.0d | 0.0d | 0 | 100%
Q3056 | Prepare WPO | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 06-Feb-26 04:00 PM |  |  | 10.0d |  | 0 | 100%
A4510 | Network Design Review (NDR) | 2899 | 2608 | 291 | 2899 | 291 | 100% | 13-Jan-26 08:00 AM | 13-Jan-26 04:00 PM |  |  | 1.0d |  | 2899 | 100%
A5140 | Gate C QRA Workshop | 0 | 0 | 0 | 0 | 0 | 100% | 23-Jan-26 08:00 AM | 23-Jan-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
4 | Gate C-D | 0 | 0 | 0 | 0 | 0 | 44.31% | 03-Feb-25 08:00 AM | 28-Jul-27 04:00 PM | 04-Apr-25 08:00 AM |  | 621.0d |  | 0
CONT100 | Contract Data - Start Date | 2533 | 2246 | 287 | 2533 | 287 | 100% | 06-Feb-26 04:00 PM | 06-Feb-26 04:00 PM |  |  | 0.0d |  | 2533 | 100%
CONT110 | Contract Data - Access Date (Date to be set as per contract info) | 2276 | 2090 | 186 | 2276 | 186 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 2276 | 100%
CONT130 | Contract Data - Key Date (Add as required)?? | 3329 | 2927 | 402 | 3329 | 402 | 100% | 06-Mar-26 04:00 PM | 06-Mar-26 04:00 PM |  |  | 0.0d |  | 3329 | 100%
CONT140 | Contract Data - Completion Date for the Whole of the Works | 2394 | 2190 | 204 | 2394 | 204 | 0% | 13-Nov-26 04:00 PM | 13-Nov-26 04:00 PM |  |  | 0.0d |  | 2394 | 0%
1 | Project Management | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
411 | Project Manager | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
PMC-D0001 | Indirect Project Mnagement C-D Cost Bar | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 236.0d |  | 0 | 13%
412 | Quantity Surveyor | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
PMC-D0004 | QS C-D Cost Bar | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 236.0d |  | 0 | 13%
413 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 235.0d |  | 0
PMC-D0002 | Project Planner C-D Cost Bar | 0 | 0 | 0 | 0 | 0 | 12.79% | 26-Jan-26 08:00 AM | 05-Jan-27 04:00 PM |  |  | 236.0d |  | 0 | 13%
3 | Procurement | 0 | 0 | 0 | 0 | 0 | 43.27% | 12-Nov-25 08:00 AM | 14-Aug-26 04:00 PM | 12-Dec-25 08:00 AM |  | 188.0d |  | 0
A5010 | Manufacture of Long Lead items | 0 | 0 | 0 | 0 | 0 | 79.87% | 12-Nov-25 08:00 AM | 10-Apr-26 04:00 PM | 10-Feb-26 08:00 AM |  | 100.0d |  | 0 | 80%
431 | Transformer Procurement | 0 | 0 | 0 | 0 | 0 | 43.27% | 12-Nov-25 08:00 AM | 14-Aug-26 04:00 PM | 12-Dec-25 08:00 AM |  | 188.0d |  | 0
PRC1210 | Transformers manufacture | 0 | 0 | 0 | 0 | 0 | 79.87% | 12-Nov-25 08:00 AM | 10-Apr-26 04:00 PM | 11-Jan-26 08:00 AM |  | 100.0d |  | 0 | 80%
A5070 | Transformers Delivery | 583 | 530 | 53 | 583 | 53 | 0% | 14-Aug-26 08:00 AM | 14-Aug-26 04:00 PM |  |  | 1.0d |  | 583 | 0%
432 | Switchgear Procurement | 0 | 0 | 0 | 0 | 0 | 43.27% | 12-Nov-25 08:00 AM | 14-Aug-26 04:00 PM | 10-Feb-26 08:00 AM |  | 188.0d |  | 0
PRC2030 | Switchgear Manufacture | 0 | 0 | 0 | 0 | 0 | 79.87% | 12-Nov-25 08:00 AM | 10-Apr-26 04:00 PM | 11-Jan-26 08:00 AM |  | 100.0d |  | 0 | 80%
A5080 | Switchgear Delivery | 0 | 0 | 0 | 0 | 0 | 0% | 14-Aug-26 08:00 AM | 14-Aug-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
434 | Cable & Materials Procurement | 0 | 0 | 0 | 0 | 0 | 74.38% | 12-Nov-25 08:00 AM | 21-Apr-26 04:00 PM | 12-Dec-25 08:00 AM |  | 107.0d |  | 0
PRC1190 | 11&33kV Cable & Materials manufacture | 2852 | 2512 | 340 | 2852 | 340 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 2852 | 52%
PRC1170 | 132kV Cable Accessories & Jointing manufacture | 0 | 0 | 0 | 0 | 0 | 100% | 12-Nov-25 08:00 AM | 11-Feb-26 04:00 PM | 10-Feb-26 08:00 AM |  | 60.0d |  | 0 | 100%
436 | Relay Panels Procurement | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0
PRC1000 | Relay panels manufacture | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0 | 52%
437 | Overhead Lines Procurement | 0 | 0 | 0 | 0 | 0 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 0
PRC1090 | OHL manufacture | 1400 | 1248 | 152 | 1400 | 152 | 51.76% | 26-Jan-26 08:00 AM | 21-Apr-26 04:00 PM |  |  | 60.0d |  | 1400 | 52%
2 | Design / Surveys / OP&C Gate C-D | 0 | 0 | 0 | 0 | 0 | 12.83% | 26-Jan-26 08:00 AM | 04-Jan-27 04:00 PM |  |  | 234.0d |  | 0
PMC-D1960 | Design C-D Cost Bar | 2421 | 2106 | 315 | 2421 | 315 | 15.12% | 26-Jan-26 08:00 AM | 13-Nov-26 04:00 PM |  |  | 205.0d |  | 2421 | 15%
A4700 | Technical Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 09-Feb-26 08:00 AM | 09-Feb-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
A4710 | Technical design using Manufacture drawings (Major plant like Transformer, Switchgear etc) | 3193 | 2883 | 310 | 3193 | 310 | 18.62% | 12-Feb-26 08:00 AM | 07-Jul-26 04:00 PM |  |  | 100.0d |  | 3193 | 19%
A4720 | Technical design using equipment Specified/ordered post gate C | 0 | 0 | 0 | 0 | 0 | 18.62% | 12-Feb-26 08:00 AM | 07-Jul-26 04:00 PM |  |  | 100.0d |  | 0 | 19%
A4730 | As-Build Drawings review | 937 | 820 | 117 | 937 | 117 | 0% | 21-Dec-26 08:00 AM | 04-Jan-27 04:00 PM |  |  | 5.0d |  | 937 | 0%
A4820 | Design Support to Construction team (TQs and Troubleshooting) | 0 | 0 | 0 | 0 | 0 | 17.65% | 12-Feb-26 12:00 PM | 15-Jul-26 12:00 PM |  |  | 105.0d |  | 0 | 18%
A4830 | Design issued for Construction - Handover to Construction Team | 884 | 804 | 80 | 884 | 80 | 100% | 11-Feb-26 04:00 PM | 11-Feb-26 04:00 PM |  |  | 0.0d |  | 884 | 100%
A4840 | Update post construction drawing (Internal Design) | 861 | 770 | 91 | 861 | 91 | 0% | 23-Nov-26 08:00 AM | 18-Dec-26 04:00 PM |  |  | 20.0d |  | 861 | 0%
A4850 | As built drawing received from Supplier | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 08:00 AM | 19-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4860 | Technical Design Complete | 0 | 0 | 0 | 0 | 0 | 0% | 15-Jul-26 12:00 PM | 15-Jul-26 12:00 PM |  |  | 0.0d |  | 0 | 0%
A4870 | As built drawing received from Site | 0 | 0 | 0 | 0 | 0 | 0% | 16-Nov-26 08:00 AM | 20-Nov-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
A4880 | As built drawing received from Commissioning team | 2112 | 1831 | 281 | 2112 | 281 | 0% | 16-Nov-26 08:00 AM | 20-Nov-26 04:00 PM |  |  | 5.0d |  | 2112 | 0%
A4960 | Pre-Construction Information - PCI Documentation ((CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 10-Feb-26 04:00 PM | 10-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
A4970 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 0% | 30-Mar-26 04:00 PM | 30-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A5050 | Request protection settings | 0 | 0 | 0 | 0 | 0 | 100% | 12-Feb-26 08:00 AM | 13-Feb-26 04:00 PM |  |  | 2.0d |  | 0 | 100%
A5060 | Protection Settings | 1324 | 1120 | 204 | 1324 | 204 | 58.97% | 16-Feb-26 08:00 AM | 27-Mar-26 04:00 PM |  |  | 30.0d |  | 1324 | 59%
4 | Construction | 0 | 0 | 0 | 0 | 0 | 44.31% | 03-Feb-25 08:00 AM | 28-Jul-27 04:00 PM | 05-Mar-25 08:00 AM |  | 621.0d |  | 0
A4480 | Direct Costs 2020 | 2257 | 1905 | 352 | 2257 | 352 | 100% | 03-Feb-25 08:00 AM | 31-Jul-25 04:00 PM | 04-May-25 08:00 AM | 05-Aug-25 04:00 PM | 125.0d | 93.0d | 2257 | 100%
A4490 | Direct Costs 2021 | 2573 | 2273 | 300 | 2573 | 300 | 60.99% | 01-Aug-25 08:00 AM | 31-Jul-26 04:00 PM | 30-Oct-25 08:00 AM |  | 250.0d |  | 2573 | 61%
A4500 | Direct Costs 2022 | 0 | 0 | 0 | 0 | 0 | 0% | 03-Aug-26 08:00 AM | 28-Jul-27 04:00 PM |  |  | 247.0d |  | 0 | 0%
441 | Site Pre Start (Enabling Works) | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 20-Feb-26 04:00 PM |  |  | 20.0d |  | 0
A1980 | Prepare Construction Phase Plan | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 30-Jan-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
A1990 | Prepare Issue F10 | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 30-Jan-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
A2000 | Setup Health & safety File | 0 | 0 | 0 | 0 | 0 | 100% | 26-Jan-26 08:00 AM | 30-Jan-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
PS4480 | Site Access | 0 | 0 | 0 | 0 | 0 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
442 | Mobilisation | 0 | 0 | 0 | 0 | 0 | 100% | 02-Feb-26 08:00 AM | 20-Feb-26 04:00 PM |  |  | 15.0d |  | 0
T2650 | Mobilisation of Principle Contractor | 1132 | 1014 | 118 | 1132 | 118 | 100% | 02-Feb-26 08:00 AM | 20-Feb-26 04:00 PM |  |  | 15.0d |  | 1132 | 100%
443 | Outages | 0 | 0 | 0 | 0 | 0 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 0
OUT1920 | Outage 1 | 2339 | 2039 | 300 | 2339 | 300 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 2339 | 100%
OUT1930 | Outage 2 | 1301 | 1148 | 153 | 1301 | 153 | 100% | 23-Feb-26 08:00 AM | 23-Feb-26 08:00 AM |  |  | 0.0d |  | 1301 | 100%
444 | Building Civils & Fit Out Contract | 0 | 0 | 0 | 0 | 0 | 10.92% | 20-Feb-26 04:00 PM | 13-Aug-26 04:00 PM |  |  | 120.0d |  | 0
CONS-14260 | Civils Start Date | 1931 | 1635 | 296 | 1931 | 296 | 100% | 20-Feb-26 04:00 PM | 20-Feb-26 04:00 PM |  |  | 0.0d |  | 1931 | 100%
A5100 | Building works | 3099 | 2564 | 535 | 3099 | 535 | 9.36% | 23-Feb-26 08:00 AM | 13-Aug-26 04:00 PM |  |  | 120.0d |  | 3099 | 9%
A5110 | Switchroom Water Tight | 0 | 0 | 0 | 0 | 0 | 0% | 13-Aug-26 04:00 PM | 13-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A5120 | Transformer Bay ready for delivery | 0 | 0 | 0 | 0 | 0 | 0% | 13-Aug-26 04:00 PM | 13-Aug-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
445 | Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 05-Nov-26 04:00 PM |  |  | 58.0d |  | 0
CONS-13730 | Install Transformer | 2933 | 2488 | 445 | 2933 | 445 | 0% | 17-Aug-26 08:00 AM | 14-Sep-26 04:00 PM |  |  | 20.0d |  | 2933 | 0%
CONS-3740 | Install TX Transformer Tails | 0 | 0 | 0 | 0 | 0 | 0% | 15-Sep-26 08:00 AM | 17-Sep-26 04:00 PM |  |  | 3.0d |  | 0 | 0%
CONS-3750 | Install Transformer Protection Panels & AVC | 0 | 0 | 0 | 0 | 0 | 0% | 18-Sep-26 08:00 AM | 24-Sep-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
CONS-3760 | Cold Commission Transformer | 820 | 694 | 126 | 820 | 126 | 0% | 25-Sep-26 08:00 AM | 15-Oct-26 04:00 PM |  |  | 15.0d |  | 820 | 0%
CONS-14170 | Transformer Installation Planned Completion | 0 | 0 | 0 | 0 | 0 | 0% | 19-Oct-26 04:00 PM | 19-Oct-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
A3070 | Hot commissioning of Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 16-Oct-26 08:00 AM | 05-Nov-26 04:00 PM |  |  | 15.0d |  | 0 | 0%
446 | Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 16-Nov-26 04:00 PM |  |  | 65.0d |  | 0
CONS-1830 | Install 11kV Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 14-Sep-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
CONS-3840 | Install Multicores & Terminate | 0 | 0 | 0 | 0 | 0 | 0% | 15-Sep-26 08:00 AM | 21-Sep-26 04:00 PM |  |  | 5.0d |  | 0 | 0%
CONS-13850 | Cold Commission 11/6.6kV Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 22-Sep-26 08:00 AM | 19-Oct-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
CONS-14200 | 11/6.6kV Switchgear Installation Planned Completion | 1748 | 1489 | 259 | 1748 | 259 | 0% | 19-Oct-26 04:00 PM | 19-Oct-26 04:00 PM |  |  | 0.0d |  | 1748 | 0%
CONS-14210 | 11/6.6kV Switchgear Installation Planned Start | 1337 | 1168 | 169 | 1337 | 169 | 0% | 17-Aug-26 08:00 AM | 17-Aug-26 08:00 AM |  |  | 0.0d |  | 1337 | 0%
A2570 | Switchgear Install Cost | 0 | 0 | 0 | 0 | 0 | 0% | 17-Aug-26 08:00 AM | 16-Nov-26 04:00 PM |  |  | 65.0d |  | 0 | 0%
A3080 | Hot commissioning of Switchgear | 571 | 476 | 95 | 571 | 95 | 0% | 20-Oct-26 08:00 AM | 16-Nov-26 04:00 PM |  |  | 20.0d |  | 571 | 0%
447 | Overhead Lines | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-26 08:00 AM | 22-Apr-26 08:00 AM |  |  | 0.0d |  | 0
CONS-14250 | Overhead Lines Installation Planned Start | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-26 08:00 AM | 22-Apr-26 08:00 AM |  |  | 0.0d |  | 0 | 0%
448 | Cable Install | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-26 08:00 AM | 05-Jun-26 04:00 PM |  |  | 31.0d |  | 0
CONS-5720 | Cable Installation Planned Start | 2723 | 2295 | 428 | 2723 | 428 | 0% | 22-Apr-26 08:00 AM | 22-Apr-26 08:00 AM |  |  | 0.0d |  | 2723 | 0%
CONS-14150 | Cable Installation Planned Completion | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jun-26 04:00 PM | 05-Jun-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CONS-14160 | Cable Installation Contract Completion Date | 2347 | 2087 | 260 | 2347 | 260 | 0% | 05-Jun-26 04:00 PM | 05-Jun-26 04:00 PM |  |  | 0.0d |  | 2347 | 0%
T13940 | Install 11kV Cabling | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-26 08:00 AM | 20-May-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
T13950 | Cable Sheath Tests | 1295 | 1153 | 142 | 1295 | 142 | 0% | 21-May-26 08:00 AM | 28-May-26 04:00 PM |  |  | 5.0d |  | 1295 | 0%
T13960 | Joint & Terminate Cables | 2639 | 2180 | 459 | 2639 | 459 | 0% | 29-May-26 08:00 AM | 04-Jun-26 04:00 PM |  |  | 5.0d |  | 2639 | 0%
T13970 | 11kV Pressure Tests | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jun-26 08:00 AM | 05-Jun-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
449 | Test & Commissioning | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 13-Nov-26 04:00 PM |  |  | 19.0d |  | 0
TC4890 | SAP Updated | 0 | 0 | 0 | 0 | 0 | 0% | 21-Oct-26 08:00 AM | 21-Oct-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
TC4900 | Netmap Updated | 2108 | 1813 | 295 | 2108 | 295 | 0% | 21-Oct-26 08:00 AM | 21-Oct-26 04:00 PM |  |  | 1.0d |  | 2108 | 0%
CLO130 | Demobilise from site | 0 | 0 | 0 | 0 | 0 | 0% | 13-Nov-26 08:00 AM | 13-Nov-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A2940 | Hot Commissioning of Substation | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 20-Oct-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
A2950 | Energisation | 1760 | 1538 | 222 | 1760 | 222 | 0% | 06-Nov-26 08:00 AM | 12-Nov-26 04:00 PM |  |  | 5.0d |  | 1760 | 0%
A3060 | Protection Settings uploaded | 588 | 506 | 82 | 588 | 82 | 0% | 20-Oct-26 04:00 PM | 20-Oct-26 04:00 PM |  |  | 0.0d |  | 588 | 0%
A4450 | Substation Under Rules | 772 | 649 | 123 | 772 | 123 | 0% | 21-Oct-26 08:00 AM | 21-Oct-26 04:00 PM |  |  | 1.0d |  | 772 | 0%
6 | Closure | 0 | 0 | 0 | 0 | 0 | 0% | 20-Oct-26 08:00 AM | 11-Jun-27 04:00 PM |  |  | 158.0d |  | 0
CLO3100 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jan-27 08:00 AM | 05-Jan-27 04:00 PM |  |  | 1.0d |  | 0 | 0%
CLO120 | Review and Approve H&S File | 3037 | 2617 | 420 | 3037 | 420 | 0% | 20-Oct-26 08:00 AM | 02-Nov-26 04:00 PM |  |  | 10.0d |  | 3037 | 0%
CLO14150 | Financial Closure | 0 | 0 | 0 | 0 | 0 | 0% | 16-Nov-26 08:00 AM | 13-May-27 04:00 PM |  |  | 120.0d |  | 0 | 0%
CLO15940 | Familiarisation Training | 3095 | 2817 | 278 | 3095 | 278 | 0% | 13-Nov-26 08:00 AM | 26-Nov-26 04:00 PM |  |  | 10.0d |  | 3095 | 0%
A4460 | Deadline for submission of defined costs (65 days from contract completion) | 0 | 0 | 0 | 0 | 0 | 0% | 11-Dec-26 04:00 PM | 11-Dec-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-27 08:00 AM | 11-Jun-27 04:00 PM |  |  | 20.0d |  | 0
Gate1070 | Prepare Gate D Paper | 2091 | 1836 | 255 | 2091 | 255 | 0% | 14-May-27 08:00 AM | 11-Jun-27 04:00 PM |  |  | 20.0d |  | 2091 | 0%
Gate1080 | Submit Gate D Paper to RPrB (AST 01 004 > £1m) | 2901 | 2143 | 758 | 2901 | 758 | 0% | 11-Jun-27 04:00 PM | 11-Jun-27 04:00 PM |  |  | 0.0d |  | 2901 | 0%