## Sheet1
Activity ID* | Activity Name* | BL Project Total Cost | Actual Total Cost | Remaining Total Cost | At Completion Total Cost | Variance BL Project - Total Cost | Performance % Complete | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Duration | Actual Duration | Planned Total Cost | Activity % Complete
X-E.IPP.107801 | Green Recovery - EPN EV Fuel Stations (Howe Green) | 766652 | 793236 | 4559 | 797795 | (31,083) | 94.78% | 06-May-22 08:00 AM | 16-Dec-24 04:00 PM | 23-Aug-22 08:00 AM |  | 655.0d | 440.0d | 766716
1 | Project Summary | 0 | 0 | 0 | 0 | 0 | 0% | 06-May-22 08:00 AM | 18-Nov-24 04:00 PM | 23-Aug-22 08:00 AM |  | 635.0d | 380.0d | 0
6 | Project Governance Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 06-May-22 08:00 AM | 30-Jul-24 04:00 PM | 23-Aug-22 08:00 AM |  | 557.0d | 245.0d | 0
Gate1010 | Gate B Award | 0 | 0 | 0 | 0 | 0 | 100% | 06-May-22 08:00 AM | 06-May-22 08:00 AM | 23-Aug-22 08:00 AM | 23-Aug-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1020 | Gate C Award | 0 | 0 | 0 | 0 | 0 | 100% | 11-Aug-23 04:00 PM | 11-Aug-23 04:00 PM | 17-Aug-23 04:00 PM | 17-Aug-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
Gate1050 | Gate D Award | 0 | 0 | 0 | 0 | 0 | 0% | 30-Jul-24 04:00 PM | 30-Jul-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
9 | Construction Delivery Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 09-Sep-22 08:00 AM | 27-Mar-24 04:00 PM | 09-Sep-22 08:00 AM | 29-Feb-24 04:00 PM | 385.0d | 366.0d | 0
DEL1050 | Start on Site | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 01-Sep-23 08:00 AM | 01-Sep-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1130 | Customer (MC or APP) Energisation available | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 04:00 PM | 04-Mar-24 04:00 PM | 02-Feb-24 04:00 PM | 02-Feb-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1140 | Site Demobilisation Complete | 0 | 0 | 0 | 0 | 0 | 100% | 29-Feb-24 04:00 PM | 29-Feb-24 04:00 PM | 29-Feb-24 04:00 PM | 29-Feb-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1070 | Practical Completion | 0 | 0 | 0 | 0 | 0 | 100% | 27-Mar-24 04:00 PM | 27-Mar-24 04:00 PM | 29-Feb-24 04:00 PM | 29-Feb-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1010 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Sep-22 08:00 AM | 09-Sep-22 08:00 AM | 09-Sep-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1000 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Sep-22 08:00 AM | 09-Sep-22 08:00 AM | 09-Sep-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
DEL1030 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building/Route/Earthing/Component) | 0 | 0 | 0 | 0 | 0 | 100% | 13-Feb-23 04:00 PM | 13-Feb-23 04:00 PM | 13-Feb-23 04:00 PM | 13-Feb-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1040 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 31-Jul-23 04:00 PM | 31-Jul-23 04:00 PM | 31-Jul-23 04:00 PM | 31-Jul-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1020 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 04:00 PM | 09-Sep-22 04:00 PM | 09-Sep-22 04:00 PM | 09-Sep-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1150 | Customer Required By energisation date | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 04:00 PM | 04-Mar-24 04:00 PM | 28-Feb-24 04:00 PM | 28-Feb-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
8 | Asset Registration/Update Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 01-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 01-Aug-23 08:00 AM | 04-Mar-24 04:00 PM | 2.0d | 148.0d | 0
ASS1040 | Asset Data - Updated (Netmap - Cable records) 66/11kV UG Cable | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 04:00 PM | 04-Mar-24 04:00 PM | 04-Mar-24 04:00 PM | 04-Mar-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
ASS1000 | Asset Data - Registration (Netmap) | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 01-Aug-23 08:00 AM | 01-Aug-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
7 | Project Closeout Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 27-Mar-24 04:00 PM | 18-Nov-24 04:00 PM | 29-Feb-24 04:00 PM |  | 163.0d | 1.0d | 0
CLO1000 | Project Completion | 0 | 0 | 0 | 0 | 0 | 0% | 30-Jul-24 04:00 PM | 30-Jul-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
CLO1020 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 30-Jul-24 04:00 PM | 30-Jul-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
CLO1030 | Financial Close | 0 | 0 | 0 | 0 | 0 | 0% | 18-Nov-24 04:00 PM | 18-Nov-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
CLO1050 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 27-Mar-24 04:00 PM | 27-Mar-24 04:00 PM | 29-Feb-24 04:00 PM | 29-Feb-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
CLO1010 | Completion Certificate Signed off | 0 | 0 | 0 | 0 | 0 | 100% | 26-Apr-24 04:00 PM | 26-Apr-24 04:00 PM | 01-Mar-24 04:00 PM | 01-Mar-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
CLO1060 | Completion of the Health and Safety File | 0 | 0 | 0 | 0 | 0 | 100% | 09-Apr-24 04:00 PM | 09-Apr-24 04:00 PM | 29-Feb-24 04:00 PM | 29-Feb-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
1 | Project Specific Milestones - Inc. Contract Data | 0 | 0 | 0 | 0 | 0 | 0% | 01-Aug-23 04:00 PM | 01-Aug-23 04:00 PM | 01-Aug-23 04:00 PM | 01-Aug-23 04:00 PM | 0.0d | 0.0d | 0
ProjKM1020 | Project Consents Executed | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-23 04:00 PM | 01-Aug-23 04:00 PM | 01-Aug-23 04:00 PM | 01-Aug-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
TASK DESIGN DELIVERY MILESTONES | TASK DESIGN DELIVERY MILESTONES (DO NOT DELETE or CHANGE ACTIVITY ID) | 0 | 0 | 0 | 0 | 0 | 0% | 09-Sep-22 08:00 AM | 19-Apr-24 12:00 PM | 09-Sep-22 08:00 AM | 04-Mar-24 04:00 PM | 399.5d | 368.0d | 0
DES-DM1 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM2 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 01-Feb-23 08:00 AM | 01-Feb-23 04:00 PM | 01-Feb-23 08:00 AM | 01-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM3 | Risk & Value Intevention A-B | 0 | 0 | 0 | 0 | 0 | 100% | 01-Feb-23 08:00 AM | 01-Feb-23 04:00 PM | 01-Feb-23 08:00 AM | 01-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM4 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM5 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM6 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 10-Feb-23 08:00 AM | 10-Feb-23 04:00 PM | 10-Feb-23 08:00 AM | 10-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM7 | Suppliers's Drawings accepted by UKPN (Manufacture/ Building / Route / Earthing / Component) | 0 | 0 | 0 | 0 | 0 | 100% | 13-Feb-23 08:00 AM | 13-Feb-23 04:00 PM | 13-Feb-23 08:00 AM | 13-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM8 | Risk & Value Intevention B-C | 0 | 0 | 0 | 0 | 0 | 100% | 28-Jul-23 08:00 AM | 28-Jul-23 04:00 PM | 28-Jul-23 08:00 AM | 28-Jul-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM9 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM11 | Pre-Construction Information - PCI Documentation (CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 01-Dec-23 08:00 AM | 01-Dec-23 04:00 PM | 01-Dec-23 08:00 AM | 01-Mar-24 04:00 PM | 1.0d | 60.0d | 0 | 100%
DES-DM12 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 01-Dec-23 12:00 PM | 04-Dec-23 12:00 PM | 01-Aug-23 12:00 PM | 02-Aug-23 12:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM13 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 100% | 18-Apr-24 12:00 PM | 19-Apr-24 12:00 PM | 15-Sep-23 12:00 PM | 18-Sep-23 12:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM14 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 27-Mar-24 08:00 AM | 27-Mar-24 04:00 PM | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
3 | Gate B-C | 76631 | 61068 | 0 | 61068 | 15562 | 100% | 09-Sep-22 08:00 AM | 21-Nov-23 04:00 PM | 09-Sep-22 08:00 AM | 19-Dec-23 04:00 PM | 300.0d | 320.0d | 76631
A2780 | B to C Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 09-Sep-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
A2790 | Update PEP, Formalise AIP & Appendix B, Set Target Budget | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 5.0d | 5.0d | 0 | 100%
A2800 | Review of Target Budget and sign off | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 13-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 13-Sep-22 04:00 PM | 3.0d | 3.0d | 0 | 100%
A3046 | Mobilise | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 5.0d | 5.0d | 0 | 100%
A3030 | Prepare PSC | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 5.0d | 5.0d | 0 | 100%
A3040 | PSC Review period | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 5.0d | 5.0d | 0 | 100%
A3035 | Finalise PSC | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 13-Sep-22 04:00 PM | 09-Sep-22 08:00 AM | 13-Sep-22 04:00 PM | 3.0d | 3.0d | 0 | 100%
1 | Project Management | 6498 | 6522 | 0 | 6522 | (24) | 100% | 09-Sep-22 08:00 AM | 01-Mar-23 09:00 AM | 09-Sep-22 08:00 AM | 31-Aug-23 04:00 PM | 116.1d | 242.0d | 6498
1 | Project Manager | 5483 | 5507 | 0 | 5507 | (24) | 100% | 09-Sep-22 08:00 AM | 01-Mar-23 09:00 AM | 09-Sep-22 08:00 AM | 31-Jul-23 04:00 PM | 116.1d | 220.0d | 5483
PMB-C2120 | Indirect Project Manager B-C Cost Bar | 3904 | 3904 | 0 | 3904 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Feb-23 04:00 PM | 09-Sep-22 08:00 AM | 31-Jul-23 04:00 PM | 103.0d | 220.0d | 3904 | 100%
A5270 | Clancy Indirect Costs | 1579 | 1603 | 0 | 1603 | (24) | 100% | 01-Mar-23 08:00 AM | 01-Mar-23 09:00 AM | 05-Dec-22 08:00 AM | 31-Jul-23 09:00 AM | 0.1d | 159.1d | 1579 | 100%
2 | Quantity Surveyor | 1015 | 1015 | 0 | 1015 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Feb-23 04:00 PM | 09-Sep-22 08:00 AM | 31-Jul-23 04:00 PM | 103.0d | 220.0d | 1015
PMB-C2140 | QS B-C Cost Bar | 1015 | 1015 | 0 | 1015 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Feb-23 04:00 PM | 09-Sep-22 08:00 AM | 31-Jul-23 04:00 PM | 103.0d | 220.0d | 1015 | 100%
3 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 0% | 09-Sep-22 08:00 AM | 09-Feb-23 04:00 PM | 09-Sep-22 08:00 AM | 31-Aug-23 04:00 PM | 103.0d | 242.0d | 0
PMB-C2130 | Project Planner B-C Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 09-Feb-23 04:00 PM | 09-Sep-22 08:00 AM | 31-Aug-23 04:00 PM | 103.0d | 242.0d | 0 | 100%
2 | Design / Surveys / OP&C | 70132 | 54546 | 0 | 54546 | 15586 | 100% | 09-Sep-22 08:00 AM | 21-Nov-23 04:00 PM | 09-Sep-22 08:00 AM | 19-Dec-23 04:00 PM | 300.0d | 320.0d | 70132
OP&C2010 | Wayleaves/Consents Approval | 0 | 0 | 0 | 0 | 0 | 100% | 31-Jul-23 08:00 AM | 01-Aug-23 04:00 PM | 31-Jul-23 08:00 AM | 01-Aug-23 04:00 PM | 2.0d | 2.0d | 0 | 100%
PMB-C2020 | Principal Design Co-ordinator/SHES - Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 09-Sep-22 08:00 AM | 28-Feb-23 04:00 PM | 09-Sep-22 08:00 AM | 31-Jul-23 08:00 AM | 116.0d | 219.0d | 0 | 100%
DESIGNB-C-0001 | Design B-C Cost Bar | 50047 | 34564 | 0 | 34564 | 15482 | 100% | 09-Sep-22 08:00 AM | 09-Feb-23 04:00 PM | 09-Sep-22 08:00 AM | 17-Aug-23 04:00 PM | 103.0d | 233.0d | 50047 | 100%
A2360 | SAP/Commissioning Engineer/Project Engineer Early Engagement | 0 | 0 | 0 | 0 | 0 | 100% | 13-Feb-23 08:00 AM | 13-Feb-23 04:00 PM | 13-Feb-23 08:00 AM | 13-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4620 | Developed Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Nov-22 08:00 AM | 01-Nov-22 04:00 PM | 01-Nov-22 08:00 AM | 01-Nov-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4630 | Prepare Developed design PSC | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-23 08:00 AM | 03-Feb-23 04:00 PM | 03-Feb-23 08:00 AM | 03-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4640 | Order Placed/Request Supplier Preliminary Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 03-Aug-23 08:00 AM | 03-Aug-23 08:00 AM | 03-Aug-23 08:00 AM | 03-Aug-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4680 | Developed Design Review | 0 | 0 | 0 | 0 | 0 | 100% | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4770 | Specification and layouts for Tendering | 0 | 0 | 0 | 0 | 0 | 100% | 02-Feb-23 08:00 AM | 02-Feb-23 04:00 PM | 02-Feb-23 08:00 AM | 02-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4780 | Developed Design 3rd Party | 0 | 0 | 0 | 0 | 0 | 100% | 13-Feb-23 08:00 AM | 24-Feb-23 04:00 PM | 01-Nov-22 08:00 AM | 01-Aug-23 08:00 AM | 10.0d | 184.0d | 0 | 100%
A4790 | Developed Design - Freedom | 0 | 0 | 0 | 0 | 0 | 100% | 01-Nov-22 08:00 AM | 14-Nov-22 04:00 PM | 01-Nov-22 08:00 AM | 31-Jul-23 08:00 AM | 10.0d | 183.0d | 0 | 100%
A4800 | Publish Developed Design Documents & Drawings/Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4810 | Surveys | 0 | 0 | 0 | 0 | 0 | 100% | 03-Feb-23 08:00 AM | 09-Feb-23 04:00 PM | 03-Feb-23 08:00 AM | 09-Feb-23 04:00 PM | 5.0d | 5.0d | 0 | 100%
A4930 | Risk & Value Intevention (AST 00 008) | 0 | 0 | 0 | 0 | 0 | 100% | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4940 | Risk & Value Intevention B-C | 0 | 0 | 0 | 0 | 0 | 100% | 28-Jul-23 04:00 PM | 28-Jul-23 04:00 PM | 28-Jul-23 04:00 PM | 28-Jul-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
A4950 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 10-Feb-23 08:00 AM | 10-Feb-23 04:00 PM | 10-Feb-23 08:00 AM | 10-Feb-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
T13940 | Freedom Design Costs | 104 | 0 | 0 | 0 | 104 | 100% | 02-May-23 08:00 AM | 21-Nov-23 04:00 PM | 03-Jul-23 08:00 AM | 19-Dec-23 04:00 PM | 143.0d | 121.0d | 104 | 100%
A5150 | Freedom Costs November 2022 | 19982 | 19982 | 0 | 19982 | 0 | 100% | 01-Nov-22 08:00 AM | 01-Nov-22 09:00 AM | 01-Nov-22 08:00 AM | 01-Nov-22 09:00 AM | 0.1d | 0.1d | 19982 | 100%
4 | Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 1.0d | 1.0d | 0
PRC B-C-1000 | B-C Long Lead Procurement | 0 | 0 | 0 | 0 | 0 | 100% | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 31-Jul-23 08:00 AM | 31-Jul-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
5 | Gate C Governance | 0 | 0 | 0 | 0 | 0 | 0% | 27-Jul-23 08:00 AM | 06-Oct-23 04:00 PM | 27-Jul-23 08:00 AM | 29-Sep-23 04:00 PM | 51.0d | 46.0d | 0
Gate1031 | Prepare Gate C Paper | 0 | 0 | 0 | 0 | 0 | 100% | 27-Jul-23 08:00 AM | 02-Aug-23 04:00 PM | 27-Jul-23 08:00 AM | 02-Aug-23 04:00 PM | 5.0d | 5.0d | 0 | 100%
Gate1041 | Submit Gate C Paper to RPfB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-23 04:00 PM | 04-Aug-23 04:00 PM | 04-Aug-23 04:00 PM | 04-Aug-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
Gate1035 | ADP Presentation at AMT | 0 | 0 | 0 | 0 | 0 | 100% | 11-Aug-23 08:00 AM | 11-Aug-23 04:00 PM | 11-Aug-23 08:00 AM | 11-Aug-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A2753 | Risk Advisory Board (RAB) Revirew | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-23 08:00 AM | 04-Aug-23 04:00 PM | 04-Aug-23 08:00 AM | 04-Aug-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
Q3056 | Prepare WPO | 0 | 0 | 0 | 0 | 0 | 100% | 02-Oct-23 08:00 AM | 06-Oct-23 04:00 PM | 15-Sep-23 08:00 AM | 29-Sep-23 04:00 PM | 5.0d | 11.0d | 0 | 100%
A4510 | Network Design Review (NDR) | 0 | 0 | 0 | 0 | 0 | 100% | 08-Aug-23 08:00 AM | 08-Aug-23 04:00 PM | 02-Aug-23 08:00 AM | 02-Aug-23 04:00 PM | 1.0d | 0.0d | 0 | 100%
A5140 | Gate C QRA Workshop | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-23 08:00 AM | 04-Aug-23 04:00 PM | 04-Aug-23 08:00 AM | 04-Aug-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
4 | Gate C-D | 690021 | 732168 | 4559 | 736726 | (46,646) | 94.2% | 01-Feb-23 08:00 AM | 16-Dec-24 04:00 PM | 01-Feb-23 08:00 AM |  | 472.0d | 332.0d | 690086
1 | Project Management | 38172 | 27668 | 4559 | 32227 | 5945 | 56.01% | 18-Aug-23 08:00 AM | 29-Aug-24 04:00 PM | 17-Aug-23 08:00 AM |  | 258.0d | 196.0d | 38172
411 | Project Manager | 29172 | 15034 | 4559 | 19593 | 9579 | 46.3% | 18-Aug-23 08:00 AM | 29-Aug-24 04:00 PM | 17-Aug-23 08:00 AM |  | 258.0d | 196.0d | 29172
PMC-D0001 | Indirect Project Manager C-D Cost Bar | 4500 | 6896 | 0 | 6896 | (2,396) | 100% | 18-Aug-23 08:00 AM | 17-Jun-24 04:00 PM | 17-Aug-23 04:00 PM | 30-May-24 04:00 PM | 206.0d | 194.0d | 4500 | 100%
A5300 | Other Project Management Costs | 24672 | 8138 | 4559 | 12697 | 11975 | 36.5% | 01-Nov-23 08:00 AM | 29-Aug-24 04:00 PM | 17-Aug-23 08:00 AM |  | 206.0d | 196.0d | 24672 | 36.5%
412 | Quantity Surveyor | 4500 | 2747 | 0 | 2747 | 1753 | 80% | 18-Aug-23 08:00 AM | 17-Jun-24 04:00 PM | 17-Aug-23 04:00 PM |  | 206.0d | 195.0d | 4500
PMC-D0004 | QS C-D Cost Bar | 4500 | 2747 | 0 | 2747 | 1753 | 80% | 18-Aug-23 08:00 AM | 17-Jun-24 04:00 PM | 17-Aug-23 04:00 PM |  | 206.0d | 195.0d | 4500 | 80%
413 | P6 Planner | 4500 | 9887 | 0 | 9887 | (5,387) | 95% | 18-Aug-23 08:00 AM | 17-Jun-24 04:00 PM | 17-Aug-23 04:00 PM |  | 206.0d | 195.0d | 4500
PMC-D0002 | Project Planner C-D Cost Bar | 4500 | 9887 | 0 | 9887 | (5,387) | 95% | 18-Aug-23 08:00 AM | 17-Jun-24 04:00 PM | 17-Aug-23 04:00 PM |  | 206.0d | 195.0d | 4500 | 95%
3 | Procurement | 115482 | 30664 | 0 | 30664 | 84818 | 100% | 01-Nov-23 08:00 AM | 03-Apr-24 04:00 PM | 01-Aug-23 08:00 AM | 06-Oct-23 08:00 AM | 103.0d | 47.0d | 115482
A5010 | Manufacture of Long Lead items | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 03-Apr-24 04:00 PM | 01-Aug-23 08:00 AM | 14-Aug-23 04:00 PM | 22.0d | 10.0d | 0 | 100%
434 | Cable & Materials Procurement | 115482 | 30664 | 0 | 30664 | 84818 | 100% | 01-Nov-23 08:00 AM | 01-Mar-24 04:00 PM | 02-Oct-23 08:00 AM | 06-Oct-23 08:00 AM | 82.0d | 4.0d | 115482
PRC1190 | 11&33kV Cable & Materials manufacture | 115482 | 30664 | 0 | 30664 | 84818 | 100% | 01-Nov-23 08:00 AM | 01-Mar-24 04:00 PM | 02-Oct-23 08:00 AM | 06-Oct-23 08:00 AM | 82.0d | 4.0d | 115482 | 100%
2 | Design / Surveys / OP&C Gate C-D | 0 | 0 | 0 | 0 | 0 | 0% | 18-Aug-23 08:00 AM | 02-Aug-24 04:00 PM | 01-Aug-23 08:00 AM |  | 240.0d | 208.0d | 0
PMC-D1960 | Design C-D Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 18-Aug-23 08:00 AM | 01-May-24 04:00 PM | 17-Aug-23 04:00 PM |  | 175.0d | 195.0d | 0 | 100%
A4700 | Technical Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 04:00 PM | 01-Aug-23 08:00 AM | 01-Aug-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A4710 | Technical design using Manufacture drawings (Major plant like Transformer, Switchgear etc) | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 12:00 PM | 05-Mar-24 12:00 PM | 02-Aug-23 12:00 PM | 03-Aug-23 12:00 PM | 1.0d | 1.0d | 0 | 100%
A4720 | Technical design using equipment Specified/ordered post gate C | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 12:00 PM | 05-Mar-24 12:00 PM | 02-Aug-23 12:00 PM | 03-Aug-23 12:00 PM | 1.0d | 1.0d | 0 | 100%
A4730 | As-Build Drawings review | 0 | 0 | 0 | 0 | 0 | 100% | 07-May-24 08:00 AM | 13-May-24 04:00 PM | 22-Mar-24 08:00 AM | 29-Mar-24 04:00 PM | 5.0d | 5.0d | 0 | 100%
A4820 | Design Support to Construction team (TQs and Troubleshooting) | 0 | 0 | 0 | 0 | 0 | 100% | 05-Mar-24 08:00 AM | 02-Aug-24 04:00 PM | 03-Aug-23 08:00 AM | 05-Jan-24 04:00 PM | 105.0d | 105.0d | 0 | 100%
A4830 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 12:00 PM | 04-Mar-24 12:00 PM | 02-Aug-23 12:00 PM | 02-Aug-23 12:00 PM | 0.0d | 0.0d | 0 | 100%
A4840 | Update post construction drawing (Internal Design) | 0 | 0 | 0 | 0 | 0 | 100% | 08-Apr-24 08:00 AM | 03-May-24 04:00 PM | 15-Mar-24 08:00 AM | 22-Mar-24 04:00 PM | 20.0d | 6.0d | 0 | 100%
A4850 | As built drawing received from Supplier | 0 | 0 | 0 | 0 | 0 | 100% | 25-Mar-24 08:00 AM | 02-Apr-24 04:00 PM | 04-Mar-24 08:00 AM | 08-Mar-24 04:00 PM | 5.0d | 5.0d | 0 | 100%
A4860 | Technical Design Complete | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 05-Jan-24 08:00 AM | 05-Jan-24 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4870 | As built drawing received from Site | 0 | 0 | 0 | 0 | 0 | 100% | 28-Mar-24 08:00 AM | 05-Apr-24 04:00 PM | 08-Mar-24 08:00 AM | 15-Mar-24 04:00 PM | 5.0d | 6.0d | 0 | 100%
A4880 | As built drawing received from Commissioning team | 0 | 0 | 0 | 0 | 0 | 100% | 28-Mar-24 08:00 AM | 05-Apr-24 04:00 PM | 15-Mar-24 08:00 AM | 22-Mar-24 04:00 PM | 5.0d | 6.0d | 0 | 100%
A4960 | Pre-Construction Information - PCI Documentation ((CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 04:00 PM | 01-Mar-24 04:00 PM | 01-Aug-23 04:00 PM | 01-Aug-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
A4970 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 18-Sep-23 08:00 AM | 18-Sep-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A5050 | Request protection settings | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 12:00 PM | 06-Mar-24 12:00 PM | 02-Aug-23 12:00 PM | 04-Aug-23 12:00 PM | 2.0d | 2.0d | 0 | 100%
A5060 | Protection Settings | 0 | 0 | 0 | 0 | 0 | 100% | 06-Mar-24 12:00 PM | 19-Apr-24 12:00 PM | 04-Aug-23 12:00 PM | 18-Sep-23 12:00 PM | 30.0d | 30.0d | 0 | 100%
4 | Construction | 448985 | 609311 | 0 | 609311 | (160,266) | 100% | 01-Feb-23 08:00 AM | 01-May-24 09:00 AM | 01-Feb-23 08:00 AM | 01-May-24 09:00 AM | 311.1d | 311.1d | 448985
441 | Site Pre Start (Enabling Works) | 0 | 0 | 0 | 0 | 0 | 0% | 01-Feb-23 08:00 AM | 01-Mar-24 08:00 AM | 01-Feb-23 08:00 AM | 02-Oct-23 08:00 AM | 270.0d | 167.0d | 0
A1980 | Prepare Construction Phase Plan | 0 | 0 | 0 | 0 | 0 | 100% | 02-Oct-23 08:00 AM | 06-Oct-23 04:00 PM | 18-Sep-23 08:00 AM | 27-Sep-23 04:00 PM | 5.0d | 8.0d | 0 | 100%
A1990 | Prepare Issue F10 | 0 | 0 | 0 | 0 | 0 | 100% | 02-Oct-23 08:00 AM | 06-Oct-23 04:00 PM | 18-Sep-23 08:00 AM | 27-Sep-23 04:00 PM | 5.0d | 8.0d | 0 | 100%
A2000 | Setup Health & safety File | 0 | 0 | 0 | 0 | 0 | 100% | 02-Oct-23 08:00 AM | 06-Oct-23 04:00 PM | 18-Sep-23 08:00 AM | 27-Sep-23 04:00 PM | 5.0d | 8.0d | 0 | 100%
PS4480 | Site Access | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 02-Oct-23 08:00 AM | 02-Oct-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
T2650 | Mobilisation of Principle Contractor | 0 | 0 | 0 | 0 | 0 | 100% | 09-Oct-23 08:00 AM | 30-Nov-23 04:00 PM | 28-Sep-23 08:00 AM | 29-Sep-23 04:00 PM | 39.0d | 2.0d | 0 | 100%
A5260 | Trail holes to establish bridge route | 0 | 0 | 0 | 0 | 0 | 100% | 01-Feb-23 08:00 AM | 02-Feb-23 04:00 PM | 01-Feb-23 08:00 AM | 02-Feb-23 04:00 PM | 2.0d | 2.0d | 0 | 100%
11 | Variation Costs |  | 0 | 0 | 0 |  | 0% | 01-Dec-23 08:00 AM | 01-Dec-23 09:00 AM | 01-Dec-23 08:00 AM | 01-Dec-23 09:00 AM | 0.1d | 0.1d | 0
A5670 | Site Setup Variation Cost |  | 0 | 0 | 0 |  | 100% | 01-Dec-23 08:00 AM | 01-Dec-23 09:00 AM | 01-Dec-23 08:00 AM | 01-Dec-23 09:00 AM | 0.1d | 0.1d | 0 | 100%
1 | Datalec land - section 1 | 108310 | 160384 | 0 | 160384 | (52,074) | 100% | 14-Dec-23 08:00 AM | 25-Mar-24 04:00 PM | 09-Oct-23 08:00 AM | 14-Dec-23 04:00 PM | 67.0d | 49.0d | 108310
A5370 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 12-Mar-24 04:00 PM | 09-Oct-23 08:00 AM | 18-Oct-23 04:00 PM | 8.0d | 8.0d | 0 | 100%
A5380 | Joint bays - cable install | 0 | 0 | 0 | 0 | 0 | 100% | 13-Mar-24 08:00 AM | 18-Mar-24 04:00 PM | 19-Oct-23 08:00 AM | 24-Oct-23 04:00 PM | 4.0d | 4.0d | 0 | 100%
A5390 | Apply for payment 1 - December | 108310 | 160384 | 0 | 160384 | (52,074) | 100% | 14-Dec-23 08:00 AM | 14-Dec-23 04:00 PM | 14-Dec-23 08:00 AM | 14-Dec-23 04:00 PM | 1.0d | 1.0d | 108310 | 100%
A5680 | HDD A10 Crossing |  | 0 | 0 | 0 |  | 100% | 15-Mar-24 08:00 AM | 25-Mar-24 04:00 PM | 16-Oct-23 08:00 AM | 24-Oct-23 04:00 PM | 7.0d | 7.0d | 0 | 100%
2 | Greensway - Skip MDW - section 2 | 0 | 0 | 0 | 0 | 0 | 0% | 15-Dec-23 08:00 AM | 14-Mar-24 04:00 PM | 26-Oct-23 08:00 AM | 22-Nov-23 04:00 PM | 59.0d | 20.0d | 0
A5400 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 14-Mar-24 04:00 PM | 26-Oct-23 08:00 AM | 10-Nov-23 04:00 PM | 10.0d | 12.0d | 0 | 100%
A5430 | Apply for payment | 0 | 0 | 0 | 0 | 0 | 100% | 15-Dec-23 08:00 AM | 15-Dec-23 04:00 PM | 22-Nov-23 08:00 AM | 22-Nov-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
3 | Baldock Road - section 3 | 0 | 0 | 0 | 0 | 0 | 0% | 13-Dec-23 08:00 AM | 26-Mar-24 04:00 PM | 23-Nov-23 08:00 AM | 13-Dec-23 04:00 PM | 69.0d | 15.0d | 0
A5440 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 13-Mar-24 08:00 AM | 26-Mar-24 04:00 PM | 23-Nov-23 08:00 AM | 11-Dec-23 04:00 PM | 10.0d | 13.0d | 0 | 100%
A5450 | Apply for payment | 0 | 0 | 0 | 0 | 0 | 100% | 13-Dec-23 08:00 AM | 13-Dec-23 04:00 PM | 12-Dec-23 08:00 AM | 13-Dec-23 04:00 PM | 1.0d | 2.0d | 0 | 100%
4 | Monks Walk - section 4 | 0 | 0 | 0 | 0 | 0 | 0% | 12-Dec-23 08:00 AM | 02-Apr-24 04:00 PM | 13-Dec-23 08:00 AM | 12-Jan-24 04:00 PM | 73.0d | 17.0d | 0
A5460 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 12-Mar-24 08:00 AM | 02-Apr-24 04:00 PM | 13-Dec-23 08:00 AM | 11-Jan-24 04:00 PM | 14.0d | 16.0d | 0 | 100%
A5470 | Apply for payment | 0 | 0 | 0 | 0 | 0 | 100% | 12-Dec-23 08:00 AM | 12-Dec-23 04:00 PM | 12-Jan-24 08:00 AM | 12-Jan-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
5 | Oak End to Monks Wlak footpath closure - section 5 | 84752 | 0 | 0 | 0 | 84752 | 100% | 15-Dec-23 08:00 AM | 03-Apr-24 04:00 PM | 23-Oct-23 08:00 AM | 15-Dec-23 04:00 PM | 71.0d | 40.0d | 84752
A5480 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 12-Mar-24 08:00 AM | 03-Apr-24 04:00 PM | 23-Oct-23 08:00 AM | 10-Nov-23 04:00 PM | 15.0d | 15.0d | 0 | 100%
A5490 | Apply for payment 2 - December | 84752 | 0 | 0 | 0 | 84752 | 100% | 15-Dec-23 08:00 AM | 15-Dec-23 04:00 PM | 15-Dec-23 08:00 AM | 15-Dec-23 04:00 PM | 1.0d | 1.0d | 84752 | 100%
6 | Oak End - Section 6 | 17193 | 176693 | 0 | 176693 | (159,500) | 100% | 29-Nov-23 08:00 AM | 28-Mar-24 04:00 PM | 14-Nov-23 08:00 AM | 12-Dec-23 04:00 PM | 81.0d | 21.0d | 17193
A5500 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 15-Mar-24 08:00 AM | 28-Mar-24 04:00 PM | 14-Nov-23 08:00 AM | 04-Dec-23 04:00 PM | 10.0d | 15.0d | 0 | 100%
A5510 | Apply for payment 3 - October | 17193 | 176693 | 0 | 176693 | (159,500) | 100% | 29-Nov-23 08:00 AM | 29-Nov-23 04:00 PM | 29-Nov-23 08:00 AM | 12-Dec-23 04:00 PM | 1.0d | 10.0d | 17193 | 100%
7 | Luynes rise - section 7 | 85780 | 0 | 0 | 0 | 85780 | 100% | 13-Dec-23 08:00 AM | 09-Apr-24 04:00 PM | 28-Nov-23 08:00 AM | 22-Dec-23 04:00 PM | 77.0d | 19.0d | 85780
A5520 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 12-Mar-24 08:00 AM | 09-Apr-24 04:00 PM | 28-Nov-23 08:00 AM | 22-Dec-23 04:00 PM | 19.0d | 19.0d | 0 | 100%
A5530 | Apply for payment 4 - November | 85780 | 0 | 0 | 0 | 85780 | 100% | 13-Dec-23 08:00 AM | 13-Dec-23 04:00 PM | 13-Dec-23 08:00 AM | 15-Dec-23 04:00 PM | 1.0d | 3.0d | 85780 | 100%
8 | Aspenden Rd - Section 8 | 47189 | 429980 | 0 | 429980 | (382,791) | 100% | 15-Dec-23 08:00 AM | 26-Mar-24 04:00 PM | 15-Dec-23 08:00 AM | 14-Feb-24 08:01 AM | 67.0d | 37.0d | 47189
A5540 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 14-Mar-24 08:00 AM | 26-Mar-24 04:00 PM | 12-Jan-24 08:00 AM | 01-Feb-24 04:00 PM | 9.0d | 15.0d | 0 | 100%
A5550 | Apply for payment 5 - December | 47189 | 429980 | 0 | 429980 | (382,791) | 100% | 15-Dec-23 08:00 AM | 15-Dec-23 04:00 PM | 15-Dec-23 08:00 AM | 14-Feb-24 08:01 AM | 1.0d | 37.0d | 47189 | 100%
9 | London Road section 9 | 33028 | 179188 | 0 | 179188 | (146,160) | 100% | 01-Nov-23 08:00 AM | 05-Apr-24 04:00 PM | 01-Nov-23 08:00 AM | 28-Mar-24 04:00 PM | 105.0d | 101.0d | 33028
A5560 | Excavation - duct install - Reinstatement | 0 | 0 | 0 | 0 | 0 | 100% | 14-Mar-24 08:00 AM | 05-Apr-24 04:00 PM | 26-Feb-24 08:00 AM | 08-Mar-24 04:00 PM | 15.0d | 10.0d | 0 | 100%
A5570 | Joint bays - cable install | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 28-Mar-24 04:00 PM | 01-Mar-24 08:00 AM | 28-Mar-24 04:00 PM | 20.0d | 20.0d | 0 | 100%
A5580 | Testing - Jointing | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 14-Mar-24 04:00 PM | 01-Mar-24 08:00 AM | 14-Mar-24 04:00 PM | 10.0d | 10.0d | 0 | 100%
A5590 | Section 58 Reinstatment | 0 | 0 | 0 | 0 | 0 | 100% | 15-Mar-24 08:00 AM | 28-Mar-24 04:00 PM | 01-Mar-24 08:00 AM | 08-Mar-24 04:00 PM | 10.0d | 6.0d | 0 | 100%
A5600 | Apply for payment 6 - December | 33028 | 179188 | 0 | 179188 | (146,160) | 100% | 01-Nov-23 08:00 AM | 01-Nov-23 04:00 PM | 01-Nov-23 08:00 AM | 01-Dec-23 04:00 PM | 1.0d | 23.0d | 33028 | 100%
A5610 | Outage & change over temp connection | 0 | 0 | 0 | 0 | 0 | 100% | 15-Mar-24 08:00 AM | 15-Mar-24 04:00 PM | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
A5620 | Outage to final connections / energise cable | 0 | 0 | 0 | 0 | 0 | 100% | 15-Mar-24 08:00 AM | 15-Mar-24 04:00 PM | 05-Mar-24 08:00 AM | 05-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
10 | Compile Completion Pack | 72732 | (336,934) | 0 | (336,934) | 409725 | 100% | 15-Dec-23 08:00 AM | 01-May-24 09:00 AM | 15-Dec-23 08:00 AM | 01-May-24 09:00 AM | 90.1d | 90.1d | 72732
A5630 | Demob - site clear - Up-Load to UKPN sharepoint | 0 | 0 | 0 | 0 | 0 | 100% | 11-Mar-24 08:00 AM | 22-Mar-24 04:00 PM | 05-Mar-24 08:00 AM | 19-Mar-24 04:00 PM | 10.0d | 11.0d | 0 | 100%
A5640 | Apply for final payment 7 - January | 72732 | (336,993) | 0 | (336,993) | 409725 | 100% | 15-Dec-23 08:00 AM | 15-Dec-23 04:00 PM | 15-Dec-23 08:00 AM | 18-Mar-24 08:00 AM | 1.0d | 60.0d | 72732 | 100%
A5690 | Permit costs |  | 59 | 0 | 59 |  | 100% | 01-May-24 08:00 AM | 01-May-24 09:00 AM | 01-May-24 08:00 AM | 01-May-24 09:00 AM | 0.1d | 0.1d | 0 | 100%
449 | Test & Commissioning | 24919 | 1997 | 0 | 1997 | 22922 | 6.7% | 15-Jan-24 08:00 AM | 27-Mar-24 04:00 PM | 15-Jan-24 08:00 AM |  | 53.0d | 96.0d | 24919
TC4890 | SAP Updated | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
TC4900 | Netmap Updated | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
CLO130 | Demobilise from site | 0 | 0 | 0 | 0 | 0 | 100% | 25-Mar-24 08:00 AM | 27-Mar-24 04:00 PM | 08-Mar-24 08:00 AM | 15-Mar-24 04:00 PM | 3.0d | 6.0d | 0 | 100%
A2940 | Hot Commissioning of Substation | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 04:00 PM | 01-Mar-24 08:00 AM | 01-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
A3060 | Protection Settings uploaded | 0 | 0 | 0 | 0 | 0 | 100% | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 01-Mar-24 08:00 AM | 0.0d | 0.0d | 0 | 100%
A4450 | Substation Under Rules | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 04-Mar-24 08:00 AM | 04-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
A5650 | Commissioning - UKPN DLO Cost | 24919 | 1997 | 0 | 1997 | 22922 | 6.7% | 15-Jan-24 08:00 AM | 15-Jan-24 09:00 AM | 15-Jan-24 08:00 AM |  | 0.1d | 96.0d | 24919 | 6.7%
5 | Employer's Risk | 62464 | 62528 | 0 | 62528 | (64) | 100% | 15-Jan-24 08:00 AM | 15-Jan-24 09:00 AM | 15-Jan-24 08:00 AM | 16-Feb-24 09:00 AM | 0.1d | 24.1d | 62528
A5660 | Risk Provision | 62464 | 62528 | 0 | 62528 | (64) | 100% | 15-Jan-24 08:00 AM | 15-Jan-24 09:00 AM | 15-Jan-24 08:00 AM | 16-Feb-24 09:00 AM | 0.1d | 24.1d | 62528 | 100%
6 | Closure | 0 | 0 | 0 | 0 | 0 | 0% | 05-Mar-24 08:00 AM | 16-Dec-24 04:00 PM | 05-Mar-24 08:00 AM |  | 200.0d | 18.0d | 0
CLO3100 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 03-Jun-24 08:00 AM | 30-Jul-24 04:00 PM |  |  | 42.0d | 0.0d | 0 | 0%
CLO120 | Review and Approve H&S File | 0 | 0 | 0 | 0 | 0 | 100% | 25-Mar-24 08:00 AM | 09-Apr-24 04:00 PM | 15-Mar-24 08:00 AM | 29-Mar-24 04:00 PM | 10.0d | 10.0d | 0 | 100%
CLO14150 | Financial Closure | 0 | 0 | 0 | 0 | 0 | 0% | 03-Jun-24 08:00 AM | 18-Nov-24 04:00 PM |  |  | 120.0d | 0.0d | 0 | 0%
CLO15940 | Familiarisation Training | 0 | 0 | 0 | 0 | 0 | 100% | 05-Mar-24 08:00 AM | 18-Mar-24 04:00 PM | 05-Mar-24 08:00 AM | 11-Mar-24 04:00 PM | 10.0d | 5.0d | 0 | 100%
A4460 | Deadline for submission of defined costs (65 days from contract completion) | 0 | 0 | 0 | 0 | 0 | 0% | 03-Jun-24 08:00 AM | 03-Jun-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 19-Nov-24 08:00 AM | 16-Dec-24 04:00 PM |  |  | 20.0d | 0.0d | 0
Gate1070 | Prepare Gate D Paper | 0 | 0 | 0 | 0 | 0 | 0% | 19-Nov-24 08:00 AM | 16-Dec-24 04:00 PM |  |  | 20.0d | 0.0d | 0 | 0%
Gate1080 | Submit Gate D Paper to RPrB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 0% | 16-Dec-24 04:00 PM | 16-Dec-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
M-L.MCN.108590 | Eastfield Est, Acacia Road, Mitcham, CR4 1BX | 1609532 | 31924 | 1578793 | 1610717 | (1,185) | 2.03% | 07-Jul-23 08:00 AM | 22-Aug-25 08:00 AM | 02-Sep-21 08:00 AM |  | 533.0d | 682.0d | 1609532
1 | Project Summary | 0 | 0 | 0 | 0 | 0 | 0% | 07-Jul-23 08:00 AM | 22-Aug-25 08:00 AM | 02-Sep-21 08:00 AM |  | 533.0d | 637.0d | 0
6 | Project Governance Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 07-Jul-23 08:00 AM | 22-Aug-25 08:00 AM | 02-Sep-21 08:00 AM |  | 111.0d | 0.0d | 0
A1000 | Gate B Award | 0 | 0 | 0 | 0 | 0 | 100% | 07-Jul-23 08:00 AM | 07-Jul-23 08:00 AM | 02-Sep-21 08:00 AM | 02-Sep-21 08:00 AM | 0.0d | 0.0d | 0 | 100%
A1010 | Gate C Award | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 27-Sep-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1020 | Gate D Award | 0 | 0 | 0 | 0 | 0 | 0% | 22-Aug-25 08:00 AM | 22-Aug-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
9 | Construction Delivery Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 01-Nov-23 04:00 PM | 14-May-25 04:00 PM | 01-Nov-23 04:00 PM |  | 380.0d | 96.0d | 0
A1030 | Start on Site | 0 | 0 | 0 | 0 | 0 | 0% | 16-Oct-24 04:00 PM | 16-Oct-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1040 | Hot Commissioning Commencement | 0 | 0 | 0 | 0 | 0 | 0% | 24-Apr-25 08:00 AM | 24-Apr-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1060 | Site Demobilisation Complete | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-25 04:00 PM | 14-May-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1070 | Switchgear Energised | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 07-May-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1080 | Cct 1 Energised | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 07-May-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1090 | Practical Completion | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-25 04:00 PM | 14-May-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1240 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 23-Nov-23 04:00 PM | 23-Nov-23 04:00 PM | 23-Nov-23 04:00 PM | 23-Nov-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
A1260 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 01-Nov-23 04:00 PM | 01-Nov-23 04:00 PM | 01-Nov-23 04:00 PM | 01-Nov-23 04:00 PM | 0.0d | 0.0d | 0 | 100%
A1360 | Suppliers's Drawings accepted by UKPN | 0 | 0 | 0 | 0 | 0 | 0% | 28-Jun-24 09:00 AM | 28-Jun-24 09:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1390 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 0% | 02-Jul-24 04:00 PM | 02-Jul-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1420 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 25-Mar-24 08:00 AM | 25-Mar-24 08:00 AM | 25-Mar-24 08:00 AM | 25-Mar-24 08:00 AM | 0.0d | 0.0d | 0 | 100%
A2070 | Customer Required By energisation date | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 07-May-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
8 | Asset Registration/Update Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 11-Jun-24 04:00 PM | 07-May-25 04:00 PM |  |  | 226.0d | 0.0d | 0
A1100 | Asset Data - Updated (SAP -Switchgear) | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 04:00 PM | 07-May-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A2120 | Asset Data - Registration (SAP) - Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 11-Jun-24 04:00 PM | 11-Jun-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
7 | Project Closeout Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 22-May-25 04:00 PM | 22-Aug-25 08:00 AM |  |  | 64.0d | 0.0d | 0
A1110 | Project Completion | 0 | 0 | 0 | 0 | 0 | 0% | 22-Aug-25 08:00 AM | 22-Aug-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1120 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 27-Jun-25 04:00 PM | 27-Jun-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1130 | Financial Close | 0 | 0 | 0 | 0 | 0 | 0% | 04-Aug-25 04:00 PM | 04-Aug-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1680 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 26-Jun-25 04:00 PM | 26-Jun-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1970 | Completion Certificate Signed off | 0 | 0 | 0 | 0 | 0 | 0% | 12-Jun-25 04:00 PM | 12-Jun-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A2080 | Completion of the Health and Safety File | 0 | 0 | 0 | 0 | 0 | 0% | 22-May-25 04:00 PM | 22-May-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
TASK DESIGN DELIVERY MILESTONES | TASK DESIGN DELIVERY MILESTONES (DO NOT DELETE or CHANGE ACTIVITY ID) | 0 | 0 | 0 | 0 | 0 | 0% | 01-Nov-23 08:00 AM | 26-Jun-25 04:00 PM | 01-Nov-23 08:00 AM |  | 411.0d | 98.0d | 0
DES-DM1 | Concept Design Scope & Forecast agreed - (CAP 02-015 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 01-Nov-23 08:00 AM | 01-Nov-23 04:00 PM | 01-Nov-23 08:00 AM | 01-Nov-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM2 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 20-Nov-23 08:00 AM | 20-Nov-23 04:00 PM | 20-Nov-23 04:00 PM | 20-Nov-23 04:00 PM | 1.0d | 0.0d | 0 | 100%
DES-DM4 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 24-Nov-23 08:00 AM | 24-Nov-23 04:00 PM | 23-Nov-23 08:00 AM | 23-Nov-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM5 | Developed Design Scope & Forecast agreed - CAP 02-015/16 signed off | 0 | 0 | 0 | 0 | 0 | 100% | 25-Mar-24 08:00 AM | 25-Mar-24 04:00 PM | 25-Mar-24 08:00 AM | 25-Mar-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
DES-DM6 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 01-Jul-24 08:00 AM | 01-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
DES-DM7 | Suppliers's Drawings accepted by UKPN | 0 | 0 | 0 | 0 | 0 | 0% | 28-Jun-24 09:00 AM | 28-Jun-24 09:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
DES-DM9 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 0% | 02-Jul-24 08:00 AM | 02-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A2200 | Asset Data - Registration (SAP) - Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 11-Jun-24 08:00 AM | 11-Jun-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
DES-DM11 | Pre-Construction Information - PCI Documentation (CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jul-24 08:00 AM | 05-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
DES-DM12 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 0% | 03-Jul-24 08:00 AM | 03-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
DES-DM13 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 0% | 21-Aug-24 12:00 PM | 22-Aug-24 12:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
DES-DM14 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 26-Jun-25 08:00 AM | 26-Jun-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
3 | Gate B-C | 93022 | 31924 | 62283 | 94207 | (1,185) | 35.2% | 09-Oct-23 08:00 AM | 04-Feb-25 09:00 AM | 09-Oct-23 08:00 AM |  | 329.1d | 160.0d | 93022
1 | Project Management | 57806 | 12900 | 46091 | 58991 | (1,185) | 20.09% | 09-Oct-23 08:00 AM | 25-Jul-24 04:00 PM | 09-Oct-23 08:00 AM |  | 199.0d | 160.0d | 57806
A1280 | Project Manager | 9000 | 3541 | 5459 | 9000 | 0 | 21% | 02-Jan-24 08:00 AM | 25-Jul-24 04:00 PM | 09-Oct-23 08:00 AM |  | 144.0d | 160.0d | 9000 | 21%
A1290 | Quanity Surveyer | 10000 | 164 | 9836 | 10000 | 0 | 2% | 09-Oct-23 08:00 AM | 08-May-24 04:00 PM | 09-Oct-23 08:00 AM |  | 144.0d | 160.0d | 10000 | 2%
A1300 | Project Planner | 6352 | 7537 | 0 | 7537 | (1,185) | 30% | 09-Oct-23 08:00 AM | 08-May-24 04:00 PM | 09-Oct-23 08:00 AM |  | 144.0d | 160.0d | 6352 | 30%
A2540 | Wayleaves | 13232 | 0 | 13232 | 13232 | 0 | 14% | 09-Oct-23 08:00 AM | 08-May-24 04:00 PM | 30-Oct-23 08:00 AM |  | 144.0d | 145.0d | 13232 | 14%
A2780 | Other Indirect Cost | 19222 | 1657 | 17565 | 19222 | 0 | 30% | 09-Oct-23 08:00 AM | 08-May-24 04:00 PM | 09-Oct-23 08:00 AM |  | 144.0d | 160.0d | 19222 | 30%
2 | Design / Surveys / OP&C | 35216 | 19024 | 16192 | 35216 | 0 | 60% | 01-Nov-23 08:00 AM | 28-Aug-24 04:00 PM | 01-Nov-23 08:00 AM |  | 205.0d | 143.0d | 35216
A1180 | Concept Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 01-Nov-23 08:00 AM | 07-Nov-23 04:00 PM | 01-Nov-23 08:00 AM | 07-Nov-23 04:00 PM | 5.0d | 5.0d | 0 | 100%
A1190 | Site Visit | 0 | 0 | 0 | 0 | 0 | 100% | 09-Nov-23 08:00 AM | 09-Nov-23 04:00 PM | 09-Nov-23 08:00 AM | 09-Nov-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A1200 | Site information review/ Protection Phylosophy/ Preliminary Layouts | 0 | 0 | 0 | 0 | 0 | 100% | 10-Nov-23 08:00 AM | 22-Nov-23 04:00 PM | 10-Nov-23 08:00 AM | 20-Nov-23 04:00 PM | 9.0d | 7.0d | 0 | 100%
A1220 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 20-Nov-23 08:00 AM | 20-Nov-23 08:00 AM | 20-Nov-23 08:00 AM | 20-Nov-23 08:00 AM | 0.0d | 0.0d | 0 | 100%
A1230 | Concept Design Review | 0 | 0 | 0 | 0 | 0 | 100% | 20-Nov-23 08:00 AM | 20-Nov-23 04:00 PM | 20-Nov-23 08:00 AM | 20-Nov-23 04:00 PM | 1.0d | 1.0d | 0 | 100%
A1250 | Concept Design - wiring diagrams | 0 | 0 | 0 | 0 | 0 | 100% | 01-Nov-23 08:00 AM | 20-Nov-23 04:00 PM | 01-Nov-23 08:00 AM | 20-Nov-23 04:00 PM | 14.0d | 14.0d | 0 | 100%
A1320 | Design B-C Cost Bar | 35216 | 19024 | 16192 | 35216 | 0 | 60% | 01-Dec-23 08:00 AM | 03-Jul-24 04:00 PM | 01-Dec-23 08:00 AM |  | 144.0d | 121.0d | 35216 | 60%
A1330 | SAP/Commissioning Engineer/Project Engineer Early Engagement | 0 | 0 | 0 | 0 | 0 | 0% | 02-Jul-24 08:00 AM | 02-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1340 | Developed Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 100% | 25-Mar-24 08:00 AM | 26-Mar-24 04:00 PM | 25-Mar-24 08:00 AM | 26-Mar-24 04:00 PM | 2.0d | 2.0d | 0 | 100%
A1350 | Order Placed/Request Supplier Preliminary Drawings | 0 | 0 | 0 | 0 | 0 | 100% | 13-May-24 08:00 AM | 13-May-24 08:00 AM | 13-May-24 08:00 AM | 13-May-24 08:00 AM | 0.0d | 0.0d | 0 | 100%
A1380 | Developed Design Review | 0 | 0 | 0 | 0 | 0 | 0% | 01-Jul-24 08:00 AM | 01-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1400 | Developed Design - UKPN Internal | 0 | 0 | 0 | 0 | 0 | 0% | 02-Jul-24 08:00 AM | 28-Aug-24 04:00 PM |  |  | 41.0d | 0.0d | 0 | 0%
A1410 | Publish Developed Design Documents & Drawings/Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 0% | 03-Jul-24 08:00 AM | 03-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1430 | Developed Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 0% | 01-Jul-24 04:00 PM | 01-Jul-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A2050 | Supplier Preliminary Drawings Preparation/Review | 0 | 0 | 0 | 0 | 0 | 0% | 19-Jun-24 09:00 AM | 27-Jun-24 09:00 AM |  |  | 6.0d | 0.0d | 0 | 0%
A2060 | Completion of Manufacturer's Drawings | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jun-24 08:00 AM | 28-Jun-24 04:00 PM |  |  | 7.0d | 0.0d | 0 | 0%
A2260 | Supplier quotation/tender | 0 | 0 | 0 | 0 | 0 | 100% | 06-Dec-23 08:00 AM | 10-Jan-24 04:00 PM | 06-Dec-23 08:00 AM | 19-Feb-24 04:00 PM | 20.0d | 48.0d | 0 | 100%
A2740 | Tender Project (ADM) | 0 | 0 | 0 | 0 | 0 | 0% | 04-Jul-24 08:00 AM | 31-Jul-24 04:00 PM |  |  | 20.0d | 0.0d | 0 | 0%
4 | Procurement | 0 | 0 | 0 | 0 | 0 | 0% | 13-May-24 08:00 AM | 04-Feb-25 09:00 AM | 13-May-24 08:00 AM |  | 183.1d | 1.0d | 0
A1440 | Eaton Manufacture | 0 | 0 | 0 | 0 | 0 | 0% | 01-Jul-24 09:00 AM | 04-Feb-25 09:00 AM |  |  | 149.0d | 0.0d | 0 | 0%
A2690 | Order issued to Eaton | 0 | 0 | 0 | 0 | 0 | 100% | 13-May-24 08:00 AM | 13-May-24 04:00 PM | 13-May-24 08:00 AM | 13-May-24 04:00 PM | 1.0d | 1.0d | 0 | 100%
A2700 | Eaton first issue of drawings | 0 | 0 | 0 | 0 | 0 | 0% | 10-Jun-24 08:00 AM | 10-Jun-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A2710 | UKPN review of Eaton drawings | 0 | 0 | 0 | 0 | 0 | 0% | 11-Jun-24 09:00 AM | 19-Jun-24 09:00 AM |  |  | 6.0d | 0.0d | 0 | 0%
A2720 | Final drawing update and sign off | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jun-24 08:00 AM | 28-Jun-24 09:00 AM |  |  | 6.1d | 0.0d | 0 | 0%
5 | Gate C Governance | 0 | 0 | 0 | 0 | 0 | 0% | 12-Aug-24 08:00 AM | 24-Sep-24 04:00 PM |  |  | 31.0d | 0.0d | 0
A1450 | Prepare Gate C Paper | 0 | 0 | 0 | 0 | 0 | 0% | 12-Aug-24 08:00 AM | 02-Sep-24 04:00 PM |  |  | 15.0d | 0.0d | 0 | 0%
A1460 | Submit Gate C Paper to RPfB | 0 | 0 | 0 | 0 | 0 | 0% | 02-Sep-24 04:00 PM | 02-Sep-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1470 | Prepare WPO | 0 | 0 | 0 | 0 | 0 | 0% | 16-Sep-24 08:00 AM | 23-Sep-24 04:00 PM |  |  | 6.0d | 0.0d | 0 | 0%
A2730 | Award WPO | 0 | 0 | 0 | 0 | 0 | 0% | 24-Sep-24 08:00 AM | 24-Sep-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
4 | Gate C-D | 1516510 | 0 | 1516510 | 1516510 | 0 | 0% | 03-Jun-24 08:00 AM | 21-Aug-25 04:00 PM |  |  | 308.0d | 0.0d | 1516510
A1480 | Contract Data - Start Date | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 27-Sep-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1490 | Contract Data - Access Date (Date to be set as per contract info) | 0 | 0 | 0 | 0 | 0 | 0% | 05-Feb-25 10:00 AM | 05-Feb-25 10:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1500 | Contract Data - Completion Date for the Whole of the Works | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-25 04:00 PM | 14-May-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
1 | Project Management | 67369 | 0 | 67369 | 67369 | 0 | 0% | 03-Jun-24 08:00 AM | 10-Jun-25 04:00 PM |  |  | 256.0d | 0.0d | 67369
A1510 | Project Manager | 36902 | 0 | 36902 | 36902 | 0 | 0% | 03-Jun-24 08:00 AM | 07-Feb-25 04:00 PM |  |  | 173.0d | 0.0d | 36902 | 0%
A1520 | Quantity Surveyor | 7244 | 0 | 7244 | 7244 | 0 | 0% | 03-Jun-24 08:00 AM | 07-Feb-25 04:00 PM |  |  | 173.0d | 0.0d | 7244 | 0%
A1530 | Project Planner | 6353 | 0 | 6353 | 6353 | 0 | 0% | 03-Jun-24 08:00 AM | 07-Feb-25 04:00 PM |  |  | 173.0d | 0.0d | 6353 | 0%
A2760 | Other Indirect Cost | 16871 | 0 | 16871 | 16871 | 0 | 0% | 27-Sep-24 08:00 AM | 10-Jun-25 04:00 PM |  |  | 173.0d | 0.0d | 16871 | 0%
3 | Procurement | 564738 | 0 | 564738 | 564738 | 0 | 0% | 10-Jun-24 08:00 AM | 04-Jun-25 10:00 AM |  |  | 246.3d | 0.0d | 564738
432 | Eaton Panel Manufacture | 355035 | 0 | 355035 | 355035 | 0 | 0% | 10-Jun-24 08:00 AM | 05-Feb-25 10:00 AM |  |  | 165.3d | 0.0d | 355035
A2110 | 10% Manufacture drawing received. | 35503 | 0 | 35503 | 35503 | 0 | 0% | 10-Jun-24 08:00 AM | 10-Jun-24 04:00 PM |  |  | 1.0d | 0.0d | 35503 | 0%
A2320 | 70% Completion Certificate and delivery to site | 248524 | 0 | 248524 | 248524 | 0 | 0% | 04-Feb-25 10:00 AM | 05-Feb-25 10:00 AM |  |  | 1.0d | 0.0d | 248524 | 0%
A2350 | 20% Approval of drawings for manufacture | 71007 | 0 | 71007 | 71007 | 0 | 0% | 01-Jul-24 09:00 AM | 02-Jul-24 09:00 AM |  |  | 1.0d | 0.0d | 71007 | 0%
1 | Eaton UK Installation | 0 | 0 | 0 | 0 | 0 | 0% | 04-Feb-25 08:00 AM | 26-Feb-25 08:00 AM |  |  | 16.0d | 0.0d | 0
A2550 | 50% value of contract price following actual start on site | 0 | 0 | 0 | 0 | 0 | 0% | 04-Feb-25 08:00 AM | 04-Feb-25 09:00 AM |  |  | 0.1d | 0.0d | 0 | 0%
A2560 | 50% value of contract price on completion of installation | 0 | 0 | 0 | 0 | 0 | 0% | 26-Feb-25 08:00 AM | 26-Feb-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
434 | Cable & Materials Procurement | 209704 | 0 | 209704 | 209704 | 0 | 0% | 27-Sep-24 08:00 AM | 04-Jun-25 10:00 AM |  |  | 168.3d | 0.0d | 209704
A1690 | Install Cable 11Kv | 7483 | 0 | 7483 | 7483 | 0 | 0% | 06-Mar-25 10:00 AM | 04-Jun-25 10:00 AM |  |  | 60.0d | 0.0d | 7483 | 0%
A2360 | Install Inter-Connected Cables 11Kv | 105987 | 0 | 105987 | 105987 | 0 | 0% | 06-Mar-25 09:00 AM | 06-Mar-25 10:00 AM |  |  | 0.1d | 0.0d | 105987 | 0%
A2500 | Install Multicore cable inter no Exca upto 50m | 96234 | 0 | 96234 | 96234 | 0 | 0% | 27-Feb-25 09:00 AM | 27-Feb-25 10:00 AM |  |  | 0.1d | 0.0d | 96234 | 0%
A2520 | Procurement of long lead items | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 27-Sep-24 09:00 AM |  |  | 0.1d | 0.0d | 0 | 0%
2 | Design / Surveys / OP&C Gate C-D | 16000 | 0 | 16000 | 16000 | 0 | 0% | 04-Jul-24 08:00 AM | 26-Jun-25 04:00 PM |  |  | 245.0d | 0.0d | 16000
A1540 | Design C-D Cost Bar | 16000 | 0 | 16000 | 16000 | 0 | 0% | 09-Dec-24 08:00 AM | 14-May-25 04:00 PM |  |  | 104.0d | 0.0d | 16000 | 0%
A1550 | Technical Design Kick off/ Scope agreement | 0 | 0 | 0 | 0 | 0 | 0% | 04-Jul-24 08:00 AM | 04-Jul-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1560 | Technical design using Manufacture drawings (Major plant like Transformer, Switchgear etc) | 0 | 0 | 0 | 0 | 0 | 0% | 08-Jul-24 12:00 PM | 26-Nov-24 12:00 PM |  |  | 100.0d | 0.0d | 0 | 0%
A1570 | Technical design using equipment Specified/ordered post gate C | 0 | 0 | 0 | 0 | 0 | 0% | 08-Jul-24 12:00 PM | 26-Nov-24 12:00 PM |  |  | 100.0d | 0.0d | 0 | 0%
A1580 | As-Build Drawings review | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jun-25 08:00 AM | 26-Jun-25 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A1590 | Design Support to Construction team (TQs and Troubleshooting) | 0 | 0 | 0 | 0 | 0 | 0% | 09-Jul-24 08:00 AM | 03-Dec-24 04:00 PM |  |  | 105.0d | 0.0d | 0 | 0%
A1600 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 0% | 08-Jul-24 12:00 PM | 08-Jul-24 12:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1610 | Update post construction drawing (Internal Design) | 0 | 0 | 0 | 0 | 0 | 0% | 22-May-25 08:00 AM | 19-Jun-25 04:00 PM |  |  | 20.0d | 0.0d | 0 | 0%
A1620 | As built drawing received from Supplier | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-25 08:00 AM | 20-May-25 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A1630 | Technical Design Complete | 0 | 0 | 0 | 0 | 0 | 0% | 03-Dec-24 04:00 PM | 03-Dec-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1640 | As built drawing received from Site | 0 | 0 | 0 | 0 | 0 | 0% | 15-May-25 08:00 AM | 21-May-25 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A1650 | As built drawing received from Commissioning team | 0 | 0 | 0 | 0 | 0 | 0% | 15-May-25 08:00 AM | 21-May-25 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A1660 | Pre-Construction Information - PCI Documentation ((CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 0% | 05-Jul-24 04:00 PM | 05-Jul-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1670 | Protection Settings Issued | 0 | 0 | 0 | 0 | 0 | 0% | 22-Aug-24 12:00 PM | 22-Aug-24 12:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A2090 | Request protection settings | 0 | 0 | 0 | 0 | 0 | 0% | 08-Jul-24 12:00 PM | 10-Jul-24 12:00 PM |  |  | 2.0d | 0.0d | 0 | 0%
A2100 | Protection Settings | 0 | 0 | 0 | 0 | 0 | 0% | 10-Jul-24 12:00 PM | 21-Aug-24 12:00 PM |  |  | 30.0d | 0.0d | 0 | 0%
4 | Construction | 868403 | 0 | 868403 | 868403 | 0 | 0% | 27-Sep-24 08:00 AM | 28-Jul-25 10:00 AM |  |  | 206.3d | 0.0d | 868403
A1700 | External Works | 419669 | 0 | 419669 | 419669 | 0 | 0% | 05-Feb-25 10:00 AM | 05-Mar-25 04:00 PM |  |  | 20.8d | 0.0d | 419669 | 0%
A2570 | Start on site | 0 | 0 | 0 | 0 | 0 | 0% | 16-Oct-24 03:00 PM | 16-Oct-24 04:00 PM |  |  | 0.1d | 0.0d | 0 | 0%
A2580 | Clear proposed switch room of all stored materials | 0 | 0 | 0 | 0 | 0 | 0% | 17-Oct-24 08:00 AM | 23-Oct-24 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A2590 | Specialist removal of asbestos in trench ducts | 0 | 0 | 0 | 0 | 0 | 0% | 24-Oct-24 08:00 AM | 13-Nov-24 04:00 PM |  |  | 15.0d | 0.0d | 0 | 0%
A2600 | Structural alterations to switch room | 0 | 0 | 0 | 0 | 0 | 0% | 14-Nov-24 08:00 AM | 04-Dec-24 04:00 PM |  |  | 15.0d | 0.0d | 0 | 0%
A2610 | Erect secure hoardings to plant access to existing & New switch room | 0 | 0 | 0 | 0 | 0 | 0% | 05-Dec-24 08:00 AM | 09-Dec-24 04:00 PM |  |  | 3.0d | 0.0d | 0 | 0%
A2620 | Remove existing timber door sets to both existing and new switch room | 0 | 0 | 0 | 0 | 0 | 0% | 10-Dec-24 08:00 AM | 16-Dec-24 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A2630 | Initial decorations in new switch room | 0 | 0 | 0 | 0 | 0 | 0% | 17-Dec-24 08:00 AM | 30-Dec-24 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A2640 | M&E refurbishment within new Switch room | 0 | 0 | 0 | 0 | 0 | 0% | 31-Dec-24 08:00 AM | 16-Jan-25 04:00 PM |  |  | 12.0d | 0.0d | 0 | 0%
A2650 | Install new door sets and glazing over | 0 | 0 | 0 | 0 | 0 | 0% | 31-Dec-24 08:00 AM | 06-Jan-25 04:00 PM |  |  | 4.0d | 0.0d | 0 | 0%
A2660 | Complete decorations | 0 | 0 | 0 | 0 | 0 | 0% | 17-Jan-25 08:00 AM | 23-Jan-25 04:00 PM |  |  | 5.0d | 0.0d | 0 | 0%
A2670 | Delivery & installation of new 11kV switch board | 0 | 0 | 0 | 0 | 0 | 0% | 04-Feb-25 08:00 AM | 25-Feb-25 04:00 PM |  |  | 16.0d | 0.0d | 0 | 0%
A2770 | Direct Labour Cost | 448735 | 0 | 448735 | 448735 | 0 | 0% | 05-Feb-25 10:00 AM | 28-Jul-25 10:00 AM |  |  | 119.0d | 0.0d | 448735 | 0%
441 | Site Pre Start (Enabling Works) | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 16-Oct-24 04:00 PM |  |  | 14.0d | 0.0d | 0
A1710 | Prepare Construction Phase Plan | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 16-Oct-24 04:00 PM |  |  | 14.0d | 0.0d | 0 | 0%
A1720 | Prepare Issue F10 | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 16-Oct-24 04:00 PM |  |  | 14.0d | 0.0d | 0 | 0%
A1730 | Setup Health & safety File | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 16-Oct-24 04:00 PM |  |  | 14.0d | 0.0d | 0 | 0%
A1740 | Site Access | 0 | 0 | 0 | 0 | 0 | 0% | 16-Oct-24 04:00 PM | 16-Oct-24 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
442 | Mobilisation | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 15-Oct-24 04:00 PM |  |  | 13.0d | 0.0d | 0
A1750 | Mobilisation of Principle Contractor | 0 | 0 | 0 | 0 | 0 | 0% | 27-Sep-24 08:00 AM | 15-Oct-24 04:00 PM |  |  | 13.0d | 0.0d | 0 | 0%
443 | Outages | 0 | 0 | 0 | 0 | 0 | 0% | 04-Mar-25 10:00 AM | 07-May-25 10:00 AM |  |  | 43.0d | 0.0d | 0
A1760 | Outage 1 | 0 | 0 | 0 | 0 | 0 | 0% | 04-Mar-25 10:00 AM | 07-May-25 10:00 AM |  |  | 43.0d | 0.0d | 0 | 0%
446 | Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 04-Feb-25 10:00 AM | 08-May-25 04:00 PM |  |  | 64.8d | 0.0d | 0
A1770 | Install 11kV Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 05-Feb-25 10:00 AM | 27-Feb-25 10:00 AM |  |  | 16.0d | 0.0d | 0 | 0%
A1780 | Install Multicores & Terminate | 0 | 0 | 0 | 0 | 0 | 0% | 27-Feb-25 10:00 AM | 06-Mar-25 10:00 AM |  |  | 5.0d | 0.0d | 0 | 0%
A1790 | Cold Commission 11/6.6kV Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 05-Feb-25 10:00 AM | 27-Feb-25 10:00 AM |  |  | 16.0d | 0.0d | 0 | 0%
A1800 | 11/6.6kV Switchgear Installation Planned Completion | 0 | 0 | 0 | 0 | 0 | 0% | 27-Feb-25 10:00 AM | 27-Feb-25 10:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1810 | 11/6.6kV Switchgear Installation Planned Start | 0 | 0 | 0 | 0 | 0 | 0% | 05-Feb-25 10:00 AM | 05-Feb-25 10:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1830 | Hot commissioning of Switchgear | 0 | 0 | 0 | 0 | 0 | 0% | 24-Apr-25 08:00 AM | 08-May-25 04:00 PM |  |  | 10.0d | 0.0d | 0 | 0%
A2510 | Delivery to site | 0 | 0 | 0 | 0 | 0 | 0% | 04-Feb-25 10:00 AM | 05-Feb-25 10:00 AM |  |  | 1.0d | 0.0d | 0 | 0%
A2790 | Joint & Terminate interconnector cable |  | 0 | 0 | 0 |  | 0% | 14-Apr-25 08:00 AM | 17-Apr-25 04:00 PM |  |  | 4.0d | 0.0d | 0 | 0%
448 | Cable Install | 0 | 0 | 0 | 0 | 0 | 0% | 06-Mar-25 10:00 AM | 06-May-25 04:00 PM |  |  | 40.8d | 0.0d | 0
A1840 | Cable Installation Planned Completion | 0 | 0 | 0 | 0 | 0 | 0% | 06-May-25 04:00 PM | 06-May-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1850 | Cable Installation Contract Completion Date | 0 | 0 | 0 | 0 | 0 | 0% | 06-May-25 04:00 PM | 06-May-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1860 | Install 11kv Cabling | 0 | 0 | 0 | 0 | 0 | 0% | 06-Mar-25 10:00 AM | 17-Apr-25 04:00 PM |  |  | 30.8d | 0.0d | 0 | 0%
A1870 | Cable Sheath Tests | 0 | 0 | 0 | 0 | 0 | 0% | 10-Apr-25 08:00 AM | 11-Apr-25 04:00 PM |  |  | 2.0d | 0.0d | 0 | 0%
A1880 | Joint & Terminate Cables to New Switchboard | 0 | 0 | 0 | 0 | 0 | 0% | 14-Apr-25 08:00 AM | 17-Apr-25 04:00 PM |  |  | 4.0d | 0.0d | 0 | 0%
A1890 | 11kV Pressure Tests | 0 | 0 | 0 | 0 | 0 | 0% | 06-May-25 08:00 AM | 06-May-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A2750 | Joint and terminate Cable to Transformer | 0 | 0 | 0 | 0 | 0 | 0% | 22-Apr-25 08:00 AM | 23-Apr-25 04:00 PM |  |  | 2.0d | 0.0d | 0 | 0%
449 | Test & Commissioning | 0 | 0 | 0 | 0 | 0 | 0% | 24-Apr-25 08:00 AM | 14-May-25 04:00 PM |  |  | 14.0d | 0.0d | 0
A1900 | SAP Updated | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 07-May-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1910 | Netmap Updated | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 07-May-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1920 | Demobilise from site | 0 | 0 | 0 | 0 | 0 | 0% | 14-May-25 08:00 AM | 14-May-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1930 | Hot Commissioning of Substation | 0 | 0 | 0 | 0 | 0 | 0% | 24-Apr-25 08:00 AM | 24-Apr-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1940 | Energisation | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 07-May-25 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A1950 | Protection Settings uploaded | 0 | 0 | 0 | 0 | 0 | 0% | 24-Apr-25 04:00 PM | 24-Apr-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
A1960 | Substation Under Rules | 0 | 0 | 0 | 0 | 0 | 0% | 24-Apr-25 08:00 AM | 24-Apr-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
6 | Closure | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 21-Aug-25 04:00 PM |  |  | 76.0d | 0.0d | 0
A1980 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 27-Jun-25 08:00 AM | 27-Jun-25 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A1990 | Review and Approve H&S File | 0 | 0 | 0 | 0 | 0 | 0% | 09-May-25 08:00 AM | 22-May-25 04:00 PM |  |  | 10.0d | 0.0d | 0 | 0%
A2000 | Financial Closure | 0 | 0 | 0 | 0 | 0 | 0% | 15-May-25 08:00 AM | 04-Aug-25 04:00 PM |  |  | 57.0d | 0.0d | 0 | 0%
A2010 | Familiarisation Training | 0 | 0 | 0 | 0 | 0 | 0% | 07-May-25 08:00 AM | 20-May-25 04:00 PM |  |  | 10.0d | 0.0d | 0 | 0%
A2020 | Deadline for submission of defined costs (65 days from contract completion) | 0 | 0 | 0 | 0 | 0 | 0% | 12-Jun-25 04:00 PM | 12-Jun-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 05-Aug-25 08:00 AM | 21-Aug-25 04:00 PM |  |  | 13.0d | 0.0d | 0
A2030 | Prepare Gate D Paper | 0 | 0 | 0 | 0 | 0 | 0% | 05-Aug-25 08:00 AM | 21-Aug-25 04:00 PM |  |  | 13.0d | 0.0d | 0 | 0%
A2040 | Submit Gate D Paper to RPrB | 0 | 0 | 0 | 0 | 0 | 0% | 21-Aug-25 04:00 PM | 21-Aug-25 04:00 PM |  |  | 0.0d | 0.0d | 0 | 0%