## Sheet1
Activity ID* | Activity Name* | BL Project Total Cost | Actual Total Cost | Remaining Total Cost | At Completion Total Cost | Variance BL Project - Total Cost | Performance % Complete | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Duration | Actual Duration | Planned Total Cost | Activity % Complete
X-E.IPJ.109211 | RAYLEIGH/CHELMSFORD(PSA) | 278795 | 264883 | 13912 | 278795 | 13912 | 95.01% | 21-Jun-24 08:00 AM | 13-Apr-26 04:00 PM | 20-Aug-24 08:00 AM | 20-Nov-25 08:00 AM | 452.0d | 457.0d | 278795
1 | Project Summary | 0 | 0 | 0 | 0 | 0 | 96.76% | 21-Jun-24 08:00 AM | 01-Apr-26 04:00 PM | 20-Aug-24 08:00 AM | 14-Nov-25 08:00 AM | 446.0d | 451.0d | 0
6 | Project Governance Milestones | 0 | 0 | 0 | 0 | 0 | 96.76% | 21-Jun-24 08:00 AM | 01-Apr-26 04:00 PM | 20-Aug-24 08:00 AM | 12-Nov-25 08:00 AM | 446.0d | 449.0d | 0
Gate1000 | Gate A Award | 0 | 0 | 0 | 0 | 0 | 100% | 21-Jun-24 08:00 AM | 21-Jun-24 08:00 AM | 20-Aug-24 08:00 AM | 20-Aug-24 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1010 | Gate B Award | 0 | 0 | 0 | 0 | 0 | 100% | 18-Apr-25 08:00 AM | 18-Apr-25 08:00 AM | 17-Jun-25 08:00 AM | 17-Jun-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate1020 | Gate C Award | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-25 04:00 PM | 09-May-25 04:00 PM | 08-Jul-25 04:00 PM | 08-Jul-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
Gate1050 | Gate D Award | 0 | 0 | 0 | 0 | 0 | 0% | 01-Apr-26 04:00 PM | 01-Apr-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
9 | Construction Delivery Milestones | 0 | 0 | 0 | 0 | 0 | 100% | 04-Jul-24 04:00 PM | 04-Mar-26 04:00 PM | 02-Sep-24 04:00 PM | 25-Oct-25 04:00 PM | 416.0d | 418.0d | 0
AL1000 | Project Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 04-Jul-24 04:00 PM | 04-Jul-24 04:00 PM | 02-Sep-24 04:00 PM | 02-Sep-24 04:00 PM | 0.0d | 0.0d | 0 | 100%
AL2010 | Award WPO Contract | 0 | 0 | 0 | 0 | 0 | 100% | 01-Aug-25 04:00 PM | 01-Aug-25 04:00 PM | 30-Sep-25 04:00 PM | 30-Sep-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1050 | Start on Site | 0 | 0 | 0 | 0 | 0 | 100% | 29-Oct-25 04:00 PM | 29-Oct-25 04:00 PM | 28-Dec-25 04:00 PM | 28-Dec-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1140 | Site Demobilisation Complete | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-26 04:00 PM | 04-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
DEL1100 | Energised | 0 | 0 | 0 | 0 | 0 | 100% | 03-Mar-26 04:00 PM | 03-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
DEL1070 | Practical Completion | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-26 04:00 PM | 04-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
DEL1010 | Concept Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 09-Apr-25 04:00 PM | 09-Apr-25 04:00 PM | 08-Jun-25 04:00 PM | 08-Jun-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1040 | Develped Design Signed off - CAP 02-017 | 0 | 0 | 0 | 0 | 0 | 100% | 01-May-25 04:00 PM | 01-May-25 04:00 PM | 30-Jun-25 04:00 PM | 30-Jun-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
7 | Project Closeout Milestones | 0 | 0 | 0 | 0 | 0 | 0% | 11-Mar-26 04:00 PM | 01-Apr-26 04:00 PM |  |  | 15.0d |  | 0
CLO1000 | Project Completion | 0 | 0 | 0 | 0 | 0 | 0% | 01-Apr-26 04:00 PM | 01-Apr-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1020 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 12-Mar-26 04:00 PM | 12-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
CLO1050 | As-Built Records Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 11-Mar-26 04:00 PM | 11-Mar-26 04:00 PM |  |  | 0.0d |  | 0 | 100%
CLO1010 | Completion Certificate Signed off | 0 | 0 | 0 | 0 | 0 | 0% | 01-Apr-26 04:00 PM | 01-Apr-26 04:00 PM |  |  | 0.0d |  | 0 | 0%
2 | Pre Gate B | 0 | 0 | 0 | 0 | 0 | 100% | 05-Jul-24 08:00 AM | 22-May-25 04:00 PM | 03-Sep-24 08:00 AM | 16-Apr-25 08:00 AM | 220.0d | 225.0d | 0
Gate2030 | Submit Gate B Paper to RPfB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 100% | 15-Apr-25 08:00 AM | 15-Apr-25 08:00 AM | 14-Jun-25 08:00 AM | 14-Jun-25 08:00 AM | 0.0d | 0.0d | 0 | 100%
Gate2000 | Prepare Gate B Paper | 0 | 0 | 0 | 0 | 0 | 100% | 10-Apr-25 08:00 AM | 14-Apr-25 04:00 PM | 09-Jun-25 08:00 AM | 17-Jun-25 08:00 AM | 3.0d | 8.0d | 0 | 100%
A5160 | Design Survey | 0 | 0 | 0 | 0 | 0 | 100% | 05-Jul-24 08:00 AM | 11-Jul-24 04:00 PM | 03-Sep-24 08:00 AM | 10-Sep-24 08:00 AM | 5.0d | 7.0d | 0 | 100%
A5170 | Concept Design | 0 | 0 | 0 | 0 | 0 | 100% | 12-Jul-24 08:00 AM | 04-Apr-25 04:00 PM | 10-Sep-24 08:00 AM | 16-Mar-25 08:00 AM | 184.0d | 187.0d | 0 | 100%
A5180 | Concept Design CAP02 - 17 | 0 | 0 | 0 | 0 | 0 | 100% | 07-Apr-25 08:00 AM | 09-Apr-25 04:00 PM | 06-Jun-25 08:00 AM | 14-Jun-25 08:00 AM | 3.0d | 8.0d | 0 | 100%
A5250 | Direct Costs 2024 | 0 | 0 | 0 | 0 | 0 | 100% | 30-Sep-24 08:00 AM | 22-May-25 04:00 PM | 29-Nov-24 08:00 AM | 10-May-25 08:00 AM | 160.0d | 162.0d | 0 | 100%
A5260 | In Direct Costs 2024 | 0 | 0 | 0 | 0 | 0 | 100% | 05-Jul-24 08:00 AM | 22-May-25 04:00 PM | 03-Sep-24 08:00 AM | 14-Apr-25 08:00 AM | 220.0d | 223.0d | 0 | 100%
3 | Gate B-C | 0 | 0 | 0 | 0 | 0 | 100% | 22-Apr-25 08:00 AM | 18-Sep-25 04:00 PM | 21-Jun-25 08:00 AM | 06-Oct-25 08:00 AM | 105.0d | 107.0d | 0
A2780 | B to C Kick Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 22-Apr-25 08:00 AM | 22-Apr-25 04:00 PM | 21-Jun-25 08:00 AM | 27-Jun-25 08:00 AM | 1.0d | 6.0d | 0 | 100%
A2790 | Detail Design | 0 | 0 | 0 | 0 | 0 | 100% | 23-Apr-25 08:00 AM | 29-Apr-25 04:00 PM | 22-Jun-25 08:00 AM | 02-Jul-25 08:00 AM | 5.0d | 10.0d | 0 | 100%
A3030 | Place Procurement Order | 0 | 0 | 0 | 0 | 0 | 100% | 22-Apr-25 08:00 AM | 28-Apr-25 04:00 PM | 21-Jun-25 08:00 AM | 29-Jun-25 08:00 AM | 5.0d | 8.0d | 0 | 100%
A3035 | Developed Design CAP02 -17 | 0 | 0 | 0 | 0 | 0 | 100% | 29-Apr-25 08:00 AM | 01-May-25 04:00 PM | 28-Jun-25 08:00 AM | 06-Jul-25 08:00 AM | 3.0d | 8.0d | 0 | 100%
Gate1031 | Prepare Gate C Paper | 0 | 0 | 0 | 0 | 0 | 100% | 02-May-25 08:00 AM | 09-May-25 04:00 PM | 01-Jul-25 08:00 AM | 08-Jul-25 08:00 AM | 5.0d | 7.0d | 0 | 100%
Gate1041 | Submit Gate C Paper to RPfB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-25 04:00 PM | 09-May-25 04:00 PM | 08-Jul-25 04:00 PM | 08-Jul-25 04:00 PM | 0.0d | 0.0d | 0 | 100%
Q3056 | Prepare WPO / PO | 0 | 0 | 0 | 0 | 0 | 100% | 21-Jul-25 08:00 AM | 01-Aug-25 04:00 PM | 19-Sep-25 08:00 AM | 04-Oct-25 08:00 AM | 10.0d | 15.0d | 0 | 100%
A5010 | Manufacture of Long Lead items | 0 | 0 | 0 | 0 | 0 | 100% | 29-Apr-25 08:00 AM | 18-Sep-25 04:00 PM | 28-Jun-25 08:00 AM | 08-Oct-25 08:00 AM | 100.0d | 102.0d | 0 | 100%
A5230 | Direct Costs 2024 | 0 | 0 | 0 | 0 | 0 | 100% | 22-Apr-25 08:00 AM | 18-Sep-25 04:00 PM | 21-Jun-25 08:00 AM | 07-Oct-25 08:00 AM | 105.0d | 108.0d | 0 | 100%
A5240 | In Direct Costs 2024 | 0 | 0 | 0 | 0 | 0 | 100% | 22-Apr-25 08:00 AM | 18-Sep-25 04:00 PM | 21-Jun-25 08:00 AM | 06-Oct-25 08:00 AM | 105.0d | 107.0d | 0 | 100%
4 | Gate C-D | 278795 | 242273 | 36522 | 278795 | 36522 | 86.9% | 04-Aug-25 08:00 AM | 13-Apr-26 04:00 PM | 03-Oct-25 08:00 AM | 29-Mar-26 08:00 AM | 172.0d | 177.0d | 278795
3 | Procurement | 0 | 0 | 0 | 0 | 0 | 100% | 18-Aug-25 08:00 AM | 02-Oct-25 04:00 PM | 17-Oct-25 08:00 AM | 24-Nov-25 08:00 AM | 33.0d | 38.0d | 0
A5190 | FAT Test Payment | 0 | 0 | 0 | 0 | 0 | 100% | 18-Aug-25 08:00 AM | 21-Aug-25 08:00 AM | 17-Oct-25 08:00 AM | 23-Oct-25 08:00 AM | 3.0d | 6.0d | 0 | 100%
A5200 | Delivery to Site | 0 | 0 | 0 | 0 | 0 | 100% | 19-Sep-25 08:00 AM | 02-Oct-25 04:00 PM | 18-Nov-25 08:00 AM | 03-Dec-25 08:00 AM | 10.0d | 15.0d | 0 | 100%
4 | Construction | 278795 | 278795 | 0 | 278795 | 0 | 100% | 04-Aug-25 08:00 AM | 04-Mar-26 04:00 PM | 03-Oct-25 08:00 AM | 28-Feb-26 08:00 AM | 146.0d | 148.0d | 278795
A4480 | Direct Costs 2024 | 278795 | 278795 | 0 | 278795 | 0 | 100% | 30-Sep-25 08:00 AM | 05-Dec-25 04:00 PM | 29-Nov-25 08:00 AM | 20-Jan-26 08:00 AM | 49.0d | 52.0d | 278795 | 100%
T2650 | Mobilisation of Principle Contractor | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-25 08:00 AM | 29-Oct-25 04:00 PM | 03-Oct-25 08:00 AM | 09-Dec-25 08:00 AM | 62.0d | 67.0d | 0 | 100%
CLO130 | Demobilise from site | 0 | 0 | 0 | 0 | 0 | 100% | 04-Mar-26 08:00 AM | 04-Mar-26 04:00 PM |  |  | 1.0d |  | 0 | 100%
A2950 | Energisation | 0 | 0 | 0 | 0 | 0 | 100% | 25-Feb-26 08:00 AM | 03-Mar-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
A5100 | On Site Works - Civils | 0 | 0 | 0 | 0 | 0 | 100% | 30-Oct-25 08:00 AM | 31-Dec-25 04:00 PM | 29-Dec-25 08:00 AM | 09-Feb-26 08:00 AM | 40.0d | 42.0d | 0 | 100%
A5210 | On Site Works - Electrical | 0 | 0 | 0 | 0 | 0 | 100% | 02-Jan-26 08:00 AM | 24-Feb-26 04:00 PM | 03-Mar-26 08:00 AM | 15-Apr-26 08:00 AM | 38.0d | 43.0d | 0 | 100%
A5220 | In Direct Costs 2024 | 0 | 0 | 0 | 0 | 0 | 100% | 04-Aug-25 08:00 AM | 04-Mar-26 04:00 PM | 03-Oct-25 08:00 AM | 03-Mar-26 08:00 AM | 146.0d | 151.0d | 0 | 100%
6 | Closure | 0 | 0 | 0 | 0 | 0 | 15.38% | 05-Mar-26 08:00 AM | 13-Apr-26 04:00 PM |  |  | 26.0d |  | 0
A4730 | As-Build Drawings review | 0 | 0 | 0 | 0 | 0 | 100% | 05-Mar-26 08:00 AM | 11-Mar-26 04:00 PM |  |  | 5.0d |  | 0 | 100%
CLO3100 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 12-Mar-26 08:00 AM | 12-Mar-26 04:00 PM |  |  | 1.0d |  | 0 | 0%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 13-Mar-26 08:00 AM | 13-Apr-26 04:00 PM |  |  | 20.0d |  | 0
Gate1070 | Prepare Gate D Paper | 0 | 0 | 0 | 0 | 0 | 0% | 13-Mar-26 08:00 AM | 13-Apr-26 04:00 PM |  |  | 20.0d |  | 0 | 0%
Gate1080 | Submit Gate D Paper to RPrB (AST 01 004 > £1m) | 0 | 0 | 0 | 0 | 0 | 0% | 13-Apr-26 04:00 PM | 13-Apr-26 04:00 PM |  |  | 0.0d |  | 0 | 0%