## Sheet1
Activity ID* | Activity Name* | BL Project Total Cost | Actual Total Cost | Remaining Total Cost | At Completion Total Cost | Variance BL Project - Total Cost | Performance % Complete | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Duration | Actual Duration | Planned Total Cost | Activity % Complete
M-E.MCN.108096 | **Awaiting Gate D** EJH (NTR) A47/A11 Thickthorn Jtn, NR4 6TD - 33kV Diversion | 269473 | 245222 | 0 | 245222 | 24251 | 99.97% | 02-Aug-21 04:00 PM | 01-Oct-24 04:00 PM | 02-Aug-21 04:00 PM |  | 789.0d | 788.0d | 262045
1 | Project Summary | 269473 | 245222 | 0 | 245222 | 24251 | 99.97% | 02-Aug-21 04:00 PM | 01-Oct-24 04:00 PM | 02-Aug-21 04:00 PM |  | 789.0d | 788.0d | 262045
ProjKM1010 | Start on Site | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 13-Jun-22 08:00 AM | 13-Jun-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM1020 | Customer Connection Date | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM1890 | Project Complete (on-site) | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM1380 | Project Closure | 0 | 0 | 0 | 0 | 0 | 0% | 01-Oct-24 08:00 AM | 01-Oct-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
ProjKM2110 | Design start - concept - N/A - Small job, no CAP 015 as working off of original mandate | 0 | 0 | 0 | 0 | 0 | 100% | 12-Oct-21 04:00 PM | 12-Oct-21 04:00 PM | 12-Oct-21 04:00 PM | 12-Oct-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM2120 | Concept Design finished & Signed Off - N/A - Small job, no CAP 015 as working off of original mandate | 0 | 0 | 0 | 0 | 0 | 100% | 14-Dec-21 04:00 PM | 14-Dec-21 04:00 PM | 14-Dec-21 04:00 PM | 14-Dec-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
OP&CM01 | Consents Conveyancing Pack & Submission | 0 | 0 | 0 | 0 | 0 | 100% | 18-Jan-22 04:00 PM | 18-Jan-22 04:00 PM | 18-Jan-22 04:00 PM | 18-Jan-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
OP&CM02 | Consent Executed | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-22 08:00 AM | 01-Jun-22 08:00 AM | 01-Jun-22 08:00 AM | 01-Jun-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM2070 | Gate B PAIF or FCAF Gate C Docuement Recieved | 0 | 0 | 0 | 0 | 0 | 100% | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM1339 | Milestone - Asset Data Updated ( Ellipse & Netmap ) | 0 | 0 | 0 | 0 | 0 | 100% | 17-Oct-22 08:00 AM | 17-Oct-22 08:00 AM | 17-Oct-22 08:00 AM | 17-Oct-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM20802 | CPP Project Kick-Off Meeting | 0 | 0 | 0 | 0 | 0 | 100% | 05-Oct-21 04:00 PM | 05-Oct-21 04:00 PM | 05-Oct-21 04:00 PM | 05-Oct-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
Proposal01 | Receive ADM Quote or Proposal | 0 | 0 | 0 | 0 | 0 | 100% | 06-May-22 04:00 PM | 06-May-22 04:00 PM | 06-May-22 04:00 PM | 06-May-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
Proposal11 | Small Works Package Order (SWPO) issue/award for Construction | 0 | 0 | 0 | 0 | 0 | 100% | 06-Jun-22 04:00 PM | 06-Jun-22 04:00 PM | 06-Jun-22 04:00 PM | 06-Jun-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
DesRevStge2 | Design Review Stage 2 (If Needed) | 0 | 0 | 0 | 0 | 0 | 100% | 14-Dec-21 08:00 AM | 14-Dec-21 08:00 AM | 14-Dec-21 08:00 AM | 14-Dec-21 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM2130 | Design start - Developed Design - N/A - Small job, no CAP 015 as working off of original mandate | 0 | 0 | 0 | 0 | 0 | 100% | 14-Dec-21 04:00 PM | 14-Dec-21 04:00 PM | 14-Dec-21 04:00 PM | 14-Dec-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM4620 | Completion Certificate Signed off | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-22 04:00 PM | 12-Aug-22 04:00 PM | 12-Aug-22 04:00 PM | 12-Aug-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM4630 | Asset Energised | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 12-Aug-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
ProjKM4640 | Developed Design finished & Signed Off - N/A - Small job, no CAP 015 as working off of original mandate | 0 | 0 | 0 | 0 | 0 | 100% | 06-May-22 04:00 PM | 06-May-22 04:00 PM | 06-May-22 04:00 PM | 06-May-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
Proposal20 | Prepare SWPO | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-22 08:00 AM | 16-May-22 04:00 PM | 09-May-22 08:00 AM | 16-May-22 04:00 PM | 6.0d | 6.0d | 0 | 100%
ProjKM2080 | Project Quote Date | 0 | 0 | 0 | 0 | 0 | 100% | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM2090 | Project Customer Acceptance Date | 0 | 0 | 0 | 0 | 0 | 100% | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProjKM2100 | Project allocation Date to PM by Portfolio Manager | 0 | 0 | 0 | 0 | 0 | 100% | 03-Aug-21 08:00 AM | 09-Aug-21 04:00 PM | 03-Aug-21 08:00 AM | 09-Aug-21 04:00 PM | 5.0d | 5.0d | 0 | 100%
ProjKM2150 | Handover Meeting Between Connections & CPP | 0 | 0 | 0 | 0 | 0 | 100% | 06-Aug-21 08:00 AM | 06-Aug-21 04:00 PM | 06-Aug-21 08:00 AM | 06-Aug-21 04:00 PM | 1.0d | 1.0d | 0 | 100%
ProjKM2160 | Customer Payment Date | 0 | 0 | 0 | 0 | 0 | 100% | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 02-Aug-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
DEL1070 | Practical Completion |  | 0 | 0 | 0 |  | 100% | 12-Aug-22 04:00 PM | 12-Aug-22 04:00 PM | 12-Aug-22 04:00 PM | 12-Aug-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
OP&CM12 | Heads of Terms Agreed. (Mackintosh Trust) |  | 0 | 0 | 0 |  | 0% | 01-Oct-24 08:00 AM | 01-Oct-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
7 | Gate B-C | 22282 | 233 | 0 | 233 | 22049 | 100% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 25-May-23 04:00 PM | 389.0d | 449.0d | 15394
31 | Project Management | 0 | 233 | 0 | 233 | (233) | 0% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 12-Aug-22 04:00 PM | 389.0d | 257.0d | 3112
311 | Project Manager | 0 | 233 | 0 | 233 | (233) | 0% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 12-Aug-22 04:00 PM | 389.0d | 257.0d | 3112
PM2000PROJ | Project Manager | 0 | 233 | 0 | 233 | (233) | 100% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 12-Aug-22 04:00 PM | 389.0d | 257.0d | 3112 | 100%
312 | Quantitiy Surveyor | 0 | 0 | 0 | 0 | 0 | 0% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 12-Aug-22 04:00 PM | 389.0d | 257.0d | 0
PM2030QS | QS | 0 | 0 | 0 | 0 | 0 | 100% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 12-Aug-22 04:00 PM | 390.0d | 257.0d | 0 | 100%
313 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 0% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 12-Aug-22 04:00 PM | 389.0d | 257.0d | 0
PM2040P6 | Project Planner P6 | 0 | 0 | 0 | 0 | 0 | 100% | 03-Aug-21 08:00 AM | 24-Feb-23 04:00 PM | 02-Aug-21 04:00 PM | 12-Aug-22 04:00 PM | 390.0d | 257.0d | 0 | 100%
32 | Design / Surveys / OP&C | 22282 | 0 | 0 | 0 | 22282 | 100% | 13-Oct-21 08:00 AM | 17-Oct-22 04:00 PM | 12-Oct-21 04:00 PM | 25-May-23 04:00 PM | 251.0d | 399.0d | 12282
322 | Concept Design | 0 | 0 | 0 | 0 | 0 | 0% | 13-Oct-21 08:00 AM | 21-Jun-22 04:00 PM | 12-Oct-21 04:00 PM | 12-Aug-22 04:00 PM | 169.0d | 207.0d | 0
D2020CDMC30 | Design Clerk | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-21 08:00 AM | 28-Feb-22 04:00 PM | 13-Oct-21 08:00 AM | 12-Aug-22 04:00 PM | 93.0d | 207.0d | 0 | 100%
PMB-C2020 | Principal Design Co-ordinator/SHES - Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-21 08:00 AM | 02-Mar-22 04:00 PM | 12-Oct-21 04:00 PM | 12-Aug-22 04:00 PM | 95.0d | 207.0d | 0 | 100%
D2020CDMC40 | CAD Design Technician | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-21 08:00 AM | 28-Feb-22 04:00 PM | 13-Oct-21 08:00 AM | 12-Aug-22 04:00 PM | 93.0d | 207.0d | 0 | 100%
PMB-C2030 | Wayleaves - Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-21 08:00 AM | 02-Mar-22 04:00 PM | 12-Oct-21 04:00 PM | 12-Aug-22 04:00 PM | 95.0d | 207.0d | 0 | 100%
D2020CDMC60 | Document Controller | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-21 08:00 AM | 28-Feb-22 04:00 PM | 13-Oct-21 08:00 AM | 12-Aug-22 04:00 PM | 93.0d | 207.0d | 0 | 100%
PMB-C2040 | HSE Advisor - Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-21 08:00 AM | 02-Mar-22 04:00 PM | 12-Oct-21 04:00 PM | 12-Aug-22 04:00 PM | 95.0d | 207.0d | 0 | 100%
ME-CON-DES | M&E Concept Design | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jan-22 08:00 AM | 21-Jun-22 04:00 PM | 20-Jan-22 08:00 AM | 12-Aug-22 04:00 PM | 104.0d | 142.0d | 0
D2020CDMC | CDMC | 0 | 0 | 0 | 0 | 0 | 100% | 20-Jan-22 08:00 AM | 21-Jun-22 04:00 PM | 20-Jan-22 08:00 AM | 12-Aug-22 04:00 PM | 104.0d | 142.0d | 0 | 100%
SUR | Surveys (move if in dvlp design) | 22282 | 0 | 0 | 0 | 22282 | 100% | 13-Oct-21 08:00 AM | 22-Sep-22 04:00 PM | 13-Oct-21 08:00 AM | 25-May-23 04:00 PM | 234.0d | 399.0d | 12282
Design-2010CD | Concept Design (Civils) completed | 0 | 0 | 0 | 0 | 0 | 100% | 02-Nov-21 08:00 AM | 06-Dec-21 04:00 PM | 02-Nov-21 08:00 AM | 06-Dec-21 04:00 PM | 25.0d | 25.0d | 0 | 100%
Design-2010CD4550 | Surveys | 0 | 0 | 0 | 0 | 0 | 100% | 13-Oct-21 08:00 AM | 26-Oct-21 04:00 PM | 13-Oct-21 08:00 AM | 26-Oct-21 04:00 PM | 10.0d | 10.0d | 0 | 100%
Design-2010CD4560 | Concept Survey Information Accepted | 0 | 0 | 0 | 0 | 0 | 100% | 01-Nov-21 04:00 PM | 01-Nov-21 04:00 PM | 01-Nov-21 04:00 PM | 01-Nov-21 04:00 PM | 0.0d | 0.0d | 0 | 100%
Design-2010CD10 | Form B Produced | 0 | 0 | 0 | 0 | 0 | 100% | 07-Dec-21 08:00 AM | 09-Dec-21 04:00 PM | 07-Dec-21 08:00 AM | 09-Dec-21 04:00 PM | 3.0d | 3.0d | 0 | 100%
Design-2010CD20 | Agreement of CU Budget | 0 | 0 | 0 | 0 | 0 | 100% | 07-Dec-21 08:00 AM | 13-Dec-21 04:00 PM | 07-Dec-21 08:00 AM | 13-Dec-21 04:00 PM | 5.0d | 5.0d | 0 | 100%
C2110 | Variations to Customer / EOL forecast goes above Baseline? | 22282 | 0 | 0 | 0 | 22282 | 100% | 15-Sep-22 08:00 AM | 22-Sep-22 04:00 PM | 15-Sep-22 08:00 AM | 25-May-23 04:00 PM | 5.0d | 170.0d | 12282 | 100%
Design-2010CD5070 | Concept Design (Electrical) completed | 0 | 0 | 0 | 0 | 0 | 100% | 02-Nov-21 08:00 AM | 06-Dec-21 04:00 PM | 02-Nov-21 08:00 AM | 06-Dec-21 04:00 PM | 25.0d | 25.0d | 0 | 100%
323 | Developed Design | 0 | 0 | 0 | 0 | 0 | 0% | 22-Dec-21 08:00 AM | 24-Jan-22 04:00 PM | 22-Dec-21 08:00 AM | 07-Jun-22 04:00 PM | 18.0d | 109.0d | 0
Design-2090DD | Gen Drawing completed | 0 | 0 | 0 | 0 | 0 | 100% | 22-Dec-21 08:00 AM | 19-Jan-22 04:00 PM | 22-Dec-21 08:00 AM | 19-Jan-22 04:00 PM | 15.0d | 15.0d | 0 | 100%
Design-2090DD10 | Material schedule produced | 0 | 0 | 0 | 0 | 0 | 100% | 20-Jan-22 08:00 AM | 24-Jan-22 04:00 PM | 20-Jan-22 08:00 AM | 07-Jun-22 04:00 PM | 3.0d | 94.0d | 0 | 100%
1 | HDD Design | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jan-22 08:00 AM | 17-Oct-22 04:00 PM | 20-Jan-22 08:00 AM | 12-Aug-22 04:00 PM | 186.0d | 142.0d | 0
1 | Summary | 0 | 0 | 0 | 0 | 0 | 0% | 10-May-22 08:00 AM | 17-Oct-22 04:00 PM | 26-Apr-22 04:00 PM | 12-Aug-22 04:00 PM | 111.0d | 75.0d | 0
2Cost_Indirect_B0010_Y21 | Indirect Cost Bar - Freedom Contractor Design Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 10-May-22 08:00 AM | 17-Oct-22 04:00 PM | 26-Apr-22 04:00 PM | 12-Aug-22 04:00 PM | 111.0d | 75.0d | 0 | 100%
2Cost_Indirect_B0010_Y41 | Direct Cost Bar - Freedom Contractor Design Cost Bar | 0 | 0 | 0 | 0 | 0 | 100% | 10-May-22 08:00 AM | 17-Oct-22 04:00 PM | 26-Apr-22 04:00 PM | 12-Aug-22 04:00 PM | 111.0d | 75.0d | 0 | 100%
2 | Deliverable | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jan-22 08:00 AM | 08-Jun-22 04:00 PM | 20-Jan-22 08:00 AM | 08-Jun-22 04:00 PM | 95.0d | 95.0d | 0
A5160 | Freedom Prepare HDD Design | 0 | 0 | 0 | 0 | 0 | 100% | 20-Jan-22 08:00 AM | 02-Mar-22 04:00 PM | 20-Jan-22 08:00 AM | 01-Jun-22 08:00 AM | 30.0d | 91.0d | 0 | 100%
A5170 | HDD Design Review / Comments / Approval | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-22 08:00 AM | 08-Jun-22 04:00 PM | 01-Jun-22 08:00 AM | 08-Jun-22 04:00 PM | 4.0d | 4.0d | 0 | 100%
324 | OP&C Wayleave/Planng Permission/Consents | 0 | 0 | 0 | 0 | 0 | 0% | 15-Dec-21 08:00 AM | 29-Apr-22 04:00 PM | 15-Dec-21 08:00 AM | 01-Jun-22 04:00 PM | 90.0d | 112.0d | 0
OP&C2130 | Wayleaves Permissions /Consents (Direct/External payments) | 0 | 0 | 0 | 0 | 0 | 100% | 15-Dec-21 08:00 AM | 29-Apr-22 04:00 PM | 15-Dec-21 08:00 AM | 01-Jun-22 04:00 PM | 90.0d | 112.0d | 0 | 100%
34 | Gate C Governance | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jan-22 08:00 AM | 09-May-22 04:00 PM | 20-Jan-22 08:00 AM | 26-Apr-22 04:00 PM | 75.0d | 67.0d | 0
GateC80 | Prepare Gate C Paper (If Applicable) | 0 | 0 | 0 | 0 | 0 | 100% | 19-Apr-22 08:00 AM | 25-Apr-22 04:00 PM | 19-Apr-22 08:00 AM | 25-Apr-22 04:00 PM | 5.0d | 5.0d | 0 | 100%
GateC100 | Gate C Award (If Applicable) | 0 | 0 | 0 | 0 | 0 | 100% | 09-May-22 08:00 AM | 09-May-22 04:00 PM | 26-Apr-22 08:00 AM | 26-Apr-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
GateC110 | Awaiting Customer Stage Payment on Delivery Stage / Material Orders | 0 | 0 | 0 | 0 | 0 | 100% | 20-Jan-22 08:00 AM | 16-Feb-22 04:00 PM | 20-Jan-22 08:00 AM | 16-Mar-22 04:00 PM | 20.0d | 40.0d | 0 | 100%
8 | Gate C-D | 247191 | 244989 | 0 | 244989 | 2202 | 99.97% | 03-Feb-22 08:00 AM | 01-Oct-24 04:00 PM | 01-Feb-22 08:00 AM |  | 664.0d | 665.0d | 246651
41 | Project Management | 7286 | 13284 | 0 | 13284 | (5,998) | 99% | 10-May-22 08:00 AM | 21-Mar-23 04:00 PM | 26-Apr-22 04:00 PM |  | 216.0d | 606.0d | 7848
411 | Project Manager | 0 | 0 | 0 | 0 | 0 | 0% | 10-May-22 08:00 AM | 21-Mar-23 04:00 PM | 26-Apr-22 04:00 PM |  | 216.0d | 606.0d | 0
PM2000PROJ10 | Project Manager | 0 | 0 | 0 | 0 | 0 | 99% | 10-May-22 08:00 AM | 21-Mar-23 04:00 PM | 26-Apr-22 04:00 PM |  | 216.0d | 606.0d | 0 | 99%
412 | Quantitiy Surveyor | 0 | 0 | 0 | 0 | 0 | 0% | 10-May-22 08:00 AM | 21-Mar-23 04:00 PM | 26-Apr-22 04:00 PM | 12-Aug-22 04:00 PM | 216.0d | 75.0d | 0
PM2030QS10 | QS | 0 | 0 | 0 | 0 | 0 | 100% | 10-May-22 08:00 AM | 21-Mar-23 04:00 PM | 26-Apr-22 04:00 PM | 12-Aug-22 04:00 PM | 216.0d | 75.0d | 0 | 100%
413 | P6 Planner | 0 | 0 | 0 | 0 | 0 | 0% | 10-May-22 08:00 AM | 21-Mar-23 04:00 PM | 26-Apr-22 04:00 PM |  | 216.0d | 606.0d | 0
PM2040P16 | Project Planner P6 | 0 | 0 | 0 | 0 | 0 | 99% | 10-May-22 08:00 AM | 21-Mar-23 04:00 PM | 26-Apr-22 04:00 PM |  | 216.0d | 606.0d | 0 | 99%
414 | Construction Management | 7286 | 13284 | 0 | 13284 | (5,998) | 99% | 13-Jun-22 08:00 AM | 01-Dec-22 04:00 PM | 13-Jun-22 08:00 AM |  | 122.0d | 576.0d | 7848
2Cost_Indirect_B0010_Y31 | Indirect Cost Bar - Internal | 7286 | 13284 | 0 | 13284 | (5,998) | 99% | 13-Jun-22 08:00 AM | 01-Dec-22 04:00 PM | 13-Jun-22 08:00 AM |  | 122.0d | 576.0d | 7848 | 99%
42 | Design / Surveys / OP&C Gate C-D | 0 | 0 | 0 | 0 | 0 | 0% | 01-Jun-22 08:00 AM | 08-Jun-22 04:00 PM | 01-Jun-22 08:00 AM | 08-Jun-22 04:00 PM | 4.0d | 4.0d | 0
Design-2010CD4830 | Design issued for Construction - Handover to Construction Team | 0 | 0 | 0 | 0 | 0 | 100% | 08-Jun-22 04:00 PM | 08-Jun-22 04:00 PM | 08-Jun-22 04:00 PM | 08-Jun-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
Design-2010CD4960 | Pre-Construction Information - PCI Documentation ((CAP 03 003) | 0 | 0 | 0 | 0 | 0 | 100% | 01-Jun-22 08:00 AM | 01-Jun-22 08:00 AM | 01-Jun-22 08:00 AM | 01-Jun-22 08:00 AM | 0.0d | 0.0d | 0 | 100%
43 | Procurement | 52819 | 54337 | 0 | 54337 | (1,518) | 100% | 07-Jun-22 04:00 PM | 01-Sep-22 04:00 PM | 05-May-22 04:00 PM | 12-Aug-22 04:00 PM | 61.0d | 69.0d | 51718
ProcM1250 | Cable / Ducts delivery to site | 52819 | 54337 | 0 | 54337 | (1,518) | 100% | 27-Jun-22 08:00 AM | 27-Jun-22 04:00 PM | 27-Jun-22 08:00 AM | 27-Jun-22 04:00 PM | 1.0d | 1.0d | 51718 | 100%
PROCM1260 | Lead Time on Cable / Ducts | 0 | 0 | 0 | 0 | 0 | 100% | 08-Jun-22 08:00 AM | 03-Aug-22 04:00 PM | 06-May-22 08:00 AM | 05-Jul-22 08:00 AM | 41.0d | 40.0d | 0 | 100%
ProcM1255 | OHL / Joints / Tile Tape Materials delivery to site | 0 | 0 | 0 | 0 | 0 | 100% | 01-Sep-22 08:00 AM | 01-Sep-22 04:00 PM | 05-Jul-22 08:00 AM | 05-Jul-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
PROCM1270 | Lead Time on OHL Materials | 0 | 0 | 0 | 0 | 0 | 100% | 08-Jun-22 08:00 AM | 03-Aug-22 04:00 PM | 06-May-22 08:00 AM | 05-Jul-22 08:00 AM | 41.0d | 40.0d | 0 | 100%
ProcM001 | Order key Materials : Cable / Ducts | 0 | 0 | 0 | 0 | 0 | 100% | 07-Jun-22 04:00 PM | 07-Jun-22 04:00 PM | 05-May-22 04:00 PM | 05-May-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
ProcM002 | Order key Materials : OHL | 0 | 0 | 0 | 0 | 0 | 100% | 07-Jun-22 04:00 PM | 07-Jun-22 04:00 PM | 05-May-22 04:00 PM | 05-May-22 04:00 PM | 0.0d | 0.0d | 0 | 100%
2Cost_Direct_0001_Y11 | Direct Cost Bar - Material | 0 | 0 | 0 | 0 | 0 | 100% | 08-Jun-22 08:00 AM | 04-Jul-22 04:00 PM | 08-Jun-22 08:00 AM | 12-Aug-22 04:00 PM | 19.0d | 48.0d | 0 | 100%
44 | Construction | 187086 | 177368 | 0 | 177368 | 9718 | 100% | 03-Feb-22 08:00 AM | 30-Sep-22 04:00 PM | 01-Feb-22 08:00 AM | 20-Dec-23 04:00 PM | 165.0d | 473.0d | 187086
1Cost_Direct_0001_Y81 | Direct Cost Bar - Other - Land Rental for Compound Use | 0 | 0 | 0 | 0 | 0 | 100% | 13-Jun-22 08:00 AM | 30-Sep-22 04:00 PM | 13-Jun-22 08:00 AM | 12-Aug-22 04:00 PM | 78.0d | 45.0d | 0 | 100%
1Cost_Direct_0001_Y91 | RSK Adas Limited | 525 | 0 | 0 | 0 | 525 | 100% | 01-Mar-22 08:00 AM | 01-Mar-22 09:00 AM | 01-Feb-22 08:00 AM | 28-Feb-22 09:00 AM | 0.1d | 19.1d | 525 | 100%
1Cost_Direct_0001_Y111 | Savills PLC | 1270 | 975 | 0 | 975 | 295 | 100% | 01-Apr-22 08:00 AM | 01-Apr-22 09:00 AM | 01-Mar-22 08:00 AM | 20-Dec-23 04:00 PM | 0.1d | 453.0d | 1270 | 100%
442 | Mobilisation | 0 | 0 | 0 | 0 | 0 | 0% | 13-Jun-22 08:00 AM | 07-Jul-22 04:00 PM | 13-May-22 08:00 AM | 17-Jun-22 04:00 PM | 19.0d | 24.0d | 0
MOB4650 | Pre-Site Mobilisation of Contractor | 0 | 0 | 0 | 0 | 0 | 100% | 13-Jun-22 08:00 AM | 07-Jul-22 04:00 PM | 13-May-22 08:00 AM | 10-Jun-22 04:00 PM | 19.0d | 19.0d | 0 | 100%
MOB4660 | Site Setup | 0 | 0 | 0 | 0 | 0 | 100% | 13-Jun-22 08:00 AM | 17-Jun-22 04:00 PM | 13-Jun-22 08:00 AM | 17-Jun-22 04:00 PM | 5.0d | 5.0d | 0 | 100%
3 | Vegetation | 18004 | 9107 | 0 | 9107 | 8898 | 100% | 03-Feb-22 08:00 AM | 15-Mar-22 04:00 PM | 03-Feb-22 08:00 AM | 31-Mar-22 04:00 PM | 29.0d | 41.0d | 18004
A5140 | Vegetation | 15001 | 9107 | 0 | 9107 | 5894 | 100% | 03-Feb-22 08:00 AM | 23-Feb-22 04:00 PM | 03-Feb-22 08:00 AM | 31-Mar-22 04:00 PM | 15.0d | 41.0d | 15001 | 100%
A5200 | Freedom Indirect (Veg) | 3004 | 0 | 0 | 0 | 3004 | 100% | 14-Mar-22 08:00 AM | 15-Mar-22 04:00 PM | 14-Mar-22 08:00 AM | 15-Mar-22 04:00 PM | 2.0d | 2.0d | 3004 | 100%
4 | Freedom Main Works | 167286 | 167286 | 0 | 167286 | 0 | 100% | 01-Apr-22 08:00 AM | 30-Sep-22 04:00 PM | 01-Mar-22 08:00 AM | 01-Sep-22 04:00 PM | 124.0d | 127.0d | 167286
1Cost_Direct_0001_Y1 | Direct Cost Bar - Contractor - Freedom Staff & Prelims | 17949 | 17949 | 0 | 17949 | 0 | 100% | 13-Jun-22 08:00 AM | 30-Sep-22 04:00 PM | 13-Jun-22 08:00 AM | 12-Aug-22 04:00 PM | 78.0d | 45.0d | 17949 | 100%
1Cost_Direct_0001_Y71 | Direct Cost Bar - Contractor - Freedom Site Estb. | 29823 | 30385 | 0 | 30385 | (561) | 100% | 13-Jun-22 08:00 AM | 30-Sep-22 04:00 PM | 13-Jun-22 08:00 AM | 12-Aug-22 04:00 PM | 78.0d | 45.0d | 29823 | 100%
1Cost_Direct_0001_Y101 | Freedom Indirect | 18582 | 18021 | 0 | 18021 | 561 | 100% | 01-Apr-22 08:00 AM | 01-Apr-22 09:00 AM | 01-Mar-22 08:00 AM | 12-Aug-22 09:00 AM | 0.1d | 113.1d | 18582 | 100%
1 | Civils Ground Works | 44755 | 44755 | 0 | 44755 | 0 | 100% | 20-Jun-22 08:00 AM | 05-Sep-22 04:00 PM | 20-Jun-22 08:00 AM | 12-Aug-22 04:00 PM | 55.0d | 40.0d | 44755
A5100 | Ground Excavation | 20000 | 20000 | 0 | 20000 | 0 | 100% | 20-Jun-22 08:00 AM | 15-Jul-22 04:00 PM | 20-Jun-22 08:00 AM | 15-Jul-22 04:00 PM | 20.0d | 20.0d | 20000 | 100%
A5110 | Install Duct | 2779 | 2779 | 0 | 2779 | 0 | 100% | 07-Jul-22 08:00 AM | 03-Aug-22 04:00 PM | 07-Jul-22 08:00 AM | 18-Jul-22 04:00 PM | 20.0d | 8.0d | 2779 | 100%
A5120 | JB Excavations | 2981 | 2981 | 0 | 2981 | 0 | 100% | 19-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 19-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 2.0d | 2.0d | 2981 | 100%
A5130 | Reinstate & Backfill | 4145 | 4145 | 0 | 4145 | 0 | 100% | 08-Aug-22 08:00 AM | 12-Aug-22 04:00 PM | 08-Aug-22 08:00 AM | 12-Aug-22 04:00 PM | 5.0d | 5.0d | 4145 | 100%
A5190 | Traffic Management | 14850 | 14850 | 0 | 14850 | 0 | 100% | 18-Jul-22 08:00 AM | 05-Sep-22 04:00 PM | 18-Jul-22 08:00 AM | 12-Aug-22 04:00 PM | 35.0d | 20.0d | 14850 | 100%
2 | HDD | 36699 | 36699 | 0 | 36699 | 0 | 100% | 21-Jul-22 08:00 AM | 10-Aug-22 04:00 PM | 11-Jul-22 08:00 AM | 22-Jul-22 04:00 PM | 15.0d | 10.0d | 36699
A5180 | HDD Works | 36699 | 36699 | 0 | 36699 | 0 | 100% | 21-Jul-22 08:00 AM | 10-Aug-22 04:00 PM | 11-Jul-22 08:00 AM | 22-Jul-22 04:00 PM | 15.0d | 10.0d | 36699 | 100%
447 | Overhead Lines | 17455 | 17455 | 0 | 17455 | 0 | 100% | 20-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 20-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 1.0d | 1.0d | 17455
A5150 | OHL Stand Pole | 17455 | 17455 | 0 | 17455 | 0 | 100% | 20-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 20-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 1.0d | 1.0d | 17455 | 100%
448 | Cable Install | 0 | 0 | 0 | 0 | 0 | 0% | 19-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 19-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 7.0d | 7.0d | 0
T13940 | Cable Pulling | 0 | 0 | 0 | 0 | 0 | 100% | 19-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 19-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 2.0d | 2.0d | 0 | 100%
T13950 | Cable Sheath Tests | 0 | 0 | 0 | 0 | 0 | 100% | 21-Jul-22 08:00 AM | 22-Jul-22 04:00 PM | 21-Jul-22 08:00 AM | 22-Jul-22 04:00 PM | 2.0d | 2.0d | 0 | 100%
T13960 | Joint & Terminate Cables | 0 | 0 | 0 | 0 | 0 | 100% | 25-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 25-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 3.0d | 3.0d | 0 | 100%
443 | Outages | 0 | 0 | 0 | 0 | 0 | 0% | 20-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 20-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 8.0d | 8.0d | 0
TC1340 | Outage: Stand Pole (Circuit name is: PCOP 31881 NV 6084 - HV1 Earlham Grid - Hopton) | 0 | 0 | 0 | 0 | 0 | 100% | 20-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 20-Jul-22 08:00 AM | 20-Jul-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
TC1350 | Outage: Jointing & Connection (Circuit name is: PCOP 31882 NV 6085 - HV1 Earlham Grid - Hopton) | 0 | 0 | 0 | 0 | 0 | 100% | 27-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 27-Jul-22 08:00 AM | 27-Jul-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
449 | Test & Commissioning | 2023 | 2023 | 0 | 2023 | 0 | 100% | 21-Jul-22 08:00 AM | 04-Sep-22 04:00 PM | 21-Jul-22 08:00 AM | 01-Sep-22 04:00 PM | 45.0d | 42.0d | 2023
TC1250 | As-Laid Cable Diagram Submitted to Netmap | 0 | 0 | 0 | 0 | 0 | 100% | 01-Sep-22 08:00 AM | 04-Sep-22 04:00 PM | 01-Sep-22 08:00 AM | 01-Sep-22 04:00 PM | 4.0d | 1.0d | 0 | 100%
TC1310 | UKPN Commissioing Engineer (DLO) | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-22 08:00 AM | 12-Aug-22 04:00 PM | 12-Aug-22 08:00 AM | 12-Aug-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
CC4660 | Final Customer Connection | 0 | 0 | 0 | 0 | 0 | 100% | 12-Aug-22 08:00 AM | 12-Aug-22 04:00 PM | 12-Aug-22 08:00 AM | 12-Aug-22 04:00 PM | 1.0d | 1.0d | 0 | 100%
TC1330 | SAP - MP | 2023 | 2023 | 0 | 2023 | 0 | 100% | 21-Jul-22 08:00 AM | 24-Jul-22 04:00 PM | 21-Jul-22 08:00 AM | 24-Jul-22 04:00 PM | 4.0d | 4.0d | 2023 | 100%
46 | Closure | 0 | 0 | 0 | 0 | 0 | 0% | 08-Aug-22 08:00 AM | 01-Oct-24 04:00 PM | 12-Aug-22 08:00 AM |  | 537.0d | 45.0d | 0
CLO3100 | Project Handover | 0 | 0 | 0 | 0 | 0 | 0% | 01-Oct-24 08:00 AM | 01-Oct-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
CLO120 | Review and Approve: As-Built / As- Laid Drawings & H&S File | 0 | 0 | 0 | 0 | 0 | 100% | 02-Sep-22 08:00 AM | 15-Sep-22 04:00 PM | 02-Sep-22 08:00 AM | 17-Oct-22 04:00 PM | 10.0d | 31.0d | 0 | 100%
A4590 | Project Handover - to Network Ops | 0 | 0 | 0 | 0 | 0 | 0% | 01-Oct-24 08:00 AM | 01-Oct-24 04:00 PM |  |  | 1.0d | 0.0d | 0 | 0%
A4610 | Financial Closure | 0 | 0 | 0 | 0 | 0 | 0% | 01-Oct-24 08:00 AM | 01-Oct-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
A4600 | Deadline for submission of defined costs (65 days from contract completion) | 0 | 0 | 0 | 0 | 0 | 0% | 01-Oct-24 08:00 AM | 01-Oct-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%
GATE-GOV-C-D | Gate D Governance | 0 | 0 | 0 | 0 | 0 | 0% | 08-Aug-22 08:00 AM | 01-Oct-24 08:00 AM | 12-Aug-22 08:00 AM |  | 536.0d | 1.0d | 0
R2080 | Risks e.g Outage, Client Driven, Network Fault, Storm.... | 0 | 0 | 0 | 0 | 0 | 100% | 08-Aug-22 08:00 AM | 05-Sep-22 04:00 PM | 12-Aug-22 08:00 AM | 12-Aug-22 04:00 PM | 20.0d | 1.0d | 0 | 100%
GateD01 | Gate D / Closure/ Completion Certificate | 0 | 0 | 0 | 0 | 0 | 0% | 01-Oct-24 08:00 AM | 01-Oct-24 08:00 AM |  |  | 0.0d | 0.0d | 0 | 0%